BIDDING DOCUMENT

___________________________________

TENDER NO. ZESCO/003/2024

TENDER FOR ENGINEERING, PROCUREMENT AND CONSTRUCTION PLUS FINANCE (EPC+F) WORKS OF COPPERBELT NETWORK REINFORCEMENT PROJECT (PACKAGE B) - ZESCO/003/2023 - ZESCO LIMITED

ZESCO Limited

Stand Number 6949

Great East Road

P. O Box 33304

Lusaka, Zambia

Tel: 260 211 223971

Fax: 260 211 223971

Part 1: Instructions To Bidders

JANUARY 2023

Table of Contents

SINGLE STAGE BIDDING	1

Section I. Invitation for Bids	2

Section II. Instructions to Bidders	7

Notes on the Instructions to Bidders	7

Table of Clauses	8

Section III. Bid Data Sheet	37

Notes on the Bid Data Sheet	37

Section II.  Bidding Data Sheet (BDS)	38

Section IV. General Conditions of Contract	68

Notes on the General Conditions of Contract	68

Table of Clauses	69

Section V. Special Conditions of Contract	137

Notes on the Special Conditions of Contract	137

Section VI. Technical Specifications and Drawings	147

Notes on Preparing the Technical Specifications and Drawings	147

Section VII. Sample Forms and Procedures	149

Notes on the Sample Forms and Procedures	149

1. Bid Forms and Price Schedules	152

2. Form of Bid Security (Bank Guarantee)	166

3. Form of Bid Security (Bid Bond)	167

4. Bid-Securing Declaration	168

5.  Form of Contract Agreement	169

6. Performance Security Forms1F1F1F	188

7. Bank Guarantee Form for Advance Payment	193

8. Form of Completion Certificate	195

9. Form of Operational Acceptance Certificate	196

10. Change Order Procedures	197

Section VIII. Eligible Countries	211

Acronyms

BDS	Bid Data Sheet

CIF	Cost, Insurance and Freight

CIP	Carriage and Insurance Paid to (named place of destination)

CPM	Critical Path Method

DDP	Delivered Duty Paid (named place of destination)

EDI	Electronic Data Interchange

ENAA	Engineering Advancement Association of Japan

EXW	Ex factory, ex works or ex warehouse

FCA	Free Carrier

FIDIC	Fédération Internationale des Ingénieurs Conseils (International Federation of Consulting Engineers)

FOB	Free on Board

GCC	General Conditions of Contract

IBRD	International Bank for Reconstruction and Development

ICC	International Chamber of Commerce

IDA	International Development Association

IFB	Invitation for Bids

ITB	Instructions to Bidders

SBD	Standard Bidding Document

SCC	Special Conditions of Contract

TS	Technical Specifications and Drawings

UNCITRAL	United Nations Commission on International Trade Law

# SINGLE STAGE BIDDING

PART 1

INVITATION FOR BIDS (IFB), INSTRUCTIONS TO BIDDERS AND CONTRACT TERMS AND CONDITIONS

# Section I. Invitation for Bids

ZESCO LIMITED

INVITATION FOR BIDS

IFB TITLE AND NUMBER: TENDER FOR ENGINEERING, PROCUREMENT AND CONSTRUCTION PLUS FINANCE (EPC+F) WORKS OF COPPERBELT NETWORK REINFORCEMENT PROJECT (PACKAGE B) - ZESCO/003/2023 - ZESCO LIMITED

- ZESCO Limited intends to reinforce the power transmission and distribution network in the Copperbelt Province to increase the power transfer capacity and enhance the security and quality of power supply in the province. The project has been divided into two parts: Tender A and Tender B. This tender B is for the reinforcement of transmission and distribution networks in Luanshya, Mpongwe and Ndola Districts while Tender A is for the reinforcement of the rest of the districts in the province.

- This reinforcement will allow ZESCO to supply power to customers whose power supply applications have been pending for some time and accommodate future customers.

- The brief scope, among other works, includes the following:

  - Construction of Transmission and Distribution substations in the above-mentioned Districts

  - Construction of Transmission and Distribution Lines in the above-mentioned Districts

A detailed scope is outlined in the tender document.

- ZESCO Limited now invites sealed bids from eligible bidders for the Engineering, Procurement, Construction and Commissioning of Transmission Lines and Substations as per detailed scope of works provided in the solicitation document.

- Bidding will be conducted through Open International Bidding (OIB) procedures specified in the Public Procurement Act of No. 8 of 2020 (PPA) and the Public Procurement Regulations of 2022. Foreign bidders and local bidders are required to partner with citizen. The term citizen or local bidder is defined in the PPA.

- The bidder shall arrange and offer financing proposals for the project with competitive rates from at least three (3) Financing or Lending Institution and the proposal(s) shall be submitted together with the bid. The bidder may propose own financing proposal at better or financing proposals similar to those of financing institutions.  The following shall form part of the termsheet as a minimum:

  - loan period of not less than 10 years

  - grace period on payment of both interest and principal covering at least for the construction period

  - Interest rate maximum margin of 2%

  - No Government Security to be provided, available security is an escrow account to be funded over two years.

  - The loan amount should cover the full EPC contract amount.

- Interested eligible bidders may obtain further information from and inspect the bidding documents at the address given below from 08:00 to 12:30 hours and from 14:00 to 16:30 hours, Monday to Friday respectively.

- Qualifications requirements are provided in the bidding documents.

- All bids must be accompanied by a bid security of not less than 2% of the bid sum duly signed and sealed by the guarantor(s) as per sample form provided in the bidding document.

- A complete set of bidding documents in English may be purchased by interested bidders at the address below upon payment of a non-refundable fee of K1,000.00 or its equivalent in any freely convertible currency. The method of payment will be cash or bank (managers) cheque issued by a recognized Commercial Bank acceptable to the Purchaser, or direct deposit or transfer of funds into the Purchaser’s bank account with evidence of such deposit as follows:

| BANK NAME | : | INDO-ZAMBIA BANK LIMITED |
| --- | --- | --- |
| ADDRESS | : | PLOT NO. 6907, P.O. BOX 35411, CAIRO ROAD, LUSAKA, ZAMBIA |
| ACCOUNT NAME | : | ZESCO LTD – CORPORATE HEAD OFFICE |
| ACCOUNT NUMBER | : | 0012020000001 |
| BRANCH | : | LUSAKA MAIN |
| SHORT CODE | : | 090001 |

- The bidding documents may be collected from the office of the Senior Manager Procurement at ZESCO Limited Head Office at the address given below. The documents may also be sent electronically to bidders upon request via email on REKalumbi@zesco.co.zm and copying LNyirenda@zesco.co.zm.

- All bidders are advised that there will be a mandatory site visit of the project sites from 5 to 9 February 2023 and the detailed per site visitation programme shown in Table 1 below:

Table 1: Site Visitation Programme

| Place To Be Visited | Proposed Luanshya 330/132/33kV substation, 132kV lines from Luanshya 330/132/33kV substation to Kafulafuta 132/33kV and Mine Farm 132/33/11kV and the proposed distribution network in Luanshya | Proposed 132kV lines from Luanshya 330/132/33kV substation to proposed Chichele 132/33kV substation and Bwana Mkubwa 132/33kV substation, and the proposed distribution network in Ndola | Proposed 132kV line from Chichele 132/33kV substation to proposed New Kitwe 132/33/11kV substation and the proposed 132kV line from Luanshya 330/132/33kV substation to proposed Mpongwe 132/88/33kV substation. |
| --- | --- | --- | --- |
| DATE | 5 February 2024 |  |  |
| TIME | 8:30hrs | TBA | TBA |
| Meeting Place | Ndola Divisional Boardroom (1st Floor) Then proceed to Luanshya Turn Off on the Ndola – Kitwe Dual Carriage Way | Luanshya Turn Off on the Ndola – Kitwe Dual Carriage Way | ZESCO Divisional Office in Ndola |

- The bids must be appropriately bound, sealed and bold labelled and delivered to the address below at or before 10:30 hours on Friday, 1 March 2024. Electronic bidding will not be permitted. Late bids will be rejected.

- The closing date for the receipt of the bids is Friday, 1 March 2024 at 10.30 hours local time. The bids will be opened immediately thereafter in the Main Conference Room, New Procurement Department Offices situated at RCC Building, in the presence of bidders or representatives who may choose to attend.

- The address(es) referred to above are:

- For Inspection and Purchase of Bidding Documents

ZESCO Limited

Attention: Head – Procurement

Ground Floor, New Procurement Department Offices

RCC Building, ZESCO Limited Head Office Premises

Adjacent to ZESCO Limited Filling Station at Central Stores

Stand Number 6949, Great East Road

P.O. Box 33304, 10101, Lusaka, Zambia.

Fax: +260 (211) 223971

Website: www.zesco.co.zm

- For Clarifications of Bidding Documents

ZESCO Limited

Attention: Head – Procurement

Ground Floor, New Procurement Department Offices

RCC Building, ZESCO Limited Head Office Premises

Adjacent to ZESCO Limited Filling Station at Central Stores

Stand Number 6949, Great East Road

P.O. Box 33304, 10101, Lusaka, Zambia.

Fax: +260 (211) 223971

Website: www.zesco.co.zm

- For Submission of Bids

ZESCO Limited

Tender Box located at the Ground Floor

Main Entrance of New Procurement Department Offices

RCC Building, ZESCO Limited Head Office Premises

Adjacent to ZESCO Limited Filling Station at Central Stores

Stand Number 6949

Great East Road

P.O Box 33304, 10101, Lusaka, Zambia

- For Opening of Bids

ZESCO Limited

Main Conference Room

New Procurement Department Offices

RCC Building, ZESCO Limited Head Office

Adjacent to ZESCO Limited Filling Station at Central Stores

Stand Number 6949, Great East Road

P.O. Box 33304, 10101, Lusaka, Zambia

………………………………

FELIX H. MUNSAKA

HEAD – PROCUREMENT

# Section II. Instructions to Bidders

## Notes on the Instructions to Bidders This section of the bidding documents provides the information necessary for bidders to prepare responsive bids, in accordance with the requirements of the Employer. It also provides information on bid submission, opening and evaluation, and on contract award. Section II contains provisions that are to be used unchanged. Section III consists of provisions that supplement, amend, or specify in detail information or requirements included in Section II and that are specific to each procurement. Matters governing the performance of the Contractor, payments under the contract, or matters affecting the risks, rights, and obligations of the parties under the contract are not normally included in this section, but instead under Section IV, General Conditions of Contract, and/or Section V, Special Conditions of Contract. If duplication of a subject is inevitable in the other sections of the document prepared by the Employer, care must be exercised to avoid contradictions between clauses dealing with the same matter. These Instructions to Bidders will not be part of the contract.

## Table of Clauses

A. Introduction

1. Source of Funds

2. Eligible Bidders

3. Eligible Plant, Equipment, and Services

4. Cost of Bidding

B. The Bidding Documents

5. Content of Bidding Documents

6. Clarification of Bidding Documents; and Pre-Bid Meeting

7. Amendment of Bidding Documents

C. Preparation of Bids

8. Language of Bid

9. Documents Comprising the Bid

10. Bid Form and Price Schedules

11. Bid Prices

12. Bid Currencies

13. Bid Security

14. Period of Validity of Bid

15. Format and Signing of Bid

D. Submission of Bids

16. Sealing and Marking of Bids

17. Deadline for Submission of Bids

18. Late Bids

19. Modification and Withdrawal of Bids

E. Bid Opening and Evaluation

20. Opening of Bids by Employer

21. Clarification of Bids

22. Preliminary Examination of Bids

23. Conversion to Single Currency

24. Technical Evaluation

25. Commercial Evaluation

26. Domestic Preference

27. Contacting the Employer

F. Award of Contract

28. Post-qualification

29. Award Criteria

30. Employer’s Right to Accept Any Bid and to Reject Any or All Bids

31. Notification of Award

32. Signing the Contract Agreement

33. Performance Security

34. Arbitrator

35. Fraud and Corruption

Instructions to Bidders

A. Introduction

| 1. Source of Funds | 1.1 The Employer indicated in the BDS has applied for or received financing (hereinafter called “funds”) toward the cost of the project or programme named in the BDS. The Employer intends to apply a portion of the funds to eligible payments under the contract(s) for which these Bidding Documents are issued. 1.2 Payments by the Employer will be made only at the request of the Engineer. The Government prohibits a withdrawal for the purpose of any payment to persons or entities, or for any import of equipment, plant, or materials, if such payment or import is prohibited by a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations. |
| --- | --- |
| 2. Eligible Bidders | 2.1 A Bidder may be a natural person, private entity, government-owned entity—subject to ITB 4.5—or any combination of such entities in the form of a joint venture or association (JVA) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a joint venture or association: - unless otherwise specified in the BDS, all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms, and (b) the JVA shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the partners of the JVA during the bidding process and, in the event the JVA is awarded the Contract, during contract execution. 2.2 A Bidder, and all partners constituting the Bidder, may have the nationality of any country subject to the restrictions specified in Section V, Eligible Countries. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract including related Services. 2.3 A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this bidding process, if : - they have at least one controlling partner in common; or - they receive or have received any direct or indirect subsidy from any of them; or - they have the same legal representative for purposes of this bid; or - they have a relationship with each other directly that puts them in a position to have access to information about or influence on the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or - a Bidder participates in more than one bid in this bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which such Bidder is involved. However, this does not limit the inclusion of the same subcontractor in more than one bid; or - a Bidder participated as a consultant in the preparation of the design or technical specifications of the works that are the subject of the bid; (g) a Bidder or any of its affiliates has been hired (or is proposed to be hired) by the Employer or Employer as Engineer for the Contract implementation. 2.4 A Bidder that has been sanctioned by ZPPA in accordance with the above ITB 3.1 (d), , shall be ineligible to be awarded a Government-financed contract, or benefit from a Government-financed contract, financially or otherwise, during such period of time as ZPPA shall determine. 2.5 A statutory corporation or body or company in which Government has a majority or controlling interest shall be eligible only if they meet the provisions of Section 34 of the Public Procurement Act of 2008. To establish eligibility, the government-owned enterprise or institution should provide all relevant documents (including its charter) sufficient to demonstrate that it meets the provisions of Section 34(2) of the Public Procurement Act of 2008. 2.6 Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. 2.7 Bidders shall be excluded if: - as a matter of law or official regulation, the Government prohibits commercial relations with that country, provided that Cooperating Partners involved are satisfied that such exclusion does not preclude effective competition for the supply of Works required; or - by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government prohibits any import of goods or contracting of Works or services from that country or any payments to persons or entities in that country. |
| 3. Eligible Plant, Equipment, and Services | 3.1 For the purposes of these bidding documents, the words “facilities,” “plant and equipment,” “installation services,” etc., shall be construed in accordance with the respective definitions given to them in the General Conditions of Contract. 3.2 All plant and equipment to be supplied and installed and services carried out under the contract shall have their origin in any country, , and pursuant to Section VIII Eligibility for the Provision of Goods, Works and Services, and all expenditures made under the contract will be limited to such plant, equipment, and services. 3.3 For purposes of this clause, “origin” means the place where the plant and equipment or component parts thereof are mined, grown, or produced. Plant and equipment are produced when, through manufacturing, processing or substantial and major assembling of components, a commercially recognized product results that is substantially different in basic characteristics or in purpose or utility from its components. 3.4 The origin of the plant, equipment, and services is distinct from the nationality of the Bidder. |
| 4. Cost of Bidding | 4.1 The Bidder shall bear all costs associated with the preparation and submission of its bid, and the Employer will in no case be responsible or liable for these costs, regardless of the conduct or outcome of the bidding process. |

B. The Bidding Documents

| 5. Content of Bidding Documents | 5.1 The facilities required, bidding procedures, contract terms and technical requirements are prescribed in the bidding documents. The bidding documents include the following sections: Invitation for Bids (IFB) Instructions to Bidders (ITB) Bid Data Sheet (BDS) General Conditions of Contract (GCC) Special Conditions of Contract (SCC) Technical Specifications and Drawings (TS) Forms and Procedures (FP) 1. Bid Form and Price Schedules 2. Bid Security Form 3. Form of Contract Agreement 4. Performance Security Forms 5. Bank Guarantee Form for Advance Payment 6. Form of Completion Certificate 7. Form of Operational Acceptance Certificate 8. Change Order Procedures Eligibility for the Provision of Goods, Works, and Services. 5.2 The Bidder is expected to examine all instructions, forms, terms, specifications and other information in the bidding documents. Failure to furnish all information required by the bidding documents or submission of a bid not substantially responsive to the bidding documents in every respect will be at the Bidder’s risk and may result in rejection of its bid. |
| --- | --- |
| 6. Clarification of Bidding Documents; and Pre-Bid Meeting | 6.1 A prospective Bidder requiring any clarification of the bidding documents may notify the Employer in writing or by cable (hereinafter, the term cable is deemed to include Electronic Data Interchange (EDI), telex or telefax) at the Employer’s mailing address indicated in the BDS. Similarly, if a Bidder feels that any important provision in the documents, such as those listed in ITB Sub-Clause 9.3(d), will be unacceptable, such an issue should be raised at this stage. The Employer will respond in writing to any request for clarification or modification of the bidding documents that it receives no later than twenty-eight (28) days prior to the deadline for submission of bids prescribed by the Employer. Written copies of the Employer’s response (including an explanation of the query but not identification of its source) will be sent to all prospective bidders that have received the bidding documents. 6.2 The Bidder is advised to visit and examine the site where the facilities are to be installed and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the bid and entering into a contract for supply and installation of the facilities. The costs of visiting the site shall be at the Bidder’s own expense. 6.3 The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such inspection, but only upon the express condition that the Bidder, its personnel and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof and will be responsible for death or personal injury, loss of or damage to property and any other loss, damage, costs and expenses incurred as a result of the inspection. 6.4 The Bidder’s designated representative is invited to attend a pre-bid meeting, which, if convened, will take place at the venue and time stipulated in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. The Bidder is requested, as far as possible, to submit any question in writing or by cable, to reach the Employer not later than one week before the meeting. It may not be practicable at the meeting to answer questions received late, but questions and responses will be transmitted as indicated hereafter. Minutes of the meeting, including the text of the questions raised and the responses given, together with any responses prepared after the meeting will be transmitted without delay to all purchasers of the bidding documents. Any modification of the bidding documents listed in ITB Sub-Clause 5.1 which may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to ITB Clause 7 and not through the minutes of the pre-bid meeting. |
| 7. Amendment of Bidding Documents | 7.1 At any time prior to the deadline for submission of bids, the Employer may, for any reason, whether at its own initiative, or in response to a clarification requested by a prospective Bidder, amend the bidding documents. 7.2 The amendment will be notified in writing or by cable to all prospective bidders that have purchased the bidding documents and will be binding on them. Bidders are required to immediately acknowledge receipt of any such amendment, and it will be assumed that the information contained therein will have been taken into account by the Bidder in its bid. 7.3 In order to afford prospective Bidders reasonable time in which to take the amendment into account in preparing their bid, the Employer may, at its discretion, extend the deadline for the submission of bids, in which case, the Employer will notify all bidders in writing of the extended deadline. |

C. Preparation of Bids

| 8. Language of Bid | 8.1 The bid prepared by the Bidder and all correspondence and documents related to the bid exchanged by the Bidder and the Employer shall be written in the language specified in the BDS, provided that any printed literature furnished by the Bidder may be written in another language, as long as such literature is accompanied by a translation of its pertinent passages in the language of the bid, in which case, for purposes of interpretation of the bid, the translation shall govern. |
| --- | --- |
| 9. Documents Comprising the Bid | 9.1 The bid submitted by the Bidder shall comprise the following documents: (a) Bid Form duly completed and signed by the Bidder, together with all Attachments identified in ITB Sub-Clause 9.3 below. (b) Price Schedules duly completed by the Bidder. 9.2 Bidders shall note that, if permitted according to the BDS, they are entitled to submit an alternative bid within the scope specified in the BDS. In such cases, bidders shall submit full details and justifications, etc., in Attachment 7 to the bid as indicated in ITB Sub-Clause 9.3 (g) below. 9.3 Each Bidder shall submit with its bid the following attachments: (a) Attachment 1: Bid Security (If required) A bid security furnished in accordance with ITB Clause 13. (b) Attachment 2: Power of Attorney A power of attorney, duly notarized, indicating that the person(s) signing the bid has(ve) the authority to sign the bid and thus that the bid is binding upon the Bidder during the full period of its validity in accordance with ITB Clause 14. (c) Attachment 3: Bidder’s Eligibility and Qualifications In the absence of prequalification, documentary evidence established in accordance with ITB Clause 2 that the Bidder is eligible to bid and is qualified to perform the contract if its bid is accepted. The documentary evidence of the Bidder’s eligibility to bid shall establish to the Employer’s satisfaction that the Bidder, at the time of submission of its bid, is from an eligible source country as defined in ITB Sub-Clause 2.1. The documentary evidence of the Bidder’s qualifications to perform the contract, if its bid is accepted, shall establish to the Employer’s satisfaction that the Bidder has the financial, technical, production, procurement, shipping, installation and other capabilities necessary to perform the contract, and, in particular, meets the experience and other criteria outlined in the BDS. Bids submitted by a joint venture of two or more firms as partners shall comply with the following requirements: (i) The bid shall include all the information required for Attachment 3 as described above for each joint venture partner. (ii) The bid shall be signed so as to be legally binding on all partners. (iii) One of the partners responsible for performing a key component of the contract shall be designated as leader, this authorization shall be evidenced by submitting with the bid a power of attorney signed by legally authorized signatures. (iv) The leader shall be authorized to incur liabilities and receive instructions for and on behalf of any and all partners of the joint venture, and the entire execution of the contract, including payment, shall be done exclusively with the leader. (v) All partners of the joint venture shall be liable jointly and severally for the execution of the contract in accordance with the contract terms. (vi) A copy of the agreement entered into by the joint venture partners shall be submitted with the bid. In order for a joint venture to qualify, each of its partners or combination of partners must meet the minimum criteria listed in the BDS for an individual Bidder for the component of the contract they are designated to perform. Failure to comply with this requirement will result in rejection of the joint venture bid. A firm can be a partner in only one joint venture; bids submitted by joint ventures or consortia including the same firm as partner will be rejected. In the case of a Bidder who offers to supply and/or install plant and equipment under the contract that the Bidder did not manufacture or otherwise produce and/or install, the Bidder shall (i) have the financial and other capabilities necessary to perform the contract; (ii) have been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country; and (iii) be responsible for ensuring that the manufacturer or producer complies with the requirements of ITB Sub-Clause 2.1 and meets the minimum criteria listed for an individual Bidder for that item. (d) Attachment 4: Eligibility and Conformity of the Facilities Documentary evidence established in accordance with ITB Clause 3 that the facilities offered by the Bidder in its bid or in any alternative bid (if permitted) are eligible and conform to the bidding documents. The documentary evidence of the eligibility of the facilities shall consist of a statement on the country of origin of the plant and equipment offered, which shall be confirmed by a certificate of origin issued at the time of shipment. The documentary evidence of the conformity of the facilities to the bidding documents may be in the form of literature, drawings and data, and shall furnish: (i) a detailed description of the essential technical and performance characteristics of the facilities; (ii) a list giving full particulars, including available sources, of all spare parts, special tools, etc., necessary for the proper and continuing functioning of the facilities for the period named in the BDS, following completion of facilities in accordance with provisions of contract; and (iii) a commentary on the Employer’s Technical Specifications and adequate evidence demonstrating the substantial responsiveness of the facilities to those specifications. Bidders shall note that standards for workmanship, materials and equipment designated by the Employer in the bidding documents are intended to be descriptive (establishing standards of quality and performance) only and not restrictive. The Bidder may substitute alternative standards, brand names and/or catalog numbers in its bid, provided that it demonstrates to the Employer’s satisfaction that the substitutions are substantially equivalent or superior to the standards designated in the Technical Specifications. (e) Attachment 5: Subcontractors Proposed by the Bidder The Bidder shall include in its bid details of all major items of supply or services that it proposes to purchase or sublet, and shall give details of the name and nationality of the proposed Subcontractor, including vendors, for each of those items. Quoted rates and prices will be deemed to apply to whichever Subcontractor is appointed, and no adjustment of the rates and prices will be permitted. The Bidder shall be responsible for ensuring that any Subcontractor proposed complies with the requirements of ITB Sub-Clause 2.1, and that any plant, equipment or services to be provided by the Subcontractor comply with the requirements of ITB Clause 3 and ITB Sub-Clause 9.3 (c). The Employer reserves the right to delete any proposed Subcontractor from the list prior to award of contract, and after discussion between the Employer and the Contractor, the corresponding Appendix to the form of Contract Agreement shall be completed, listing the approved Subcontractors for each item concerned. (f) Attachment 6: Deleted (g) Attachment 7: Alternative Bids (i) When alternatives to the Time Schedule called for in the corresponding Appendix to the Contract Agreement are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different time schedules. (ii) Except as provided under subparagraph (iii) below, bidders wishing to offer technical alternatives to the requirements of the bidding documents must first price the Employer’s design of the facilities as described in the bidding documents, and shall further provide all information necessary for a complete evaluation of the alternatives by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, proposed installation methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. (iii) When bidders are permitted in the BDS to submit alternative technical solutions for specified parts of the facilities, such parts shall be described in Section VI, Technical Specifications and Drawings. Technical alternatives that comply with the performance and technical criteria specified for the facilities shall be considered by the Employer on their own merits, pursuant to ITB Sub-Clause 24.2. |
| 10. Bid Form and Price Schedules | 10.1 The Bidder shall complete the Bid Form and the appropriate Price Schedules furnished in the bidding documents as indicated therein and in the Subsection “Bid Form and Price Schedules” of the bidding documents, following the requirements of ITB Clauses 11 and 12. |
| 11. Bid Prices | 11.1 Unless otherwise specified in the Technical Specifications, bidders shall quote for the entire facilities on a “single responsibility” basis such that the total bid price covers all the Contractor’s obligations mentioned in or to be reasonably inferred from the bidding documents in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction, installation and completion of the facilities. This includes all requirements under the Contractor’s responsibilities for testing, precommissioning and commissioning of the facilities and, where so required by the bidding documents, the acquisition of all permits, approvals and licenses, etc.; the operation, maintenance and training services and such other items and services as may be specified in the bidding documents, all in accordance with the requirements of the General Conditions of Contract. Items against which no price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed to be covered by the prices for other items. 11.2 Bidders are required to quote the price for the commercial, contractual and technical obligations outlined in the bidding documents. 11.3 Bidders shall give a breakdown of the prices in the manner and detail called for in the Price Schedules. Where no Price Schedules are included in the bidding documents, bidders shall present their prices in the following manner: Separate numbered Schedules shall be used for each of the following elements. The total amount from each Schedule (1 to 4) shall be summarized in a Grand Summary (Schedule 5) giving the total bid price(s) to be entered in the Bid Form. Schedule No. 1 Plant and Equipment (including Mandatory Spare Parts) Supplied from Abroad Schedule No. 2 Plant and Equipment (including Mandatory Spare Parts) Supplied from within the Employer’s Country Schedule No. 3 Local Transportation Schedule No. 4 Installation Services Schedule No. 5 Project Management, Engineering Design Schedule No. 6 Day Work for both 330kV and 132kV works Schedule No. 7 Detail Prices, Summary for 330kV and 132kV Transmission lines total cost Schedule No. 8 Substations total cost Schedule No 9 Total Project bid price Bidders shall note that the plant and equipment included in Schedule Nos. 1 and 2 above exclude materials used for civil, building and other construction works. All such materials shall be included and priced under Schedule No. 4, Installation Services. 11.4 In the Schedules, bidders shall give the required details and a breakdown of their prices as follows: (a) Plant and equipment to be supplied from abroad (Schedule No. 1) shall be quoted on CIP-named place of destination as specified in BDS. [note: The named place destination shall be the site(s) where the equipment will be installed. If it is different from the site of installation (project site) it shall be clearly stated in the BDS] (b) Plant and equipment manufactured or fabricated within the Employer’s country (Schedule No. 2) shall be quoted on an EXW (ex factory, ex works, ex warehouse or off-the-shelf, as applicable) basis, and shall be inclusive of all costs as well as duties and taxes paid or payable on components and raw materials incorporated or to be incorporated in the facilities. (c) Local transportation to the named place of destination, as specified in BDS, insurance and other services incidental to delivery of the plant and equipment including any local taxes for transportation services payable in the Employer’s country as of twenty-eight (28) days prior to the deadline for submission of bids. (Schedule No. 3).[Note: When the named place of destination is the project site, the transportation costs for Schedule No. 1 items are covered under CIP and therefore will not be stated here. This schedule will cover only for items in Schedule No.2. If the named place of destination is different from the site of installation (project site), then the transport cost from the named place of destination to project site for Schedule No.1 shall be also included here.] (d) Installation Services shall be quoted separately (Schedule No.4) and shall include rates or prices for all labor, contractor’s equipment, temporary works, materials, consumables and all matters and things of whatsoever nature, including operations and maintenance services, the provision of operations and maintenance manuals, training, etc., where identified in the bidding documents, as necessary for the proper execution of the Installation Services, including all taxes, duties, levies and charges payable in the Employer’s country as of twenty-eight (28) days prior to the deadline for submission of bids. (e) Recommended spare parts shall be quoted separately (Schedule 6) as specified in either subparagraph (a) or (b) above in accordance with the origin of the spare parts. 11.5 The terms EXW, CIF, CIP, etc., shall be governed by the rules prescribed in the current edition of Incoterms, published by the International Chamber of Commerce, 38 Cours Albert 1er, 75008 Paris, France. 11.6 The prices shall be in accordance with one of the following alternatives, as specified in the BDS: (a) Fixed Price. Prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A bid submitted with an adjustable price quotation will be treated as nonresponsive and rejected. or (b) Adjustable Price. Prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, transport and contractor’s equipment in accordance with the procedures specified in the corresponding Appendix to the Form of Contract Agreement. A bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. The price adjustment provision will not be taken into consideration in bid evaluation. Bidders are required to indicate the source of labor and material indexes in the said corresponding Appendix. |
| 12. Bid Currencies | 12.1 Prices shall be quoted in US dollars. |
| 13. Bid Security | 13.1 The Bidder shall furnish, as part of its bid, a bid security (or a Bid-Securing Declaration), as specified in the BDS. The bid security shall be in the amount stipulated in the BDS in the currency of the Employer’s country, or in the equivalent amount in a freely convertible currency. 13.2 The bid security shall, at the Bidder’s option, be in the form of either a letter of credit or a bank guarantee from a reputable banking institution, or a bond issued by a surety selected by the Bidder and located in any country. If the institution issuing the bond is located outside the Employer’s Country, it shall have a correspondent financial institution located in the Employer’s Country to make it enforceable. The format of the bank guarantee/ bond shall be in accordance with the forms included in the bidding documents; other formats may be permitted, subject to the prior approval of the Employer. Bid security shall remain valid for a period of twenty-eight (28) days beyond the original bid validity period, and beyond any extension subsequently requested under ITB Sub-Clause 14.2. 13.3 Any bid not accompanied by an acceptable bid security, (or a Bid-Securing Declaration in accordance with ITB Sub-Clause 13.1) if required, shall be rejected by the Employer as being nonresponsive, pursuant to ITB Clause 22.5. The bid security of a joint venture must be in the name of all the partners in the joint venture submitting the bid. 13.4 The bid securities of unsuccessful bidders will be returned as promptly as possible, but not later than twenty-eight (28) days after the expiration of the bid validity period. 13.5 The bid security of the successful Bidder will be returned when the Bidder has signed the Contract Agreement, pursuant to ITB Clause 32, and has furnished the required performance security, pursuant to ITB Clause 33. 13.6 The bid security may be forfeited (or the Bid-Securing Declaration executed) (a) if the Bidder withdraws its bid during the period of bid validity specified by the Bidder in the Bid Form (b) in the case of a successful Bidder, if the Bidder fails within the specified time limit (i) to sign the Contract Agreement, in accordance with ITB Clause 32, or (ii) to furnish the required performance security, in accordance with ITB Clause 33. |
| 14. Period of Validity of Bid | 14.1 Bids shall remain valid for the period named in the BDS after the closing date prescribed by the Employer for the receipt of bids, pursuant to ITB Sub-Clause 17.1. A bid valid for a shorter period shall be rejected by the Employer as being nonresponsive. 14.2 In exceptional circumstance, the Employer may solicit the Bidder’s consent to an extension of the bid validity period. The request and responses thereto shall be made in writing or by cable. If a Bidder accepts to prolong the period of validity, the bid security shall also be suitably extended. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request will not be required or permitted to modify its bid, except as provided in ITB Sub-Clause 14.3. 14.3 In the case of fixed price contracts (not subject to price adjustment), if the bid validity period is extended beyond sixty (60) days, the amounts payable in both local and foreign currencies to the Bidder selected for award shall be increased by applying the factors specified in the request for extension to both the local and the foreign currency component of the payments, respectively, for the period of delay beyond sixty (60) days after the expiry of the initial bid validity up to the time of notification of award. Bid evaluation will be based on the bid prices without considering the above correction. |
| 15. Format and Signing of Bid | 15.1 The Bidder shall prepare an original and the number of copies/sets of the bid specified in the BDS, clearly marking each one as “Original Bid,” “Copy No. 1,” “Copy No. 2,” etc., as appropriate. In the event of any discrepancy between them, the original shall govern. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Bidders submitting bids electronically shall follow the procedures specified in the BDS. 15.2 The original and all copies of the bid, each consisting of the documents listed in ITB Sub-Clause 9.1, shall be typed or written in indelible ink and shall be signed by the Bidder or a person or persons duly authorized to bind the Bidder to the contract. The latter authorization shall be indicated by written power of attorney accompanying the bid and submitted as Attachment 2 to the Bid under ITB Sub-Clause 9.3. All pages of the bid, except for unamended printed literature, shall be initialed by the person or persons signing the bid. 15.3 The bid shall contain no alterations, omissions or additions, unless such corrections are initialed by the person or persons signing the bid. 15.4 The Bidder shall furnish information as described in the last paragraph of the Form of Bid on commissions or gratuities, if any, paid or to be paid to agents relating to this bid, and to contract execution if the Bidder is awarded the contract. |

D. Submission of Bids

| 16. Sealing and Marking of Bids | 16.1 The Bidder shall seal the original and each copy of the bid in separate envelopes, duly marking the envelopes as “Original Bid” and “Copy No. [number]” The envelopes shall then be sealed in an outer envelope. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Bidders submitting bids electronically shall follow the procedures specified in the BDS. 16.2 The inner and outer envelopes shall (a) be addressed to the Employer at the address given in the BDS, and (b) bear the contract name indicated in the BDS, the Invitation for Bids title and number indicated in the BDS, and the statement “Do Not Open Before [date],” to be completed with the time and date specified in the BDS, pursuant to ITB Sub-Clause 20.1. 16.3 The inner envelopes shall also indicate the name and address of the Bidder so that the bid can be returned unopened in case it is declared “late.” 16.4 If the outer envelope is not sealed and marked as required by ITB Sub-Clause 16.2 above, the Employer will assume no responsibility for the bid’s misplacement or premature opening. If the outer envelope discloses the Bidder’s identity, the Employer will not guarantee the anonymity of the bid submission, but this disclosure will not constitute grounds for bid rejection. |
| --- | --- |
| 17. Deadline for Submission of Bids | 17.1 Bids must be received by the Employer at the address specified under ITB Sub-Clause 16.2 no later than the time and date stated in the BDS. 17.2 The Employer may, at its discretion, extend this deadline for submission of bids by amending the bidding documents in accordance with ITB Sub-Clause 7.3, in which case all rights and obligations of Employer and bidders will thereafter be subject to the deadline as extended. |
| 18. Late Bids | 18.1 Any bid received by the Employer after the bid submission deadline prescribed by the Employer, pursuant to ITB Clause 17, will be rejected and returned unopened to the Bidder. |
| 19. Modification and Withdrawal of Bids | 19.1 The Bidder may modify or withdraw its bid after submission, provided that written notice of the modification or withdrawal is received by the Employer prior to the deadline prescribed for bid submission. 19.2 The Bidder’s modifications shall be prepared, sealed, marked and dispatched as follows: (a) The Bidders shall provide an original and the number of copies specified in the BDS of any modifications to its bid, clearly identified as such, in two inner envelopes duly marked “Bid Modifications—Original” and “Bid Modifications—Copies.” The inner envelopes shall be sealed in an outer envelope, which shall be duly marked “Bid Modifications.” (b) Other provisions concerning the marking and dispatch of bid modifications shall be in accordance with ITB Sub-Clauses 16.2, 16.3 and 16.4. 19.3 A Bidder wishing to withdraw its bid shall notify the Employer in writing prior to the deadline prescribed for bid submission. The notice of withdrawal shall (a) be addressed to the Employer at the address named in the BDS, and (b) bear the contract name, the IFB number, and the words “Bid Withdrawal Notice.” Bid withdrawal notices received after the bid submission deadline will be ignored, and the submitted bid will be deemed to be a validly submitted bid. 19.4 No bid may be withdrawn in the interval between the bid submission deadline and the expiration of the bid validity period specified in ITB Clause 14. Withdrawal of a bid during this interval may result in the Bidder’s forfeiture of its bid security, pursuant to ITB Sub-Clause 13.6. |

E. Bid Opening and Evaluation

| 20. Opening of Bids by Employer | 20.1 The Employer will open the bids in public, including withdrawals and modifications made pursuant to ITB Clause 19, in the presence of bidders’ designated representatives and anyone who choose to attend, at the time, date, and location stipulated in the BDS. The bidders’ representatives who are present shall sign a register evidencing their attendance. If electronic bidding is permitted, specific opening procedures shall be as specified in the BDS. 20.2 Envelopes marked “Withdrawal” shall be opened first and the name of the Bidder shall be read out. Bids for which an acceptable notice of withdrawal has been submitted pursuant to ITB Clause 19 shall not be opened. 20.3 The bidders’ names, the Bid Prices, including any alternative Bid Price or deviation, any discounts, bid modifications and withdrawals, the presence (or absence) of bid security, and any such other details as the Employer may consider appropriate, will be announced by the Employer at the opening. Subsequently, all envelopes marked “Modification” shall be opened and the submissions therein read out in appropriate detail. No bid shall be rejected at bid opening except for late bids pursuant to ITB Clause 18. 20.4 The Employer shall prepare minutes of the bid opening, including the information disclosed to those present in accordance with ITB Sub-Clause 20.3. 20.5 Bids not opened and read out at bid opening shall not be considered further for evaluation, irrespective of the circumstances. |
| --- | --- |
| 21. Clarification of Bids | 21.1 During bid evaluation, the Employer may, at its discretion, ask the Bidder for a clarification of its bid. The request for clarification and the response shall be in writing, and no change in the price or substance of the bid shall be sought, offered or permitted. |
| 22. Preliminary Examination of Bids | 22.1 The Employer will examine the bids to determine whether they are complete, whether any computational errors have been made, whether required sureties have been furnished, whether the documents have been properly signed, and whether the bids are generally in order. 22.2 Arithmetical errors will be rectified on the following basis. If there is a discrepancy between the unit price and the total price, which is obtained by multiplying the unit price and quantity, or between subtotals and the total price, the unit or subtotal price shall prevail, and the total price shall be corrected. If there is a discrepancy between words and figures, the amount in words will prevail. If the Bidder does not accept the correction of errors, its bid will be rejected. 22.3 The Employer may waive any minor informality, nonconformity or irregularity in a bid that does not constitute a material deviation, and that does not prejudice or affect the relative ranking of any Bidder as a result of the technical and commercial evaluation, pursuant to ITB Clauses 24 and 25. 22.4 Prior to the detailed evaluation, the Employer will determine whether each bid is of acceptable quality, is complete and is substantially responsive to the bidding documents. For purposes of this determination, a substantially responsive bid is one that conforms to all the terms, conditions and specifications of the bidding documents without material deviations, objections, conditionalities or reservations. A material deviation, objection, conditionality or reservation is one (i) that affects in any substantial way the scope, quality or performance of the contract; (ii) that limits in any substantial way, inconsistent with the bidding documents, the Employer’s rights or the successful Bidder’s obligations under the contract; or (iii) whose rectification would unfairly affect the competitive position of other bidders who are presenting substantially responsive bids. 22.5 If a bid is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by the Bidder by correction of the nonconformity. The Employer’s determination of a bid’s responsiveness is to be based on the contents of the bid itself without recourse to extrinsic evidence. |
| 23. Conversion to Single Currency | 23.1 To facilitate evaluation and comparison, the Employer will convert all bid prices expressed in the amounts in various currencies in which the bid price is payable to either (a) the currency of the Employer’s country at the selling exchange rate established for similar transactions by the central bank or by a commercial bank in the Employer’s country, or (b) a currency widely used in international trade, such as U.S. dollars, at the selling rate of exchange published in the international press for the amount payable in foreign currency, and at the selling exchange rate established for similar transactions by the central bank in the Employer’s country for the amount payable in the currency of the Employer’s country. 23.2 The currency selected for converting bid prices to a common base for the purpose of evaluation, along with the source and date of the exchange rate, is specified in the BDS. |
| 24. Technical Evaluation | 24.1 The Employer will carry out a detailed evaluation of the bids previously determined to be substantially responsive in order to determine whether the technical aspects are in accordance with the requirements set forth in the bidding documents. In order to reach such a determination, the Employer will examine and compare the technical aspects of the bids on the basis of the information supplied by the bidders, taking into account the following factors: (a) overall completeness and compliance with the Technical Specifications and Drawings; suitability of the facilities offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the bid. The bid that does not meet minimum acceptable standards of completeness, consistency and detail will be rejected for nonresponsiveness. (b) achievement of specified performance criteria by the facilities (c) type, quantity and long-term availability of mandatory and recommended spare parts and maintenance services (d) any other relevant factors, if any, listed in the BDS, or that the Employer deems necessary or prudent to take into consideration. 24.2 Where alternative technical solutions have been permitted and offered in Attachment 7 to the bid, the Employer will make a similar evaluation of the alternatives, which will be treated in the technical and commercial evaluations as if they were base bids. Where alternatives are not permitted, but have in any event been offered, they shall be ignored. |
| 25. Commercial Evaluation | 25.1 The comparison shall be, on the total price in Price Schedule No.5 Grand Summary (Total of Schedule Nos. 1 to 4). The Employer’s comparison will also include the costs resulting from application of the evaluation procedures described in ITB Sub-Clause 25.2 and 25.3. 25.2 The Employer’s evaluation of a bid will take into account, in addition to the bid prices indicated in Price Schedule Nos. 1 through 5, the following costs and factors that will be added to each Bidder’s bid price in the evaluation using pricing information available to the Employer, in the manner and to the extent indicated in ITB Sub-Clause 25.3 and in the Technical Specifications: (a) the cost of all quantifiable deviations and omissions from the contractual and commercial conditions and the Technical Specifications and other deviations and omissions; (b) compliance with the time schedule called for in the corresponding Appendix to the Form of Contract Agreement and evidenced as needed in a milestone schedule provided in the bid; (c) the projected operating and maintenance costs during the life of the facilities; (d) the functional guarantees of the facilities offered; - the extra cost of work, services, facilities, etc., required to be provided by the Employer or third parties; - any other relevant factors listed in BDS. The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the contract, shall not be taken into account in bid evaluation. 25.3 Pursuant to ITB Sub-Clause 25.2, the following evaluation methods will be followed: (a) Contractual and commercial compliance The evaluation shall be based on the evaluated cost of fulfilling the contract in compliance with all commercial, contractual and technical obligations under this bidding document. (b) Time schedule (program of performance) The plant and equipment covered by this bidding are required to be shipped and installed, and the facilities shall have the precommissioning completed within the time schedule specified in the BDS after the effective date specified in the Form of Contract Agreement. Bidders are required to base their prices on the time schedule given in the corresponding Appendix to the Form of Contract Agreement (Time Schedule). If no time schedule is given, bidders shall base their price on the completion date(s) given in the BDS. No credit will be given for earlier completion. Where an Alternative Time Schedule is accepted, pursuant to ITB Sub-Clause 9.3 (g) (i), and where the completion date offered is within the limits specified in the BDS, bids offering a completion date beyond the minimum designated period shall be adjusted in the evaluation by adding a factor specified in the BDS to the bid price. Bids offering a completion date beyond the maximum designated period shall be rejected. (c) Operating and maintenance costs (i) Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given in the BDS, including the cost of spare parts for the initial period of operation stated in the BDS and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other employers similarly placed. Such costs shall be added to the bid price for evaluation. (ii) The price of recommended spare parts quoted in Price Schedule No. 6 shall not be considered for evaluation. (d) Functional Guarantees of the facilities (i) Bidders shall state the functional guarantees (e.g., performance, efficiency, consumption) of the proposed facilities as specified in BDS in response to the Technical Specifications. Plant and equipment offered shall have a minimum (or a maximum, as the case may be) level of functional guarantees specified in the BDS and Technical Specifications to be considered responsive. Bids offering plant and equipment with functional guarantees less (or more) than the minimum (or maximum) specified shall be rejected. (ii) For the purposes of evaluation, the adjustment specified in the BDS will be added to the bid price for each drop (or excess) in the responsive functional guarantees offered by the Bidder, below (or above) either a norm of one hundred (100) or the value committed in the responsive bid with the most performing functional guarantees, as specified in the BDS. (e) Work, services, facilities, etc., to be provided by the Employer Where bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the bidding documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the contract. Such costs shall be added to the bid price for evaluation. (f) Specific additional criteria The relevant evaluation method, if any, shall be detailed in the BDS and/or in the Technical Specifications. 25.4 Any adjustments in price that result from the above procedures shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.” Bid prices quoted by bidders shall remain unaltered. |
| 26. Domestic Preference | 26.1 There is no margin of domestic preference. |
| 27. Contacting the Employer | 27.1 From the time of bid opening to the time of contract award, if any Bidder wishes to contact the Employer on any matter related to its bid, it should do so in writing. 27.2 Any effort by a Bidder to influence the Employer in the Employer’s bid evaluation, bid comparison or contract award decisions may result in rejection of the Bidder’s bid. |

F. Award of Contract

| 28. Post-qualification | 28.1 In the absence of prequalification, the Employer will determine to its satisfaction whether the Bidder selected as having submitted the lowest evaluated responsive bid is qualified to satisfactorily perform the contract. 28.2 The determination will take into account the Bidder’s financial, technical and production capabilities, in particular the Bidder’s contract work in hand, future commitments and current litigation. It will be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder in Attachment 3 to the bid, as well as such other information as the Employer deems necessary and appropriate. 28.3 An affirmative determination will be a prerequisite for award of the contract to the Bidder. A negative determination will result in rejection of the Bidder’s bid, in which event the Employer will proceed to the next lowest evaluated bid to make a similar determination of that Bidder’s capabilities to perform satisfactorily. 28.4 The capabilities of the vendors and subcontractors proposed in Attachment 5 to the bid to be used by the lowest evaluated Bidder will also be evaluated for acceptability. Their participation should be confirmed with a letter of intent between the parties, as needed. Should a vendor or subcontractor be determined to be unacceptable, the bid will not be rejected, but the Bidder will be required to substitute an acceptable vendor or subcontractor without any change to the bid price. |
| --- | --- |
| 29. Award Criteria | 29.1 Subject to ITB Clause 30, the Employer will award the contract to the successful Bidder whose bid has been determined to be substantially responsive and to be the lowest evaluated bid, further provided that the Bidder is determined to be qualified to perform the contract satisfactorily. |
| 30. Employer’s Right to Accept Any Bid and to Reject Any or All Bids | 30.1 The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to award of contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Employer’s action. |
| 31. Notification of Award | 31.1 Prior to the expiration of the period of bid validity, the Employer will notify the successful Bidder in writing, that its bid has been accepted. The notification of award will constitute the formation of the contract.31.2The Employer shall publish in UNDB online and in the dgMarket the results identifying the bid and lot numbers and the following information: (i) name of each Bidder who submitted a Bid; (ii) bid prices as read out at bid opening; (iii) name and evaluated prices of each Bid that was evaluated; (iv) name of bidders whose bids were rejected and the reasons for their rejection; and (v) name of the winning Bidder, and the price it offered, as well as the duration and summary scope of the contract awarded. After publication of the award, unsuccessful bidders may request in writing to the Employer for a debriefing seeking explanations on the grounds on which their bids were not selected. The Employer shall promptly respond in writing to any unsuccessful Bidder who, after Publication of contract award, requests a debriefing. 31.3 Upon the successful Bidder’s furnishing of the performance security pursuant to ITB Clause 33, the Employer will promptly notify each unsuccessful Bidder and will discharge its bid security, pursuant to ITB Sub-Clause 13.4. |
| 32. Signing the Contract Agreement | 32.1 At the same time as the Employer notifies the successful Bidder that its bid has been accepted, the Employer will send the Bidder the Contract Agreement provided in the bidding documents, incorporating all agreements between the parties. 32.2 Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Bidder shall sign and date the Contract Agreement and return it to the Employer. 32.3 Notwithstanding ITB 32.2 above, in case signing of the Contract Agreement is prevented by any export restrictions attributable to the Employer, to the country of the Employer, or to the use of the Plant and Installation Services to be supplied, where such export restrictions arise from trade regulations from a country supplying those Plant and Installation Services, the Bidder shall not be bound by its bid, always provided, however, that the Bidder can demonstrate to the satisfaction of the Employer and of the Bank that signing of the Contact Agreement has not been prevented by any lack of diligence on the part of the Bidder in completing any formalities, including applying for permits, authorizations and licenses necessary for the export of the Plant and Installation Services under the terms of the Contract. |
| 33. Performance Security | 33.1 Within twenty-eight (28) days after receipt of the notification of award, the successful Bidder shall furnish the performance security in the amount given in the BDS and in the form provided in Section VII, Sample Forms and Procedures, of the bidding documents or in another form acceptable to the Employer. 33.2 Failure of the successful Bidder to comply with the requirements of ITB Clause 32 or Clause 33 shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security, in which event the Employer may make the award to the next lowest evaluated Bidder or call for new bids. |
| 34. Arbitrator | 34.1 The Employer proposes that the person named in the BDS be appointed as Arbitrator under the contract, at an hourly fee stated in the BDS. A résumé of the named person is attached to the BDS, as well as a description of the expenses that would be considered reimbursable. If a Bidder does not accept the Arbitrator proposed by the Employer, it should so state in its Bid Form and make a counterproposal of an Arbitrator and an hourly fee. If on the day the Contract Agreement is signed, the Employer and the Contractor have not agreed on the appointment of the Arbitrator, the Arbitrator shall be appointed, at the request of either party, by the Appointing Authority specified in the Special Conditions of Contract, pursuant to GCC Sub-Clause 6.1.4. |
| 35. Fraud and Corruption | 35.1 It is the Government’s policy to require that Procuring Entities (including beneficiaries of the funds), as well as bidders, suppliers, and contractors and their agents (whether declared or not), personnel, subcontractors, sub-consultants, service providers and suppliers, under Government-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Government: - defines, for the purposes of this provision, the terms set forth below as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Bank investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or (bb) acts intended to materially impede the exercise of the Bank’s inspection and audit rights provided for under sub-clause 3.1(e) below. - will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for the contract in question; - will cancel the the funds allocated to a contract if it determines at any time that representatives of the Employer or of a beneficiary engaged in corrupt, fraudulent, collusive, or coercive practices during the procurement or the execution of that contract, without the Employer having taken timely and appropriate action satisfactory to remedy the situation; and - will sanction a firm or an individual, at any time, in accordance with prevailing sanctions procedures, including suspending or barring a bidder in accordance with Sections sixty-five, sixty-six and sixty-seven of the Public Procurement Act of 2008 and in accordance with regulations 162 to 167 of the Public Procurement Regulations of 2011: (i) to be awarded a Government-financed contract; and (ii) to be a nominatedb sub-contractor, consultant, manufacturer or supplier, or service provider of an otherwise eligible firm being awarded a Government-financed contract. A bidder or supplier aggrieved by such a decision, may appeal in accordance with Section sixty-nine of the Public Procurement Act of 2008. 35.2 In further pursuance of this policy, Bidders shall permit the Government to inspect any accounts and records and other documents relating to the Bid submission and contract performance, and to have them audited by auditors appointed by the Government. |
|  | 35.3 Furthermore, Bidders shall be aware of the provision stated in Sub-Clause 15.6 of the General Conditions. |

# Section III. Bid Data Sheet

## Notes on the Bid Data Sheet Section III is intended to assist the Employer in providing the specific information in relation to corresponding clauses in the Instructions to Bidders included in Section II,

Bid Data Sheet

The following bid-specific data for the plant and equipment to be procured shall amend and/or supplement the provisions in the Instructions to Bidders (ITB). Whenever there is a conflict, the provisions herein shall prevail over those in the ITB.

| ITB Clause Reference | A. General |
| --- | --- |
| ITB 1.1 | The Procuring Entity is: ZESCO Limited |
| ITB 1.1 | The name and identification number of the OIB are: TENDER FOR ENGINEERING, PROCUREMENT AND CONSTRUCTION PLUS FINANCE (EPC+F) WORKS OF COPPERBELT NETWORK REINFORCEMENT PROJECT (PACKAGE B) - ZESCO/003/2023 - ZESCO LIMITED |
| ITB 1.1 | The project shall be funded by ZESCO Limited in collaboration with a financier to be facilitated by the bidder. This is a requisite for the bidders to participate in the bidding process. The bidders will be required to show the ability to facilitate for the financing of the project. |
| ITB 1.1 | The name of the Project is: Copperbelt Network Reinforcement Project – Contract B |
| ITB 2.4 | Lists of debarred firms is available at http://www.zppa.org.zm |
|  | B. Contents of Bidding Documents |
| ITB5.1 | The Bidding Document are packaged in five (5) parts as follows: - Part 1: Bidding Instructions, Forms and Procedures and Conditions of Contract - Part 2: Employer’s requirements for substations - Part 3: Employer’s requirements for lines - Part 4: Price Schedules - Part 5: Employers Drawings |
| ITB 6.1 | For Clarification of bid purposes only, the Procuring Entity’s address is: Attention: Head - Procurement Address: ZESCO Limited, Regional Control Centre Building South Wing, P.O Box 33304, Lusaka, Tel: 260 211 223971 Fax : 260 01 362366/223971 City: Lusaka, Zambia Telephone: 260 211 223971 Facsimile number: 260 01 362366/223971 Electronic mail address: REKalumbi@zesco.co.zm; LNyirenda@zesco.co.zm Requests for clarification should be received by the Employer no later than Fourteen (14 days) from date of tender closing. No late submission of request for clarifications shall be accepted. |
| ITB 6.2 | In addition, All bidders are advised that there will be a mandatory site visit of the project sites as per site visitation programme shown in Table below: Place To Be Visited; Proposed Luanshya 330/132/33kV substation, 132kV lines from Luanshya 330/132/33kV substation to Kafulafuta 132/33kV and Mine Farm 132/33/11kV and the proposed distribution network in Luanshya; Proposed 132kV lines from Luanshya 330/132/33kV substation to proposed Chichele 132/33kV substation and Bwana Mkubwa 132/33kV substation, and the proposed distribution network in Ndola; Proposed 132kV line from Chichele 132/33kV substation to proposed New Kitwe 132/33/11kV substation and the proposed 132kV line from Luanshya 330/132/33kV substation to proposed Mpongwe 132/88/33kV substation.. DATE; 5 February 2024; TBA; TBA. TIME; 8:30hrs; TBA; TBA. Meeting Place; Ndola Divisional Boardroom (1st Floor) Luansya Turn Off on the Ndola – Kitwe Dual Carriage Way; Luansya Turn Off on the Ndola – Kitwe Dual Carriage Way; ZESCO Divisional Office in Ndola. |
|  | C. Preparation of Bids |
| ITB 8.1 | The language of the bid is: English. |
| ITB9.3 (b) | The written confirmation of authorization to sign on behalf of the Bidder shall be a Power of Attorney: Issued by the Company Board / Company Secretary or Registered Legal Practitioner and should be duly Notarized by Public Notary or Court of Law. |
| ITB9.3 (c) | In the case of Bids submitted by an existing or intended Joint Venture Agreement (JVCA), an undertaking signed by all parties clearly spelling out the roles and responsibilities of each partner should be submitted as part of the bid in addition to the following. - Stating that all parties shall be jointly and severally liable, if so required in accordance with ITB 4.1(a), and - Nominating a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JVCA during the bidding process and, in the event the JVCA is awarded the Contract, during contract execution. |
| ITB 9.3 (g) | Alternative bids are permitted only if the main bid is offered. Alternatives to the Time Schedule shall not be permitted. |
| ITB 11.1 (e) | Manufacturer’s authorization is required as per sample in these bidding dcouments. Any deviation from the format will render the Bid non-responsive. This shall be required for the following equipment: - 330kV, 132kV, and 33kV switchgear - 330kV, 132kV, and 33kV Power Transformers - Protection/Control IEDs - DC systems (DC battery and charger) - 330kV and 132kV Polymer insulators - OPGW, aerial earth and Earthwire - Hardware fittings and Connectors - Telecommunications equipment - Phase Conductors - Steel Monopole and Steel lattice structures - Substation Automation System The Bidder shall submit the following additional documents in its bid: - Manufacture’s brochures containing details of equipment, data sheets and drawings; - Type test certificates for all key equipment to be supplied including Quality Assurance Certification for the manufacturers. Failure to submit these documents shall render the Bid non-responsive. |
| ITB 11.4 (a) and (b) | Place of Destination: Zambia |
| ITB 11.4 (a), (b) and (c) | Final destination (project sites): Respective project line route sections and substations in Luanshya, Mpongwe and Ndola |
| ITB 11.5 | The Incoterms edition is Incoterms 2020. |
| ITB 11.4 (a) | For all the materials supplied from abroad, the entered price shall be Delivery Duty Paid (DDP) to respective project delivery sites. However, bidders shal also include the Cost Insurance Price Paid to (CIP) respective project delivery sites as provided in the sample price schedules. Materials and services supplied locally include value added tax (VAT) at 16% except where VAT may be claimed as an input for local companies. |
| ITB 11.6 (a) | The prices quoted by the Bidder shall not be subject to adjustment during the performance of the Contract. |
| ITB13.1 | A bid shall include a Bid Security (issued by a bank) whose sample is included in Section IV of the Bidding Forms. Any Bid Security submitted in a form other than that provided shall not be accepted. |
| ITB13.2 | A Bid Security in the form of Bank Guarantee shall be required, issued by an internationally recognised Bank through a Zambian registered Bank. The amount and currency of the bid security shall not less than 2% of the bidders’ bid sum. |
| ITB 14.1 | The bid validity period shall be One Hundred and Twenty Days (120) days. |
| ITB 15.1 | In addition to the original of the Bid, the number of copies of bid required is Five (05) i.e. One (1) Original and Four (4) copies. Bids shall be properly arranged with separators for easy of reference. In addition to the hard copies, bidders are required to submit a softcopy of their bid on a USB or CD. HOWEVER ELECTRONIC OFFERS WILL NOT BE ACCEPTED. |
|  | D. Submission and Opening of Bids |
| ITB 16.1 | Bidders shall not have the option of submitting their bids electronically. |
| ITB 16.2 (a) | The inner and outer envelops shall bear the following additional identification marks: “TENDER FOR ENGINEERING, PROCUREMENT AND CONSTRUCTION PLUS FINANCE (EPC+F) WORKS OF COPPERBELT NETWORK REINFORCEMENT PROJECT (CONTRACT B) - ZESCO/…/2023 - ZESCO LIMITED” |
| ITB 17.1 | For bid submission purposes, the Procuring Entity’s address is: Attention: Head - Procurement Address: ZESCO Limited, Ground Floor Regional Control Centre Building South Wing, P.O Box 33304, Lusaka, Tel: 260 211 223971 Fax : 260 211 223971 Floor-Room number: ZESCO Limited, Sadzu Road, Regional Control Centre Building, P.O Box 33304, Lusaka, City: Lusaka Zambia The deadline for the submission of bids is: Date: Friday, 1 March 2024 Time: 10:30 A.M, local time |
| ITB 20.1 | The bid opening shall take place at: Address: ZESCO Limited, Great East Road, Auditorium, Refurbished Regional Control Centre Building, Great East Road, Stand Number 6949, P.O Box 33304, Lusaka, City: Lusaka, Zambia Date: Friday, 1 March 2024 Time: Immediately after tender opening at 10:30 A.M, local time |
| ITB 23.1 | The currency that shall be used for bid evaluation and comparison purposes to convert all bid prices expressed in various currencies into a single currency is: United States Dollar (USD) The source of exchange rate shall be: Bank of Zambia The date for the exchange rates shall be: Two (02) weeks before date of tender closing. |
|  | E. Evaluation and Comparison of Bids |
| ITB22.1 | In addition to the requirements under ITB 9.0 and ITB 22.0 the following additional Evaluation Criteria shall be considered: (a) Qualification and Evaluation Criteria - Bidders must submit proof of purchase of Bidding Document; - Bidders must submit a Power of Attorney; issued by the Company Board/Company Secretary or Registered Legal Practitioner and should be duly Notarized by Public Notary or Court of Law; indicating that the person(s) signing the bid has (ve) the authority to sign and thus that the bid is binding upon the Bidder during the full period of its validity in accordance with ITB clause 16. - Bidders must submit information regarding any litigation, current or during the last five years, in which the Bidder is involved, the parties concerned, and disputed amount. The bidder’s litigation status shall be provided by a registered Legal Practitioner or Attorney. A written statement by the bidder himself shall not be accepted. Non-compliance with this requirement will result into disqualification of the bid; - All pending litigation shall in total not represent more than forty per cent (40%) of the Bidder’s net worth and shall be treated as resolved against the Bidder. - Bidders must submit a Manufacturer’s Authorization in the form and wording provided, for ALL the equipment listed in this Bid Data Sheet. Bidders who are manufacturers must also provide an authorization letter and state that they are the manufacturers of the said products and extend warranty/guarantee as indicated in the manufacturer’s authorization form. - Bidders must submit proof of registration as a legal entity (e.g. Certificate of Incorporation) as well as Article of Association; - The Bidder must have a proven track record and experience of handling similar overhead lines and substations projects. The Bidder must have performed at least three similar Contracts at 330kV or higher volatges in the last ten years. Bidders shall provide information on Contract values, description of services performed, goods delivered, purchaser’s name and address. Submission of only experience of the manufacturer where the bidder is not a manufacturer shall not suffice; - The Bidder must provide a detailed preliminary design for all of the works proving exercising the necessary due diligence in executing the total works. Failure to submit this information shall render the bid non-responsive; - The Bidder must submit a list of key personnel proposed for this project, indicating their qualification(s) and experience. Failure to submit this information shall render the bid non-responsive. - Bidders shall also submit a list of plant, equipment and tools, owned or rented available to be used for this project. - The bidder shall be required to arrange and offer financing proposals for the project with tentative terms sheets, competitive interest rates, repayment period and a letter of intent from at least three (3) financing or lending institutions and the proposal (s) must be submitted together with the bid. The bidder may propose own financing proposal at better or financing proposals similar to those of financing institutions. Failure to provide this information will render the bid NON-RESPONSIVE. - The Bidder are required to demonstrate that they have previously successfully secured financing for power transmission and substation projects, with a value exceeding US$250 million (Two Hundred and fifty Million United States Dollars) by providing documentary evidence of previous or current contracts, or confirmation letters from lending Financing Institutions stating the name of project, client and value of the project financed for at least two (02) projects. - The Bidder shall provide a WORK METHODOLOGY (Method Statement) outlining HOW the Works are intended to be executed; type of equipment, qualifications and number key personnel (labour) that would be used for successful completion of the project within the proposed period. The Bidder shall further submit a SCHEDULE OF WORKS accompanied by a Gantt-Chart WITH CASH FLOW projections related to the milestones in the Gantt Chart. Failure to submit this information shall render the bidder Non Responsive. - Bidders must submit audited financial statements for the last Three (03) years (2022 to 2020) to demonstrate the current soundness of the bidder’s financial position. Failure to submit this information shall render the bidder Non-Responsive. - Bidders must have annual revenue of more than US$500 Million and have a cash flow of more than US$ 80 Million. Failure to submit this information shall render the bidder Non Responsive. - Bidders shall provide a minimum of 24 months warranty on equipment; - The bidder shall arrange and offer financing proposals for the project with competitive rates from at least three (3) Financing or Lending Institution and the proposal(s) shall be submitted together with the bid. The bidder may propose own financing proposal at better or financing proposals similar to those of financing institutions. The following shall form part of the termsheet as a minimum: - loan period of not less than 10 years - grace period on payment of both interest and principal covering at least for the construction period - Interest rate maximum margin of 2% - No Government Security to be provided, available security is an escrow account to be funded over two years. - The loan amount should cover the full EPC contract amount. - Bidders must keep the prices firm during the Contract period; and - Citizen and Local Bidders must have obtained the registration certificate with Engineering Institution of Zambia (EIZ) and National Construction Council of Zambia (NCC) Certificate for electrical, civil and telecommunications of Grade 1, Category E. Foreign bidders are required to provide valid registration certificate as evidence of proof of their registration with the relevant regulatory institutions equivalent to EIZ and NCC in their country of origin. However, Foreign bidders shall be required to register with EIZ and NCC after award of contract as required by the Laws of Zambia. Bidders are required to confirm their commitment to comply with this requirement. - Foreign bidders and local bidders are required to partner with citizen bidders. The terms Foreign. Citizen and Local bidder are defined in the Public Procurement Act No. 8 of 2020. Evidence of partners with a citizen bidder must be supported by the following (Foreign bidders are at liberty to provide any form of evidence of partnership with citizen bidders (Documentation may be in form of joint venture agreements, MOUs, sub-contracting, partnership agreements consented to by all parties, e.t.c): - Signed partnership agreement indicating all the parties; - There must be evidence and explanation of how skills will be transferred to the local companies and personnel in the partnership agreement. The absence of ANY of this information shall render the bid non-responsive. |
| ITB24.1 | The Employer will carry out a detailed evaluation of the bids previously determined to be substantially responsive in order to determine whether the technical aspects are in accordance with the requirements set forth in the bidding documents. In order to reach such a determination, the Employer will examine and compare the technical aspects of the bids on the basis of the information supplied by the bidders, taking into account the following factors: (a) overall completeness and compliance with the Technical Specifications and Drawings; deviations from the Technical Specifications as identified in Attachment 6 to the bid and those deviations not so identified; suitability of the facilities offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the bid. The bid that does not meet minimum acceptable standards of completeness, consistency and detail will be rejected. (b) achievement of specified performance criteria by the facilities (c) type, quantity and long-term availability of mandatory and recommended spare parts and maintenance services (d) any other relevant factors, if any, listed in the Bid Data Sheet, or that the Employer deems necessary or prudent to take into consideration. 24.2 Where alternative technical solutions have been permitted and offered to the bid, the Employer will make a similar evaluation of the alternatives, which will be treated in the technical and commercial evaluations as if they were base bids. Where alternatives are not permitted, but have in any event been offered, they shall be ignored. |
| ITB25.1 | COMMERCIAL EVALUATION The Employer’s evaluation of a bid will take into account, in addition to the bid prices indicated in Price Schedules, the following costs and factors that will be added to each Bidder’s bid price in the evaluation using pricing information available to the Employer, in the manner and to the extent indicated in ITB Sub-Clause 25.3 and in the Technical Specifications: (a) the cost of all quantifiable deviations and omissions from the contractual and commercial conditions and the Technical Specifications as identified in Attachment 6 to the bid, and other deviations and omissions not so identified (b) compliance with the time schedule to the form of Contract Agreement and evidenced as needed in a milestone schedule provided in the bid (c) the projected operating and maintenance costs during the life of the facilities (d)the functional guarantees of the facilities offered (e) the extra cost of work, services, facilities etc., required to be provided by the Employer or third parties. Pursuant to ITB, the following evaluation methods will be followed: (a)Contractual and commercial deviations The evaluation shall be based on the evaluated cost of fulfilling the contract in compliance with all commercial, contractual and technical obligations under this bidding document. In arriving at the evaluated cost, the price for withdrawal of deviations shown in Attachment 6 of the bid will be used, if necessary. If such a price is not given, the Employer will make its own assessment of the cost of such a deviation for the purpose of ensuring fair comparison of bids. (b)Time schedule (program of performance) The plant and equipment covered by this bidding are required to be shipped and installed, and the facilities shall have the pre-commissioning completed within the period named in the Bid Data Sheet after the effective date specified in the Contract Agreement. Bidders are required to base their prices on the time schedule given in Appendix 4 to the form of Contract Agreement (Time Schedule) or, where no time schedule is given, on the completion date(s) given in the Bid Data Sheet. No credit will be given for earlier completion. Where an Alternative Time Schedule is accepted, pursuant to ITB Sub-Clause 9.3 (g) (i), and where the completion date offered is within the limits specified in the Bid Data Sheet, bids offering a completion date beyond the minimum designated period shall be adjusted in the evaluation by adding a factor specified in the Bid Data Sheet to the bid price. Bids offering a completion date beyond the maximum designated period shall be rejected. (d)Functional Guarantees of the facilities (i)Bidders shall state the functional guarantees (e.g. performance, efficiency, consumption) of the proposed facilities in response to the Technical Specifications. Plant and equipment offered shall have a minimum (or a maximum, as the case may be) level of functional guarantees specified in the Technical Specifications to be considered responsive. Bids offering plant and equipment with functional guarantees less (or more) than the minimum (or maximum) specified shall be rejected. (ii) For the purposes of evaluation, the adjustment specified in the Bid Data Sheet will be added to the bid price for each drop (or excess) in the responsive functional guarantees offered by the Bidder, below (or above) either a norm of 100 or the value committed in the responsive bid with the most performing functional guarantees, as specified in the Bid Data Sheet. (e)Work, services, facilities etc., to be provided by the Employer Where bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the bidding documents, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the contract. Such costs shall be added to the bid price for evaluation. (f)Specific additional criteria The relevant evaluation method, if any, shall be detailed in the Bid Data Sheet and/or in the Technical Specifications. Any adjustments in price that result from the above procedures shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.” Bid prices quoted by Bidders shall remain unaltered. |
| ITB 25.4 | The adjustments shall be determined using the following criteria, from amongst those set out in Section III, Evaluation and Qualification Criteria: - Deviation in Delivery schedule: No - Deviation in payment schedule: No - the cost of major replacement components, mandatory spare parts, and service: No - the availability in Zambia of spare parts and after-sales services for the equipment offered in the bid No - the projected operating and maintenance costs during the life of the equipment Yes, Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given in the Bid Data Sheet, including the cost of spare parts for the initial period of operation stated in the Bid Data Sheet and based on prices furnished by each Bidder in Price Schedules Nos. 1 and 2, as well as on past experience of the Employer or other employers similarly placed. Such costs shall be added to the bid price for evaluation. The price of recommended spare parts quoted in Price Schedule No. 6 shall not be considered for evaluation. |
| ITB 26.1 | Foreign and local bidders are required to partner with citizen bidders as required in the Public Procurement Act No. 8 of 2020. |
| ITB 28 | The Successful bidder (s) will be subjected to Post Qualification using the qualification information below. |

Post Qualification Requirements

| Factor | # 2.1 Eligibility |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ##### Sub-Factor | ##### Criteria |  |  |  |  | ##### Documentation Required |
|  | ##### Requirement | ##### Bidder |  |  |  |  |
|  |  | Single Entity | ##### Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | ##### Each partner | At least one partner |  |
| - Nationality | Nationality in accordance with ITB 2.2. | Must meet requirement | Existing or intended JVCA must meet requirement | Must meet requirement | N / A | Form ELI –1.1 and 1.2, with attachments |
| - Power of Attorney | Bidders must submit a copy of power of attorney, duly notarized, indicating that the person(s) has (ve) the authority to sign in accordance with ITB9.3 (b). | Must meet requirement | Existing or intended JV must meet requirement | N/A | N/A | Bidders must submit a power of attorney, duly notarized (or equivalent), indicating that the person(s) has (ve) the authority to sign in accordance with ITB9.3 (a) |
| - Conflict of Interest | No- conflicts of interests as described in ITB 2.3. | Must meet requirement | Existing or intended JVCA must meet requirement | Must meet requirement | N / A | Letter of Bid |
| - ZPPA Ineligibility | Not having been declared ineligible by the ZPPA as described in ITB 2.4. | Must meet requirement | Existing JVCA must meet requirement | Must meet requirement | N / A | Letter of Bid |
| - Government Owned Entity | Compliance with conditions of ITB2.5 | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Form ELI –1.1 and 1.2, with attachments |
| - Ineligibility based on a United Nations resolution or Borrower’s country law | Not having been excluded as a result of the Borrower’s country laws or official regulations, or by an act of compliance with UN Security Council resolution, in accordance with ITB2.7 | Must meet requirement | Existing JVCA must meet requirement | Must meet requirement | N / A | Letter of Bid |

| Factor | # 2.2 Historical Contract Non-Performance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ##### Sub-Factor | ##### Criteria |  |  |  |  | Documentation Required |
|  | ##### Requirement | ##### Bidder |  |  |  |  |
|  |  | Single Entity | ##### Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| - History of non-performing contracts or poor quality workmanship | Non-performance of a contract or poor workmanship did not occur within the last Five (5) years prior to the deadline for bid submission, based on all information on fully settled disputes or litigation. | Must meet requirement by itself or as partner to past or existing JVCA | N / A | Must meet requirement by itself or as partner to past or existing JVCA | N / A | Completion of Form CON - 2 |
| - Failure to Sign Contract | Not being under execution of a Bid-Securing Declaration pursuant to ITB 2.6 for five years | Must meet requirement | N / A | Must meet requirement by itself or as part of a JVCA | N / A | Letter of Bid |
| - Pending Litigation | ### All pending litigation shall in total not represent more than forty per cent (40%) of the Bidder’s net worth and shall be treated as resolved against the Bidder. | Must meet requirement by itself or as partner to past or existing JVCA | N / A | Must meet requirement by itself or as partner to past or existing JVCA | N / A | Completion of Form CON – 2 and supported by a letter from an independent Law Firm. A statement by the bidder themselves shall not be accepted. |

| Factor | 2.3 Financial Situation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Bidder |  |  |  |  |
|  |  | Single Entity | Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| 2.3.1 Historical Financial Performance | Submission of audited financial statements or if not required by the law of the bidder’s country, other financial statements acceptable to the Employer, for the last Three [3] (2022 to 2020) years to demonstrate the current soundness of the bidders financial position and its prospective long term profitability. Liquidity Working Capital | Must meet requirement | N / A | Must meet requirement | N / A | Form FIN – 3.1 with attachments of financial statements |
| 2.3.2.Average Annual Turnover | Minimum average annual turnover of USD500 million, calculated as total certified payments received for contracts in progress or completed, within the last three (3) years | Must meet requirement | Must meet requirement | Must meet thirty percent (30%) of the requirement | Must meet sixty percent (60%) of the requirement | Form FIN –3.2 |
| 2.3.3.Financial Resources | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet: (i) the cash-flow requirement USD80 million and (ii) the overall cash flow requirements for this contract and its current commitments. | Must meet requirement | Must meet requirement | Must meet thirty percent (30%) of the requirement | Must meet seventy percent (70%) of the requirement | Form FIN –3.3 + Form CCC |

| Factor | # 2.4 Experience |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | ##### Criteria |  |  |  |  | ##### Documentation Required |
|  | Requirement | ##### Bidder |  |  |  |  |
|  |  | ##### Single Entity | Joint Venture, Consortium or Association |  |  |  |
|  |  |  | All partners combined | Each partner | At least one partner |  |
| ## 2.4.1General ## Experience | Experience under contracts in the role of contractor or subcontractor for at least the last five (5) years prior to the bid submission deadline, and with activity in at least nine (9) months in each year | Must meet requirement | N / A | N / A | Must meet requirement | Form EXP-2.4.1 |
| 2.4.2Specific Experience | ### (a)Participation as contractor or subcontractor, in at least three (3) contracts within the last ten (10) years, each with a value of at least USD150 million, that have been successfully and substantially completed and that are similar to the proposed Facilities. The similarity shall be based on the physical size, complexity, methods/technology in the following voltage classes: ### (i) 330kV substations or higher voltages ### (ii) 330kV lines or higher | Must meet requirement | Must meet requirements for all characteristics | N / A | Must meet requirement for one characteristic (e.g., can be a specialist subcontractor) | Form EXP 2.4.2(a) |
| ## 2.4.2 Specific Experience | b) For the above or other contracts executed during the period stipulated in 2.4.2 (a) above, a minimum experience in the following key activities: Civil and structural Installation of 330kV, 132kV, 33kV- and 11kV equipment Proof of minimum specific experience in key activities should be design, construction or management of civil works for 330/11kV 132kV/33kV and 330/132/11kV substations followed by names of at least three (3) of such substations over the past 5 years will suffice. | Must meet requirements | Must meet requirements | Must meet at least one requirement | Must meet the following requirements for the key activities listed below (e.g., can be a specialist subcontractor1. Civil works - Equipment commissioning. | Form EXP-2.4.2(b) |

2.5	Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements:

330kV and 132kV Transmission lines

| No. | Position | Total Work Experience (years) | Experience In Similar Work (years) |
| --- | --- | --- | --- |
| 1 | Project Manager | 15 | 8 |
| 2 | Civil Engineer | 10 | 8 |
| 3 | Transmission line Engineer | 10 | 5 |
| 4 | Distribution line Engineer | 10 | 5 |
| 5 | Lines Foreman | 10 | 5 |
| 6 | Linesman or fitter/rigger | 8 | 5 |

330/132kV substation works

| No. | Position | Total Work Experience (years) | Experience In Similar Work (years) |
| --- | --- | --- | --- |
| 1 | Project Manager | 15 | 8 |
| 2 | Substations Engineer | 10 | 5 |
| 3 | Telecoms Engineer | 10 | 5 |
| 4 | Protection/ SCADA Engineer | 10 | 5 |
| 5 | Metering Engineer | 10 | 5 |
| 6 | Civil Engineer | 10 | 5 |

The Bidder shall provide details of the proposed personnel and their experience records using Forms PER-1 and PER-2 included in Section IV, Bidding Forms.

2.6 Equipment

The Bidder must demonstrate that it owns or will have access to the key Contractor’s equipment listed hereafter:

330kV, 132kV lines

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 | Line construction tools | For fifteen (15) line gangs |
| 2 | Tensioner and Puller rated at least 8 tons | 3 Sets |
| 3 | Earth moving equipment: excavator, dozer etc. | 10 |
| 4 | 15 ton truck with on board crane | 8 |
| 5 | 50 ton mobile crane | 3 |

33kV, 11kV lines

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 | Line construction tools | For fifteen (15) line gangs |
| 2 | Tensioner and Puller rated at least 8 tons | 3 Sets |
| 3 | Earth moving equipment: excavator, dozer etc. | 10 |
| 4 | 15 ton truck with on board crane | 8 |
| 5 | 50 ton mobile crane | 3 |

330/132-88/33/11kV substation works

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 | Various assembly/erection tools | 3 sets |
| 2 | Oil treatment plant, min. 6000 L/hr | 3 sets |
| 3 | Vacuum pump | 3 sets |
| 4 | Modern test equipment for primary/secondary injection tests | 2/2 set |
| 5 | 15 ton truck with on board crane | 2 |
| 6 | 50 ton mobile crane | 2 |

The Bidder shall provide further details of proposed items of equipment using the Form EQU furnished in Section IV, Bidding Forms.

2.7 	Manufacturers/Subcontractors

Manufacturers/Subcontractors for the following major items of supply or installation services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 | HV Transformers | Minimum 20 years’ experience, ISO 9001 certification, must have manufactured and type tested transformers with rating above 100 MVA and same or higher voltage class as this project. Must clearly show design technical features of the tapped HV winding 330/11kV, 132/33/11kV two winding and 330/132/11kV three winding transformer and technical reasons there-of. |
| 2 | HV, MV and LV Circuit Breakers | Record of at least 20 years in manufacture and supply of HV circuit breakers in the voltage classes for this project. Records of type tests of designs by reputable test houses. ISO 9001 certification |
| 3 | Substation control system | Established manufacturer, at least 20 years’ supply experience in Substation Automation Systems. ISO 9001 certification |
| 4 | Protection relays | Established manufacturer, at least 20 years’ experience in supply of protection relays. ISO 9001 certification. All protection relays shall be IEC61850 compliant |

Failure to comply with this requirement will result in rejection of the subcontractor or manufacturer.

In the case of a Bidder who offers to supply and install major items of supply under the contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using the form provided in Section IV, Bidding Forms, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and 5, and meets the minimum criteria listed above for that item.

# Note: The Successful bidder (s) will be subjected to Post Qualification using the qualification information above.

Technical Proposal

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Plant

- Contractor’s Equipment

- Personnel

- Proposed Subcontractors for Major Items of Plant and Installation Services

- Others

Site Organization

Method Statement

Mobilization Schedule

Construction Schedule

Plant

Contractor’s Equipment

Form EQU

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key Contractor’s equipment listed in Section III, Evaluation and Qualification Criteria. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Form FUNC

The Bidder shall copy in the left column of the table below, the identification of each functional guarantee required in the Specification and stated by the Employer in para. 1.2 (c) of Section III. Evaluation and Qualification Criteria, and in the right column, provide the corresponding value for each functional guarantee of the proposed plant and equipment.

| Required Functional Guarantee | Value of Functional Guarantee of the Proposed Plant and Equipment |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

Personnel

Form PER -1

Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements stated in Section III. The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position* |
| --- | --- |
|  | Name |
| 2. | Title of position* |
|  | Name |
| 3. | Title of position* |
|  | Name |
| 4. | Title of position* |
|  | Name |

*As listed in Section III.

Form PER-2

Curriculum Vitae for Key personnel. This form is to be completed by all bidders. A separate form shall be used for each key personnel.

Resume of Proposed Personnel

Name of Bidder

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last 20 years, in reverse chronological order.  Indicate particular technical and managerial experience relevant to the Project.

| From | To | Company/Project/Position/Relevant technical and management experience |
| --- | --- | --- |

Proposed Subcontractors for Major Items of Plant and Installation Services

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are proposed for carrying out the item of the facilities indicated.  Bidders are free to propose more than one for each item

| Major Items of Plant and Installation Services | Proposed Subcontractors/Manufacturers | Nationality |
| --- | --- | --- |

## Equipment Capabilities

This form is to be completed by all bidders.  It should provide adequate information to demonstrate clearly that the bidder has the capability to meet the requirements for each and all items of equipment listed in the instructions to candidates.  A separate form shall be prepared for each item of equipment or for alternative equipment proposed by the bidder.

Name of equipment

| Item No. of equipment |  |
| --- | --- |
| Equipment information | 1. Name of manufacturer |
|  | 2. Model |
|  | 3. Year of manufacture |
|  | 4. Capacity |
| Current status | 5. Current location |
|  | 6. Details of current commitments |
| Source | 7. Indicate source of the equipment * Owned * Rented * Leased * Specially manufactured |

Omit the following information for equipment owned by the Bidder

| Owner | 8. Name 9. Address of owner Telephone Contact name and title Fax Email |
| --- | --- |
| Agreements | Details or rental/lease/manufacture agreements specific to the project |

Form ELI 1.1

Bidder Information Sheet

Date:  ______________________

ICB No.: ___________________

Invitation for Bid No.: ________

Page ________ of _______ pages

1. Bidder’s Legal Name

2. In case of JVA, legal name of each party:

3. Bidder’s actual or intended Country of Registration:

4. Bidder’s Year of Registration:

5. Bidder’s Legal Address in Country of Registration:

6. Bidder’s Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of: Articles of Incorporation or Registration of firm named in 1, above, in accordance with ITB Sub-Clauses 4.1 and 4.2. - In case of JVA, letter of intent to form JVA including a draft agreement, or JVA agreement, in accordance with ITB Sub-Clauses 4.1 and 11.1(i) Single Stage Bidding or 11.1(g) Two Stage Bidding. - In case of government owned entity from the Employer’s country, documents establishing legal and financial autonomy and compliance with the principles of commercial law, in accordance with ITB Sub-Clause 4.5.

Please note that a written authorization needs to be attached to this sheet as required by ITB 21.2 Single Stage Bidding) or ITB 17.2 Two Stage Bidding

Form ELI 1.2

Party to JVA Information Sheet

Date: ______________________

ICB No.: ___________________

Invitation for Bid No.:_________

Page ________ of_ ______ pages

1. Bidder’s Legal Name:

2. JVA’s Party legal name:

3. JVA’s Party Country of Registration:

4. JVA’s Party Year of Registration:

5. JVA’s Party Legal Address in Country of Registration:

6. JVA’s Party Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of: Articles of Incorporation or Registration of firm named in 1, above, in accordance with ITB Sub-Clauses 4.1 and 4.2. - In case of government owned entity from the Purchaser’s country, documents establishing legal and financial autonomy and compliance with the principles of commercial law, in accordance with ITB Sub-Clause 4.5.

Form CON – 2

Historical Contract Non-Performance

Bidder’s Legal Name:  _______________________     	Date:  _____________________

JVA Partner Legal Name:  _______________________	   ___________________

ICB No.:  __________________

Page _______ of _______ pages

| Non-Performing Contracts in accordance with Section III, Evaluation Criteria |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Contract non-performance did not occur during the stipulated period, in accordance with Sub- Factor 2.2.1 of Section III, Evaluation Criteria |  |  |  |  |  |
| Pending Litigation, in accordance with Section III, Evaluation Criteria |  |  |  |  |  |
| No pending litigation in accordance with Sub-Factor 2.2.2 of Section III, Evaluation Criteria Pending litigation in accordance with Sub-Factor 2.2.2 of Section III, Evaluation Criteria, as indicated below |  |  |  |  |  |
| Year | Outcome as Percent of Total Assets | Contract Identification |  | Total Contract Amount (current value, US$ equivalent) |  |
| ______ | ______ | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  | ___________ |  |
| ______ | ______ | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  | ___________ |  |

# Form 2.2 - Litigation History

This form is to be completed by all.  It should provide information on any history of litigation or arbitration resulting from contracts executed in the last five years or currently under execution.

Name of Bidder or partner

Bidders should provide information of any history of litigation or arbitration resulting from contracts executed in the last five years or currently under execution (Instructions to Bidders, para. 4.8).

| Year | Award FOR or AGAINST Bidder | Name of client, cause of litigation, and matter in dispute | Disputed amount (current value) |
| --- | --- | --- | --- |

The bidder should provide accurate information on any litigation or arbitration resulting from contracts completed or under its execution over the last five years.  A consistent history of awards against the bidder or any partner of a joint venture may result in failure of the application.

Form CCC

Current Contract Commitments / Works in Progress

Bidders and each partner to a JVA should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

| Name of contract | Employer, contact address/tel/fax | Value of outstanding work (current US$ equivalent) | Estimated completion date | Average monthly invoicing over last six months (US$/month) |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| etc. |  |  |  |  |

Form FIN – 3.1

Financial Situation

Historical Financial Performance

Bidder’s Legal Name: _______________________     	Date:  _____________________

JVA Partner Legal Name: _______________________ 	ICB No.:  __________________

Page _______ of _______ pages

To be completed by the Bidder and, if JVA, by each partner

| Financial information in US$ equivalent | Historic information for previous ______ (__) years (US$ equivalent in 000s) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year … | Year n | Avg. | Avg. Ratio |
| Information from Balance Sheet |  |  |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |  |  |

Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:

- Must reflect the financial situation of the Bidder or partner to a JVA, and not sister or parent companies

- Historic financial statements must be audited by a certified accountant

- Historic financial statements must be complete, including all notes to the financial statements

- Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

Attach latest copies of financial statements (balance sheets, including all related notes, and income statements) for the past three (03) years required above; and complying with the requirements.

Form FIN – 3.2

Average Annual Turnover of contracts of similar nature undertaken

Bidder’s Legal Name:  ___________________________     	Date:  _____________________

JVA Partner Legal Name: ____________________________ 	ICB No.:  __________________

Page _______ of _______ pages

| Annual turnover data (construction only) |  |  |
| --- | --- | --- |
| Year | Amount and Currency | US$ equivalent |
|  | _________________________________________ | ____________________ |
|  | _________________________________________ | ____________________ |
|  | _________________________________________ | ____________________ |
|  | _________________________________________ | ____________________ |
|  | _________________________________________ | ____________________ |
| *Average Annual Construction Turnover | _________________________________________ | ____________________ |

*Average annual turnover calculated as total certified payments received for work in progress or completed, divided by the number of years specified in Section III, Evaluation Criteria, Sub-Factor 2.3.2.

Form FIN 3.3

Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section III, Evaluation and Qualification Criteria

| Source of financing | Amount (US$ equivalent) |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

Form EXP 2.4.1

Experience - General Experience

Bidder’s Legal Name:  ____________________________     	Date:  _____________________

JVA Partner Legal Name:  ____________________________	ICB No.:  __________________

Page _______ of _______ pages

| Starting Month / Year | Ending Month / Year | Years* | Contract Identification | Role of Bidder |
| --- | --- | --- | --- | --- |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |
| ______ | ______ |  | Contract name: Brief Description of the Works performed by the Bidder: Name of Employer: Address: | _________ |

*List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year

Form EXP – 2.4.2(a)

Specific Experience

Bidder’s Legal Name:  ___________________________     	Date:  _____________________

JVA Partner Legal Name: _________________________	ICB No.:  __________________

Page _______ of _______ pages

| Similar Contract Number: ___ of ___ required. | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification | _______________________________________ |  |  |
| Award date Completion date | _______________________________________ _______________________________________ |  |  |
| Role in Contract | Contractor | Management Contractor | Subcontractor |
| Total contract amount | ____________________________ |  | US$__________ |
| If partner in a JVA or subcontractor, specify participation of total contract amount | __________% | _____________ | US$_______ |
| Employer’s Name: | _______________________________________ |  |  |
| Address: Telephone/fax number: E-mail: | _______________________________________ _______________________________________ _______________________________________ _______________________________________ |  |  |

Form EXP – 2.4.2(a) (cont.)

Specific Experience (cont.)

Bidder’s Legal Name:  ___________________________     	Page _______ of _______ pages

JVA Partner Legal Name:  ___________________________

| Similar Contract No. __[insert specific number] of [total number of contracts] ___ required | Information |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 2.4.2a) of Section III: |  |
| Amount | _________________________________ |
| Physical size | _________________________________ |
| Complexity | _________________________________ |
| Methods/Technology | _________________________________ |
| Physical Production Rate | _________________________________ |

Form EXP – 2.4.2(b)

Specific Experience in Key Activities

Bidder’s Legal Name:  ___________________________     	Date:  _____________________

JVA Partner Legal Name: _________________________	ICB No.:  __________________

Subcontractor’s Legal Name: ______________	Page _______ of _______ pages

|  | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification | _______________________________________ |  |  |
| Award date Completion date | _______________________________________ _______________________________________ |  |  |
| Role in Contract | Contractor | Management Contractor | Subcontractor |
| Total contract amount | _________________________ |  | US$________ |
| If partner in a JVA or subcontractor, specify participation of total contract amount | __________% | _____________ | US$________ |
| Employer’s Name: | _______________________________________ |  |  |
| Address: Telephone/fax number: E-mail: | _______________________________________ _______________________________________ _______________________________________ _______________________________________ |  |  |

Form EXP – 2.4.2 (b)(cont.)

Specific Experience in Key Activities (cont.)

Bidder’s Legal Name:  ___________________________     	Page _______ of _______ pages

JVA Partner Legal Name:  ___________________________

Subcontractor’s Legal Name: __________________________

|  | Information |
| --- | --- |
| Description of the key activities in accordance with Sub-Factor 2.4.2b) of Section III: |  |

Sales/Construction Experience in Key Activities

Bidder's Legal Name: [insert full name]
Date: [insert day, month, year]
Bidder's Party Legal Name: [insert full name]
Nominated Subcontractor's Legal Name: [insert full name]
ICB No. and title: [insert ICB number and title]

All Subcontractors for key activities must complete the information in this form as per Qualification Criteria and Requirements in the Solicitation Document.

1.	Key Activity No One: [insert brief description of the Activity, emphasizing its specificity]

|  | Information |  |  |
| --- | --- | --- | --- |
| Contract Identification | [insert contract name and number, if applicable] |  |  |
| Award date | [insert day, month, year, i. e., 15 June, 2015] |  |  |
| Completion date | [insert day, month, year, i.e., 03 October, 2017] |  |  |
| Role in Contract [check the appropriate box] | Contractor | Management Contractor | Subcontractor |
| Total Contract Amount | [insert total contract amount in local currency] |  | US$ [insert Total contract amount in US$ equivalent] |
| If party in a JV, specify participation of total contract amount | [insert a percentage amount | [insert total contract amount in local currency] | [insert total contract amount in US$ equivalent] |

|  | Information |
| --- | --- |
| Employer’s Name: | [insert full name] |
| Address: Telephone/fax number E-mail: | [indicate street / number / town or city / country] [insert telephone/fax numbers, including country and city area codes] [insert e-mail address, if available] |

2. Activity No Two

3. …………………

|  | Information |
| --- | --- |
| Description of the key activities in accordance with in the Solicitation Document. | [insert response to inquiry indicated in left column] |

## Bidder Form 7 – Source of Financing

This form is to be completed by all Bidders. It should provide adequate information to demonstrate clearly that the Bidder has the capability to source financing for the project.

Information on Successful Sourcing of Financing by the Bidders

Please provide information on sourcing of financing for similar projects in the last ten years, separately.

| Name of the Project |  |
| --- | --- |
| Contact Details of the client Name:………………………….. Designation:……………………. Telephone Number:……………. Email Address:………………… |  |
| Location and description of the project |  |
| Overall financing arrangement for the project |  |
| Details of the financing sourced by the Bidder |  |
| Source of financing |  |
| Date of Transaction |  |

Proposed Source of Financing for this Project

| Proposed Source of Financing |  |
| --- | --- |
| Proposed Amount |  |

Term Sheet

| Indicative Term Sheet for the Debt portion of the project financing | [ Please attach] |
| --- | --- |

# Section IV. General Conditions of Contract

## Notes on the General Conditions of Contract The General Conditions of Contract in Section IV, read in conjunction with the Special Conditions of Contract in Section V and other documents listed therein, should be a complete document expressing all the rights and obligations of the parties. The General Conditions of Contract herein shall not be altered. Any changes and complementary information that may be needed shall be introduced only through the Special Conditions of Contract in Section V.

## Table of Clauses

0HA. Contract and Interpretation	184H98

1H1.	Definitions	185H98

2H2.	Contract Documents	186H101

3H3.	Interpretation	187H101

4H4.	Notices	188H103

5H5.	Governing Law	189H104

6H6.	Settlement of Disputes	190H104

7HB. Subject Matter of Contract	191H105

8H7.	Scope of Facilities	192H105

9H8.	Time for Commencement and Completion	193H106

10H9.	Contractor’s Responsibilities	194H107

11H10.	Employer’s Responsibilities	195H108

12HC. Payment	196H109

13H11.	Contract Price	197H109

14H12.	Terms of Payment	198H109

15H13.	Securities	199H110

16H14.	Taxes and Duties	200H111

17HD. Intellectual Property	201H112

18H15.	Copyright	202H112

19H16.	Confidential Information	203H112

20HE.  Execution of the Facilities	204H113

21H17.	Representatives	205H113

22H18.	Work Program	206H115

23H19.	Subcontracting	207H117

24H20.	Design and Engineering	208H117

25H21.	Procurement	209H120

26H22.	Installation	210H121

27H23.	Test and Inspection	211H126

28H24.	Completion of the Facilities	212H128

29H25.	Commissioning and Operational Acceptance	213H130

30HF. Guarantees and Liabilities	214H132

31H26.	Completion Time Guarantee	215H132

32H27.	Defect Liability	216H133

33H28.	Functional Guarantees	217H135

34H29.	Patent Indemnity	218H136

35H30.	Limitation of Liability	219H137

36HG. Risk Distribution	220H137

37H31.	Transfer of Ownership	221H137

38H32.	Care of Facilities	222H138

39H33.	Loss of or Damage to Property; Accident or Injury to Workers; Indemnification	223H139

40H34.	Insurance	224H140

41H35.	Unforeseen Conditions	225H143

42H36.	Change in Laws and Regulations	226H144

43H37.	Force Majeure	227H145

44H38.	War Risks	228H146

45HH. Change in Contract Elements	229H148

46H39.	Change in the Facilities	230H148

47H40.	Extension of Time for Completion	231H152

48H41.	Suspension	232H153

49H42.	Termination	233H154

50H43.	Assignment	234H163

51H44.	Export Restriction	235H163

General Conditions of Contract

A. Contract and Interpretation

| 1. Definitions | 1.1 The following words and expressions shall have the meanings hereby assigned to them: (a) “Arbitrator” means the person or persons named as such in the SCC appointed by agreement between the Employer and the Contractor to make a decision on or to settle any dispute or difference between the Employer and the Contractor referred to him or her by the parties pursuant to GCC Sub-Clause 6.1 (Arbitrator) hereof. (b) “Commissioning” means operation of the Facilities or any part thereof by the Contractor following Completion, which operation is to be carried out by the Contractor as provided in GCC Sub-Clause 25.1 (Commissioning) hereof, for the purpose of carrying out Guarantee Test(s). (c) “Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the SCC) have been completed operationally and structurally and put in a tight and clean condition, and that all work in respect of Precommissioning of the Facilities or such specific part thereof has been completed; in other words, that the Facilities or specific part thereof are ready for Commissioning as provided in GCC Clause 24 (Completion) hereof. (d) “Contract” means the Contract Agreement entered into between the Employer and the Contractor, together with the Contract Documents referred to therein; they shall constitute the Contract, and the term “the Contract” shall in all such documents be construed accordingly. (e) “Contract Documents” means the documents listed in Article 1.1 (Contract Documents) of the Form of Contract Agreement (including any amendments thereto). (f) “Contract Price” means the sum specified in Article 2.1 (Contract Price) of the Contract Agreement, subject to such additions and adjustments thereto or deductions therefrom, as may be made pursuant to the Contract. (g) “Contractor” means the person(s) whose bid to perform the Contract has been accepted by the Employer and is named as such in the Contract Agreement and SCC, and includes the legal successors or permitted assigns of the Contractor. (h) “Contractor’s Equipment” means all plant, facilities, equipment, machinery, tools, apparatus, appliances or things of every kind required in or for installation, completion and maintenance of Facilities that are to be provided by the Contractor, but does not include Plant and Equipment, or other things intended to form or forming part of the Facilities. (i) “Contractor’s Representative” means any person nominated by the Contractor and named as such in the SCC and approved by the Employer in the manner provided in GCC Sub-Clause 17.2 (Contractor’s Representative and Construction Manager) hereof to perform the duties delegated by the Contractor. (j) “Country of Origin” means the countries and territories eligible under the rules of the Employer as further elaborated in the SCC. (k) “Day” means calendar day of the Gregorian Calendar. (l) “Defect Liability Period” means the period of validity of the warranties given by the Contractor commencing at Completion of the Facilities or a part thereof, during which the Contractor is responsible for defects with respect to the Facilities (or the relevant part thereof) as provided in GCC Clause 27 (Defect Liability) hereof. (m) “Effective Date” means the date of fulfillment of all conditions stated in Article 3 (Effective Date for Determining Time for Completion) of the Form of Contract Agreement, for the purpose of determining the Time for Completion. (n) “Employer” means the person named as such in the SCC and includes the legal successors or permitted assigns of the Employer. (o) “Facilities” means the Plant and Equipment to be supplied and installed, as well as all the Installation Services to be carried out by the Contractor under the Contract. (p) “GCC” means the General Conditions of Contract hereof. (q) “Guarantee Test(s)” means the test(s) specified in the Technical Specifications to be carried out to ascertain whether the Facilities or a specified part thereof is able to attain the Functional Guarantees specified in the Technical Specifications in accordance with the provisions of GCC Sub-Clause 25.2 (Guarantee Test) hereof. (r) “Installation Services” means all those services ancillary to the supply of the Plant and Equipment for the Facilities, to be provided by the Contractor under the Contract; e.g., transportation and provision of marine or other similar insurance, inspection, expediting, site preparation works (including the provision and use of Contractor’s Equipment and the supply of all construction materials required), installation, testing, precommissioning, commissioning, operations, maintenance, the provision of operations and maintenance manuals, training, etc. (s) “Month” means calendar month of the Gregorian Calendar. (t) “Operational Acceptance” means the acceptance by the Employer of the Facilities (or any part of the Facilities where the Contract provides for acceptance of the Facilities in parts), which certifies the Contractor’s fulfillment of the Contract in respect of Functional Guarantees of the Facilities (or the relevant part thereof) in accordance with the provisions of GCC Clause 28 (Functional Guarantees) hereof and shall include deemed acceptance in accordance with GCC Clause 25 (Commissioning and Operational Acceptance) hereof. (u) “Plant and Equipment” means permanent plant, equipment, machinery, apparatus, articles and things of all kinds to be provided and incorporated in the Facilities by the Contractor under the Contract (including the spare parts to be supplied by the Contractor under GCC Sub-Clause 7.3 hereof), but does not include Contractor’s Equipment. (v) “Precommissioning” means the testing, checking and other requirements specified in the Technical Specifications that are to be carried out by the Contractor in preparation for Commissioning as provided in GCC Clause 24 (Completion) hereof. (w) “Project Manager” means the person appointed by the Employer in the manner provided in GCC Sub-Clause 17.1 (Project Manager) hereof and named as such in the SCC to perform the duties delegated by the Employer. (x) “SCC” means the Special Conditions of Contract. (y) “Site” means the land and other places upon which the Facilities are to be installed, and such other land or places as may be specified in the Contract as forming part of the Site. (z) “Subcontractor,” including vendors, means any person to whom execution of any part of the Facilities, including preparation of any design or supply of any Plant and Equipment, is sub-contracted directly or indirectly by the Contractor, and includes its legal successors or permitted assigns. (aa) “Time for Completion” means the time within which Completion of the Facilities as a whole (or of a part of the Facilities where a separate Time for Completion of such part has been prescribed) is to be attained in accordance with the specifications in the SCC and the relevant provisions of the Contract. (bb) “ZPPA” refers to the Zambia Public Procurement Authority. |
| --- | --- |
| 2. Contract Documents | 2.1 Subject to Article 1.2 (Order of Precedence) of the Contract Agreement, all documents forming part of the Contract (and all parts thereof) are intended to be correlative, complementary and mutually explanatory. The Contract shall be read as a whole. |
| 3. Interpretation | 3.1 Language 3.1.1 The ruling language of the Contract shall be specified in the SCC. 3.1.2 The language for communications shall be that stated in the SCC. If no language is ststed there, the language for communications shall be the ruling language of the Contract. 3.2 Singular and Plural The singular shall include the plural and the plural the singular, except where the context otherwise requires. 3.3 Headings The headings and marginal notes in the General Conditions of Contract are included for ease of reference, and shall neither constitute a part of the Contract nor affect its interpretation. 3.4 Persons Words importing persons or parties shall include firms, corporations and government entities. 3.5 Incoterms Unless inconsistent with any provision of the Contract, the meaning of any trade term and the rights and obligations of parties thereunder shall be as prescribed by Incoterms. Incoterms means international rules for interpreting trade terms published by the International Chamber of Commerce (latest edition), 38 Cours Albert 1er, 75008 Paris, France. 3.6 Entire Agreement Subject to GCC Sub-Clause 16.4 hereof, the Contract constitutes the entire agreement between the Employer and Contractor with respect to the subject matter of Contract and supersedes all communications, negotiations and agreements (whether written or oral) of parties with respect thereto made prior to the date of Contract. 3.7 Amendment No amendment or other variation of the Contract shall be effective unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each party hereto. 3.8 Independent Contractor The Contractor shall be an independent contractor performing the Contract. The Contract does not create any agency, partnership, joint venture or other joint relationship between the parties hereto. Subject to the provisions of the Contract, the Contractor shall be solely responsible for the manner in which the Contract is performed. All employees, representatives or Subcontractors engaged by the Contractor in connection with the performance of the Contract shall be under the complete control of the Contractor and shall not be deemed to be employees of the Employer, and nothing contained in the Contract or in any subcontract awarded by the Contractor shall be construed to create any contractual relationship between any such employees, representatives or Subcontractors and the Employer. 3.9 Joint Venture If the Contractor is a joint venture of two or more persons, all such firms shall be jointly and severally bound to the Employer for the fulfillment of the provisions of the Contract and shall designate one of such persons to act as a leader with authority to bind the joint venture . The composition or the constitution of the joint venture shall not be altered without the prior consent of the Employer. 3.10 Non-Waiver 3.10.1 Subject to GCC Sub-Clause 3.10.2 below, no relaxation, forbearance, delay or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect or restrict the rights of that party under the Contract, nor shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract. 3.10.2 Any waiver of a party’s rights, powers or remedies under the Contract must be in writing, must be dated and signed by an authorized representative of the party granting such waiver, and must specify the right and the extent to which it is being waived. 3.11 Severability If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract. 3.12 Country of Origin “Origin” means the place where the materials, equipment and other supplies for the Facilities are mined, grown, produced or manufactured, and from which the services are provided. |
| 4. Notices | 4.1 Unless otherwise stated in the Contract, all notices to be given under the Contract shall be in writing, and shall be sent by personal delivery, airmail post, special courier, cable, telegraph, telex, facsimile or Electronic Data Interchange (EDI) to the address of the relevant party set out in the SCC, with the following provisions: 4.1.1 Any notice sent by cable, telegraph, telex, facsimile or EDI shall be confirmed within two (2) days after dispatch by notice sent by airmail post or special courier, except as otherwise specified in the Contract. 4.1.2 Any notice sent by airmail post or special courier shall be deemed (in the absence of evidence of earlier receipt) to have been delivered ten (10) days after dispatch. In proving the fact of dispatch, it shall be sufficient to show that the envelope containing such notice was properly addressed, stamped and conveyed to the postal authorities or courier service for transmission by airmail or special courier. 4.1.3 Any notice delivered personally or sent by cable, telegraph, telex, facsimile or EDI shall be deemed to have been delivered on date of its dispatch. 4.1.4 Either party may change its postal, cable, telex, facsimile or EDI address or addressee for receipt of such notices by ten (10) days’ notice to the other party in writing. 4.2 Notices shall be deemed to include any approvals, consents, instructions, orders and certificates to be given under the Contract. |
| 5. Governing Law | 5.1 The Contract shall be governed by and interpreted in accordance with laws of the country specified in the SCC. |
| 6. Settlement of Disputes | 6.1 Arbitrator 6.1.1 If any dispute of any kind whatsoever shall arise between the Employer and the Contractor in connection with or arising out of the Contract, including without prejudice to the generality of the foregoing, any question regarding its existence, validity or termination, or the execution of the Facilities—whether during the progress of the Facilities or after their completion and whether before or after the termination, abandonment or breach of the Contract—the parties shall seek to resolve any such dispute or difference by mutual consultation. If the parties fail to resolve such a dispute or difference by mutual consultation, then the dispute shall be referred in writing by either party to the Arbitrator, with a copy to the other party. 6.1.2 The Arbitrator shall give its decision in writing to both parties within twenty-eight (28) days of a dispute being referred to it. If the Arbitrator has done so, and no notice of intention to commence arbitration has been given by either the Employer or the Contractor within fifty-six (56) days of such reference, the decision shall become final and binding upon the Employer and the Contractor. Any decision that has become final and binding shall be implemented by the parties forthwith. 6.1.3 The Arbitrator shall be paid an hourly fee at the rate specified in the SCC plus reasonable expenditures incurred in the execution of its duties as Arbitrator, and these costs shall be divided equally between the Employer and the Contractor. 6.1.4 Should the Arbitrator resign or die, or should the Employer and the Contractor agree that the Arbitrator is not fulfilling its functions in accordance with the provisions of the Contract, a new Arbitrator shall be jointly appointed by the Employer and the Contractor. Failing agreement between the two within twenty-eight (28) days, the new Arbitrator shall be appointed at the request of either party by the Appointing Authority specified in the SCC. 6.2 Arbitration 6.2.1 If either the Employer or the Contractor is dissatisfied with the Arbitrator’s decision, or if the Arbitrator fails to give a decision within twenty-eight (28) days of a dispute being referred to it, then either the Employer or the Contractor may, within fifty-six (56) days of such reference, give notice to the other party, with a copy for information to the Arbitrator, of its intention to commence arbitration, as hereinafter provided, as to the matter in dispute, and no arbitration in respect of this matter may be commenced unless such notice is given. 6.2.2 Any dispute in respect of which a notice of intention to commence arbitration has been given, in accordance with GCC Sub-Clause 6.2.1, shall be finally settled by arbitration. Arbitration may be commenced prior to or after completion of the Facilities. 6.2.3 Arbitration proceedings shall be conducted in accordance with the rules of procedure designated in the SCC. 6.3 Notwithstanding any reference to the Arbitrator or arbitration herein, (a) the parties shall continue to perform their respective obligations under the Contract unless they otherwise agree (b) the Employer shall pay the Contractor any monies due the Contractor. |

B. Subject Matter of Contract

| 7. Scope of Facilities | 7.1 Unless otherwise expressly limited in the Technical Specifications, the Contractor’s obligations cover the provision of all Plant and Equipment and the performance of all Installation Services required for the design, the manufacture (including procurement, quality assurance, construction, installation, associated civil works, Precommissioning and delivery) of the Plant and Equipment and the installation, completion and commissioning of the Facilities in accordance with the plans, procedures, specifications, drawings, codes and any other documents as specified in the Technical Specifications. Such specifications include, but are not limited to, the provision of supervision and engineering services; the supply of labor, materials, equipment, spare parts (as specified in GCC Sub-Clause 7.3 below) and accessories; Contractor’s Equipment; construction utilities and supplies; temporary materials, structures and facilities; transportation (including, without limitation, unloading and hauling to, from and at the Site); and storage, except for those supplies, works and services that will be provided or performed by the Employer, as set forth in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. 7.2 The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract. 7.3 In addition to the supply of Mandatory Spare Parts included in the Contract, the Contractor agrees to supply spare parts required for the operation and maintenance of the Facilities for the period specified in the SCC. However, the identity, specifications and quantities of such spare parts and the terms and conditions relating to the supply thereof are to be agreed between the Employer and the Contractor, and the price of such spare parts shall be that given in Price Schedule No. 6, which shall be added to the Contract Price. The price of such spare parts shall include the purchase price therefor and other costs and expenses (including the Contractor’s fees) relating to the supply of spare parts. |
| --- | --- |
| 8. Time for Commencement and Completion | 8.1 The Contractor shall commence work on the Facilities within the period specified in the SCC and without prejudice to GCC Sub-Clause 26.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix (Time Schedule) to the Contract Agreement. 8.2 The Contractor shall attain Completion of the Facilities (or of a part where a separate time for Completion of such part is specified in the Contract) within the time stated in the SCC or within such extended time to which the Contractor shall be entitled under GCC Clause 40 hereof. |
| 9. Contractor’s Responsibilities | 9.1 The Contractor shall design, manufacture (including associated purchases and/or subcontracting), install and complete the Facilities with due care and diligence in accordance with the Contract. 9.2 The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Facilities (including any data as to boring tests) provided by the Employer, and on the basis of information that the Contractor could have obtained from a visual inspection of the Site (if access thereto was available) and of other data readily available to it relating to the Facilities as of the date twenty-eight (28) days prior to bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities. 9.3 The Contractor shall acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located that are necessary for the performance of the Contract, including, without limitation, visas for the Contractor’s and Subcontractor’s personnel and entry permits for all imported Contractor’s Equipment. The Contractor shall acquire all other permits, approvals and/or licenses that are not the responsibility of the Employer under GCC Sub-Clause 10.3 hereof and that are necessary for the performance of the Contract. 9.4 The Contractor shall comply with all laws in force in the country where the Facilities are installed and where the Installation Services are carried out. The laws will include all local, state, national or other laws that affect the performance of the Contract and bind upon the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such laws by the Contractor or its personnel, including the Subcontractors and their personnel, but without prejudice to GCC Sub-Clause 10.1 hereof. 9.5 Any Plant, Material and Services that will be incorporated in or be required for the Facilities and other supplies shall have their origin as specified under GCC Clause 1 (Country of Origin). 9.6 The Contractor shall permit the Employer to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by auditors appointed by the Employer, if so required by the Employer. |
| 10. Employer’s Responsibilities | 10.1 The Employer shall ensure the accuracy of all information and/or data to be supplied by the Employer as described in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract, except when otherwise expressly stated in the Contract. 10.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix. 10.3 The Employer shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located. Such authorities or undertakings require the Employer to obtain them in the Employer’s name, are necessary for the execution of the Contract (they include those required for the performance by both the Contractor and the Employer of their respective obligations under the Contract), and are specified in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. 10.4 If requested by the Contractor, the Employer shall use its best endeavors to assist the Contractor in obtaining in a timely and expeditious manner all permits, approvals and/or licenses necessary for the execution of the Contract from all local, state or national government authorities or public service undertakings that such authorities or undertakings require the Contractor or Subcontractors or the personnel of the Contractor or Subcontractors, as the case may be, to obtain. 10.5 Unless otherwise specified in the Contract or agreed upon by the Employer and the Contractor, the Employer shall provide sufficient, properly qualified operating and maintenance personnel; shall supply and make available all raw materials, utilities, lubricants, chemicals, catalysts, other materials and facilities; and shall perform all work and services of whatsoever nature, including those required by the Contractor to properly carry out Precommissioning, Commissioning and Guarantee Tests, all in accordance with the provisions of the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement at or before the time specified in the program furnished by the Contractor under GCC Sub-Clause 18.2 hereof and in the manner thereupon specified or as otherwise agreed upon by the Employer and the Contractor. 10.6 The Employer shall be responsible for the continued operation of the Facilities after Completion, in accordance with GCC Sub-Clause 24.8, and shall be responsible for facilitating the Guarantee Test(s) for the Facilities, in accordance with GCC Sub-Clause 25.2. 10.7 All costs and expenses involved in the performance of the obligations under this GCC Clause 10 shall be the responsibility of the Employer, save those to be incurred by the Contractor with respect to the performance of Guarantee Tests, in accordance with GCC Sub-Clause 25.2. |

C. Payment

| 11. Contract Price | 11.1 The Contract Price shall be as specified in Article 2 (Contract Price and Terms of Payment) of the Form of Contract Agreement. 11.2 Unless indicated otherwise in the SCC, the Contract Price shall be a firm lump sum not subject to any alteration, except in the event of a Change in the Facilities or as otherwise provided in the Contract. 11.3 Subject to GCC Sub-Clauses 9.2, 10.1 and 35 hereof, the Contractor shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract. |
| --- | --- |
| 12. Terms of Payment | 12.1 The Contract Price shall be paid as specified in the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement. The procedures to be followed in making application for and processing payments shall be those outlined in the same Appendix. 12.2 No payment made by the Employer herein shall be deemed to constitute acceptance by the Employer of the Facilities or any part(s) thereof. 12.3 In the event that the Employer fails to make any payment by its respective due date or within the period set forth in the Contract, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate(s) shown in the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement for the period of delay until payment has been made in full, whether before or after judgment or arbitrage award. 12.4 The currency or currencies in which payments are made to the Contractor under this Contract shall be specified in the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement, subject to the general principle that payments will be made in the currency or currencies in which the Contract Price has been stated in the Contractor’s bid. 12.5 All payments shall be made in the currency or currencies specified in the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement, pursuant to GCC 12.4. |
| 13. Securities | 13.1 Issuance of Securities The Contractor shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner and form specified below. 13.2 Advance Payment Security 13.2.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to the advance payment calculated in accordance with the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency or currencies. 13.2.2 The security shall be in the form provided in the bidding documents or in another form acceptable to the Employer. The amount of the security shall be reduced in proportion to the value of the Facilities executed by and paid to the Contractor from time to time, and shall automatically become null and void when the full amount of the advance payment has been recovered by the Employer. The security shall be returned to the Contractor immediately after its expiration. 13.3 Performance Security 13.3.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security for the due performance of the Contract in the amount specified in the SCC. 13.3.2 The security shall be denominated in the currency or currencies of the Contract, or in a freely convertible currency acceptable to the Employer, and shall be in one of the forms of bank guarantees provided in the bidding documents, as stipulated by the Employer in the SCC, or in another form acceptable to the Employer. 13.3.3 The security shall automatically be reduced by half on the date of the Operational Acceptance and shall become null and void, eighteen (18) months after Completion of the Facilities or twelve (12) months after Operational Acceptance of the Facilities, whichever occurs first; provided, however, that if the Defects Liability Period has been extended on any part of the Facilities pursuant to GCC Sub-Clause 27.8 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor, pursuant to GCC Sub-Clause 27.10, is liable for an extended warranty obligation, the performance security shall be extended for the period and up to the amount specified in the SCC. |
| 14. Taxes and Duties | 14.1 Except as otherwise specifically provided in the Contract, the Contractor shall bear and pay all taxes, duties, levies and charges assessed on the Contractor, its Subcontractors or their employees by all municipal, state or national government authorities in connection with the Facilities in and outside of the country where the Site is located. 14.2 Notwithstanding GCC Sub-Clause 14.1 above, the Employer shall bear and promptly pay (a) all customs and import duties for the Plant and Equipment specified in Price Schedule No. 1; and (b)other domestic taxes such as , sales tax and value added tax (VAT) on the Plant and Equipment specified in Price Schedules No.1 & 2 and that are to be incorporated into the Facilities, and on the finished goods, imposed by the law of the country where the Site is located . 14.3 If any tax exemptions, reductions, allowances or privileges may be available to the Contractor in the country where the Site is located, the Employer shall use its best endeavors to enable the Contractor to benefit from any such tax savings to the maximum allowable extent. 14.4 For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2 (Contract Price and Terms of Payment) of the Form of Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date twenty-eight (28) days prior to the date of bid submission in the country where the Site is located (hereinafter called “Tax” in this GCC Sub-Clause 14.4). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation or application of any Tax occurs in the course of the performance of Contract, which was or will be assessed on the Contractor, Subcontractors or their employees in connection with performance of the Contract, an equitable adjustment of the Contract Price shall be made to fully take into account any such change by addition to the Contract Price or deduction therefrom, as the case may be, in accordance with GCC Clause 36 hereof. |

D. Intellectual Property

| 15. Copyright | 15.1 The copyright in all drawings, documents and other materials containing data and information furnished to the Employer by the Contractor herein shall remain vested in the Contractor or, if they are furnished to the Employer directly or through the Contractor by any third party, including suppliers of materials, the copyright in such materials shall remain vested in such third party. |
| --- | --- |
| 16. Confidential Information | 16.1 The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor under this GCC Clause 16. 16.2 The Employer shall not use such documents, data and other information received from the Contractor for any purpose other than the operation and maintenance of the Facilities. Similarly, the Contractor shall not use such documents, data and other information received from the Employer for any purpose other than the design, procurement of Plant and Equipment, construction or such other work and services as are required for the performance of the Contract. 16.3 The obligation of a party under GCC Sub-Clauses 16.1 and 16.2 above, however, shall not apply to that information which (a) now or hereafter enters the public domain through no fault of that party (b) can be proven to have been possessed by that party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other party hereto (c) otherwise lawfully becomes available to that party from a third party that has no obligation of confidentiality. 16.4 The above provisions of this GCC Clause 16 shall not in any way modify any undertaking of confidentiality given by either of the parties hereto prior to the date of the Contract in respect of the Facilities or any part thereof. 16.5 The provisions of this GCC Clause 16 shall survive termination, for whatever reason, of the Contract. |

E.  Execution of the Facilities

| 17. Representatives | 17.1 Project ManagerIf the Project Manager is not named in the Contract, then within fourteen (14) days of the Effective Date, the Employer shall appoint and notify the Contractor in writing of the name of the Project Manager. The Employer may from time to time appoint some other person as the Project Manager in place of the person previously so appointed, and shall give a notice of the name of such other person to the Contractor without delay. No such appointment shall be made at such a time or in such a manner as to impede the progress of work on the Facilities. Such appointment shall only take effect upon receipt of such notice by the Contractor. The Project Manager shall represent and act for the Employer at all times during the currency of the Contract. All notices, instructions, orders, certificates, approvals and all other communications under the Contract shall be given by the Project Manager, except as herein otherwise provided. All notices, instructions, information and other communications given by the Contractor to the Employer under the Contract shall be given to the Project Manager, except as herein otherwise provided. 17.2 Contractor’s Representative & Construction Manager 17.2.1 If the Contractor’s Representative is not named in the Contract, then within fourteen (14) days of the Effective Date, the Contractor shall appoint the Contractor’s Representative and shall request the Employer in writing to approve the person so appointed. If the Employer makes no objection to the appointment within fourteen (14) days, the Contractor’s Representative shall be deemed to have been approved. If the Employer objects to the appointment within fourteen (14) days giving the reason therefor, then the Contractor shall appoint a replacement within fourteen (14) days of such objection, and the foregoing provisions of this GCC Sub-Clause 17.2.1 shall apply thereto. 17.2.2 The Contractor’s Representative shall represent and act for the Contractor at all times during the currency of the Contract and shall give to the Project Manager all the Contractor’s notices, instructions, information and all other communications under the Contract.All notices, instructions, information and all other communications given by the Employer or the Project Manager to the Contractor under the Contract shall be given to the Contractor’s Representative or, in its absence, its deputy, except as herein otherwise provided.The Contractor shall not revoke the appointment of the Contractor’s Representative without the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, the Contractor shall appoint some other person as the Contractor’s Representative, pursuant to the procedure set out in GCC Sub-Clause 17.2.1. 17.2.3 The Contractor’s Representative may, subject to the approval of the Employer (which shall not be unreasonably withheld), at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Contractor’s Representative, and shall specify the powers, functions and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Employer and the Project Manager.Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GCC Sub-Clause 17.2.3 shall be deemed to be an act or exercise by the Contractor’s Representative. 17.2.4 From the commencement of installation of the Facilities at the Site until Completion, the Contractor’s Representative shall appoint a suitable person as the construction manager (hereinafter referred to as “the Construction Manager”). The Construction Manager shall supervise all work done at the Site by the Contractor and shall be present at the Site throughout normal working hours except when on leave, sick or absent for reasons connected with the proper performance of the Contract. Whenever the Construction Manager is absent from the Site, a suitable person shall be appointed to act as his or her deputy. 17.2.5 The Employer may by notice to the Contractor object to any representative or person employed by the Contractor in the execution of the Contract who, in the reasonable opinion of the Employer, may behave inappropriately, may be incompetent or negligent, or may commit a serious breach of the Site regulations provided under GCC Sub-Clause 22.3. The Employer shall provide evidence of the same, whereupon the Contractor shall remove such person from the Facilities. 17.2.6 If any representative or person employed by the Contractor is removed in accordance with GCC Sub-Clause 17.2.5, the Contractor shall, where required, promptly appoint a replacement. |
| --- | --- |
| 18. Work Program | 18.1 Contractor’s Organization The Contractor shall supply to the Employer and the Project Manager a chart showing the proposed organization to be established by the Contractor for carrying out work on the Facilities. The chart shall include the identities of the key personnel together with the curricula vitae of such key personnel to be employed within twenty-one (21) days of the Effective Date. The Contractor shall promptly inform the Employer and the Project Manager in writing of any revision or alteration of such an organization chart. 18.2 Program of Performance Within twenty-eight (28) days after the date of signing the Contract Agreement, the Contractor shall prepare and submit to the Project Manager a detailed program of performance of the Contract, made in the form specified in the SCC and showing the sequence in which it proposes to design, manufacture, transport, assemble, install and precommission the Facilities, as well as the date by which the Contractor reasonably requires that the Employer shall have fulfilled its obligations under the Contract so as to enable the Contractor to execute the Contract in accordance with the program and to achieve Completion, Commissioning and Acceptance of the Facilities in accordance with the Contract. The program so submitted by the Contractor shall accord with the Time Schedule included in the corresponding Appendix (Time Schedule) to the Contract Agreement and any other dates and periods specified in the Contract. The Contractor shall update and revise the program as and when appropriate or when required by the Project Manager, but without modification in the Times for Completion given in the SCC and any extension granted in accordance with GCC Clause 40, and shall submit all such revisions to the Project Manager. 18.3 Progress Report The Contractor shall monitor progress of all the activities specified in the program referred to in GCC Sub-Clause 18.2 above, and supply a progress report to the Project Manager every month. The progress report shall be in a form acceptable to the Project Manager and shall indicate: (a) percentage completion achieved compared with the planned percentage completion for each activity; and (b) where any activity is behind the program, giving comments and likely consequences and stating the corrective action being taken. 18.4 Progress of Performance If at any time the Contractor’s actual progress falls behind the program referred to in GCC Sub-Clause 18.2, or it becomes apparent that it will so fall behind, the Contractor shall, at the request of the Employer or the Project Manager, prepare and submit to the Project Manager a revised program, taking into account the prevailing circumstances, and shall notify the Project Manager of the steps being taken to expedite progress so as to attain Completion of the Facilities within the Time for Completion under GCC Sub-Clause 8.2, any extension thereof entitled under GCC Sub-Clause 40.1, or any extended period as may otherwise be agreed upon between the Employer and the Contractor. 18.5 Work Procedures The Contract shall be executed in accordance with the Contract Documents and the procedures given in the section on Sample Forms and Procedures of the Contract Documents. The Contractor may execute the Contract in accordance with its own standard project execution plans and procedures to the extent that they do not conflict with the provisions contained in the Contract. |
| 19. Subcontracting | 19.1 The corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement specifies major items of supply or services and a list of approved Subcontractors against each item, including vendors. Insofar as no Subcontractors are listed against any such item, the Contractor shall prepare a list of Subcontractors for such item for inclusion in such list. The Contractor may from time to time propose any addition to or deletion from any such list. The Contractor shall submit any such list or any modification thereto to the Employer for its approval in sufficient time so as not to impede the progress of work on the Facilities. Such approval by the Employer for any of the Subcontractors shall not relieve the Contractor from any of its obligations, duties or responsibilities under the Contract. 19.2 The Contractor shall select and employ its Subcontractors for such major items from those listed in the lists referred to in GCC Sub-Clause 19.1. 19.3 For items or parts of the Facilities not specified in the corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement, the Contractor may employ such Subcontractors as it may select, at its discretion. |
| 20. Design and Engineering | 20.1 Specifications and Drawings 20.1.1 The Contractor shall execute the basic and detailed design and the engineering work in compliance with the provisions of the Contract, or where not so specified, in accordance with good engineering practice. The Contractor shall be responsible for any discrepancies, errors or omissions in the specifications, drawings and other technical documents that it has prepared, whether such specifications, drawings and other documents have been approved by the Project Manager or not, provided that such discrepancies, errors or omissions are not because of inaccurate information furnished in writing to the Contractor by or on behalf of the Employer. 20.1.2 The Contractor shall be entitled to disclaim responsibility for any design, data, drawing, specification or other document, or any modification thereof provided or designated by or on behalf of the Employer, by giving a notice of such disclaimer to the Project Manager. 20.2 Codes and Standards Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied after approval by the Employer and shall be treated in accordance with GCC Clause 39. 20.3 Approval/Review of Technical Documents by Project Manager 20.3.1 The Contractor shall prepare (or cause its Subcontractors to prepare) and furnish to the Project Manager the documents listed in the corresponding Appendix (List of Documents for Approval or Review) to the Contract Agreement for its approval or review as specified and in accordance with the requirements of GCC Sub-Clause 18.2 (Program of Performance).Any part of the Facilities covered by or related to the documents to be approved by the Project Manager shall be executed only after the Project Manager’s approval thereof.GCC Sub-Clauses 20.3.2 through 20.3.7 shall apply to those documents requiring the Project Manager’s approval, but not to those furnished to the Project Manager for its review only. 20.3.2 Within fourteen (14) days after receipt by the Project Manager of any document requiring the Project Manager’s approval in accordance with GCC Sub-Clause 20.3.1, the Project Manager shall either return one copy thereof to the Contractor with its approval endorsed thereon or shall notify the Contractor in writing of its disapproval thereof and the reasons therefor and the modifications that the Project Manager proposes. If the Project Manager fails to take such action within the said fourteen (14) days, then the said document shall be deemed to have been approved by the Project Manager. 20.3.3 The Project Manager shall not disapprove any document, except on the grounds that the document does not comply with some specified provision of the Contract or that it is contrary to good engineering practice. 20.3.4 If the Project Manager disapproves the document, the Contractor shall modify the document and resubmit it for the Project Manager’s approval in accordance with GCC Sub-Clause 20.3.2. If the Project Manager approves the document subject to modification(s), the Contractor shall make the required modification(s), whereupon the document shall be deemed to have been approved. 20.3.5 If any dispute or difference occurs between the Employer and the Contractor in connection with or arising out of the disapproval by the Project Manager of any document and/or any modification(s) thereto that cannot be settled between the parties within a reasonable period, then such dispute or difference may be referred to an Arbitrator for determination in accordance with GCC Sub-Clause 6.1 hereof. If such dispute or difference is referred to an Arbitrator, the Project Manager shall give instructions as to whether and if so, how, performance of the Contract is to proceed. The Contractor shall proceed with the Contract in accordance with the Project Manager’s instructions, provided that if the Arbitrator upholds the Contractor’s view on the dispute and if the Employer has not given notice under GCC Sub-Clause 6.1.2 hereof, then the Contractor shall be reimbursed by the Employer for any additional costs incurred by reason of such instructions and shall be relieved of such responsibility or liability in connection with the dispute and the execution of the instructions as the Arbitrator shall decide, and the Time for Completion shall be extended accordingly. 20.3.6 The Project Manager’s approval, with or without modification of the document furnished by the Contractor, shall not relieve the Contractor of any responsibility or liability imposed upon it by any provisions of the Contract except to the extent that any subsequent failure results from modifications required by the Project Manager. 20.3.7 The Contractor shall not depart from any approved document unless the Contractor has first submitted to the Project Manager an amended document and obtained the Project Manager’s approval thereof, pursuant to the provisions of this GCC Sub-Clause 20.3.If the Project Manager requests any change in any already approved document and/or in any document based thereon, the provisions of GCC Clause 39 shall apply to such request. |
| 21. Procurement | 21.1 Plant and Equipment Subject to GCC Sub-Clause 14.2, the Contractor shall manufacture or procure and transport all the Plant and Equipment in an expeditious and orderly manner to the Site. 21.2 Employer-Supplied Plant, Equipment, and Materials If the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement provides that the Employer shall furnish any specific items of machinery, equipment or materials to the Contractor, the following provisions shall apply: 21.2.1 The Employer shall, at its own risk and expense, transport each item to the place on or near the Site as agreed upon by the parties and make such item available to the Contractor at the time specified in the program furnished by the Contractor, pursuant to GCC Sub-Clause 18.2, unless otherwise mutually agreed. 21.2.2 Upon receipt of such item, the Contractor shall inspect the same visually and notify the Project Manager of any detected shortage, defect or default. The Employer shall immediately remedy any shortage, defect or default, or the Contractor shall, if practicable and possible, at the request of the Employer, remedy such shortage, defect or default at the Employer’s cost and expense. After inspection, such item shall fall under the care, custody and control of the Contractor. The provision of this GCC Sub-Clause 21.2.2 shall apply to any item supplied to remedy any such shortage or default or to substitute for any defective item, or shall apply to defective items that have been repaired. 21.2.3 The foregoing responsibilities of the Contractor and its obligations of care, custody and control shall not relieve the Employer of liability for any undetected shortage, defect or default, nor place the Contractor under any liability for any such shortage, defect or default whether under GCC Clause 27 or under any other provision of Contract. 21.3 Transportation 21.3.1 The Contractor shall at its own risk and expense transport all the Plant and Equipment and the Contractor’s Equipment to the Site by the mode of transport that the Contractor judges most suitable under all the circumstances. 21.3.2 Unless otherwise provided in the Contract, the Contractor shall be entitled to select any safe mode of transport operated by any person to carry the Plant and Equipment and the Contractor’s Equipment. 21.3.3 Upon dispatch of each shipment of the Plant and Equipment and the Contractor’s Equipment, the Contractor shall notify the Employer by telex, cable, facsimile or Electronic Data Interchange (EDI) of the description of the Plant and Equipment and of the Contractor’s Equipment, the point and means of dispatch, and the estimated time and point of arrival in the country where the Site is located, if applicable, and at the Site. The Contractor shall furnish the Employer with relevant shipping documents to be agreed upon between the parties. 21.3.4 The Contractor shall be responsible for obtaining, if necessary, approvals from the authorities for transportation of the Plant and Equipment and the Contractor’s Equipment to the Site. The Employer shall use its best endeavors in a timely and expeditious manner to assist the Contractor in obtaining such approvals, if requested by the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any claim for damage to roads, bridges or any other traffic facilities that may be caused by the transport of the Plant and Equipment and the Contractor’s Equipment to the Site. 21.4 Customs Clearance The Contractor shall, at its own expense, handle all imported Plant and Equipment and Contractor’s Equipment at the point(s) of import and shall handle any formalities for customs clearance, subject to the Employer’s obligations under GCC Sub-Clause 14.2, provided that if applicable laws or regulations require any application or act to be made by or in the name of the Employer, the Employer shall take all necessary steps to comply with such laws or regulations. In the event of delays in customs clearance that are not the fault of the Contractor, the Contractor shall be entitled to an extension in the Time for Completion, pursuant to GCC Clause 40. |
| 22. Installation | 22.1 Setting Out/Supervision/Labor 22.1.1 Bench Mark: The Contractor shall be responsible for the true and proper setting-out of the Facilities in relation to bench marks, reference marks and lines provided to it in writing by or on behalf of the Employer. If, at any time during the progress of installation of the Facilities, any error shall appear in the position, level or alignment of the Facilities, the Contractor shall forthwith notify the Project Manager of such error and, at its own expense, immediately rectify such error to the reasonable satisfaction of the Project Manager. If such error is based on incorrect data provided in writing by or on behalf of the Employer, the expense of rectifying the same shall be borne by the Employer. 22.1.2 Contractor’s Supervision: The Contractor shall give or provide all necessary superintendence during the installation of the Facilities, and the Construction Manager or its deputy shall be constantly on the Site to provide full-time superintendence of the installation. The Contractor shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand. 22.1.3 Labor: (a) The Contractor shall provide and employ on the Site in the installation of the Facilities such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. The Contractor is encouraged to use local labor that has the necessary skills. (b) Unless otherwise provided in the Contract, the Contractor shall be responsible for the recruitment, transportation, accommodation and catering of all labor, local or expatriate, required for the execution of the Contract and for all payments in connection therewith. (c) The Contractor shall be responsible for obtaining all necessary permit(s) and/or visa(s) from the appropriate authorities for the entry of all labor and personnel to be employed on the Site into the country where the Site is located. (d) The Contractor shall at its own expense provide the means of repatriation to all of its and its Subcontractor’s personnel employed on the Contract at the Site to their various home countries. It shall also provide suitable temporary maintenance of all such persons from the cessation of their employment on the Contract to the date programmed for their departure. In the event that the Contractor defaults in providing such means of transportation and temporary maintenance, the Employer may provide the same to such personnel and recover the cost of doing so from the Contractor. (e) The Contractor shall at all times during the progress of the Contract use its best endeavors to prevent any unlawful, riotous or disorderly conduct or behavior by or amongst its employees and the labor of its Subcontractors. (f) The Contractor shall, in all dealings with its labor and the labor of its Subcontractors currently employed on or connected with the Contract, pay due regard to all recognized festivals, official holidays, religious or other customs and all local laws and regulations pertaining to the employment of labor. 22.2 Contractor’s Equipment 22.2.1 All Contractor’s Equipment brought by the Contractor onto the Site shall be deemed to be intended to be used exclusively for the execution of the Contract. The Contractor shall not remove the same from the Site without the Project Manager’s consent that such Contractor’s Equipment is no longer required for the execution of the Contract. 22.2.2 Unless otherwise specified in the Contract, upon completion of the Facilities, the Contractor shall remove from the Site all Equipment brought by the Contractor onto the Site and any surplus materials remaining thereon. 22.2.3 The Employer will, if requested, use its best endeavors to assist the Contractor in obtaining any local, state or national government permission required by the Contractor for the export of the Contractor’s Equipment imported by the Contractor for use in the execution of the Contract that is no longer required for the execution of the Contract. 22.3 Site Regulations and Safety The Employer and the Contractor shall establish Site regulations setting out the rules to be observed in the execution of the Contract at the Site and shall comply therewith. The Contractor shall prepare and submit to the Employer, with a copy to the Project Manager, proposed Site regulations for the Employer’s approval, which approval shall not be unreasonably withheld. Such Site regulations shall include, but shall not be limited to, rules in respect of security, safety of the Facilities, gate control, sanitation, medical care, and fire prevention. 22.4 Opportunities for Other Contractors 22.4.1 The Contractor shall, upon written request from the Employer or the Project Manager, give all reasonable opportunities for carrying out the work to any other contractors employed by the Employer on or near the Site. 22.4.2 If the Contractor, upon written request from the Employer or the Project Manager, makes available to other contractors any roads or ways the maintenance for which the Contractor is responsible, permits the use by such other contractors of the Contractor’s Equipment, or provides any other service of whatsoever nature for such other contractors, the Employer shall fully compensate the Contractor for any loss or damage caused or occasioned by such other contractors in respect of any such use or service, and shall pay to the Contractor reasonable remuneration for the use of such equipment or the provision of such services. 22.4.3 The Contractor shall also so arrange to perform its work as to minimize, to the extent possible, interference with the work of other contractors. The Project Manager shall determine the resolution of any difference or conflict that may arise between the Contractor and other contractors and the workers of the Employer in regard to their work. 22.4.4 The Contractor shall notify the Project Manager promptly of any defects in the other contractors’ work that come to its notice, and that could affect the Contractor’s work. The Project Manager shall determine the corrective measures, if any, required to rectify the situation after inspection of the Facilities. Decisions made by the Project Manager shall be binding on the Contractor. 22.5 Emergency Work If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Facilities, the Contractor shall immediately carry out such work. If the Contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Facilities. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Contractor in writing of such emergency, the work done and the reasons therefor. If the work done or caused to be done by the Employer is work that the Contractor was liable to do at its own expense under the Contract, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Contractor to the Employer. Otherwise, the cost of such remedial work shall be borne by the Employer. 22.6 Site Clearance 22.6.1 Site Clearance in Course of Performance: In the course of carrying out the Contract, the Contractor shall keep the Site reasonably free from all unnecessary obstruction, store or remove any surplus materials, clear away any wreckage, rubbish or temporary works from the Site, and remove any Contractor’s Equipment no longer required for execution of the Contract. 22.6.2 Clearance of Site after Completion: After Completion of all parts of the Facilities, the Contractor shall clear away and remove all wreckage, rubbish and debris of any kind from the Site, and shall leave the Site and Facilities clean and safe. 22.7 Watching and Lighting The Contractor shall provide and maintain at its own expense all lighting, fencing, and watching when and where necessary for the proper execution and the protection of the Facilities, or for the safety of the owners and occupiers of adjacent property and for the safety of the public. 22.8 Work at Night and on Holidays 22.8.1 Unless otherwise provided in the Contract, no work shall be carried out during the night and on public holidays of the country where the Site is located without prior written consent of the Employer, except where work is necessary or required to ensure safety of the Facilities or for the protection of life, or to prevent loss or damage to property, when the Contractor shall immediately advise the Project Manager, provided that provisions of this GCC Sub-Clause 22.8.1 shall not apply to any work which is customarily carried out by rotary or double-shifts. 22.8.2 Notwithstanding GCC Sub-Clauses 22.8.1 or 22.1.3, if and when the Contractor considers it necessary to carry out work at night or on public holidays so as to meet the Time for Completion and requests the Employer’s consent thereto, the Employer shall not unreasonably withhold such consent. |
| 23. Test and Inspection | 23.1 The Contractor shall at its own expense carry out at the place of manufacture and/or on the Site all such tests and/or inspections of the Plant and Equipment and any part of the Facilities as are specified in the Contract. 23.2 The Employer and the Project Manager or their designated representatives shall be entitled to attend the aforesaid test and/or inspection, provided that the Employer shall bear all costs and expenses incurred in connection with such attendance including, but not limited to, all traveling and board and lodging expenses. 23.3 Whenever the Contractor is ready to carry out any such test and/or inspection, the Contractor shall give a reasonable advance notice of such test and/or inspection and of the place and time thereof to the Project Manager. The Contractor shall obtain from any relevant third party or manufacturer any necessary permission or consent to enable the Employer and the Project Manager (or their designated representatives) to attend the test and/or inspection. 23.4 The Contractor shall provide the Project Manager with a certified report of the results of any such test and/or inspection. If the Employer or Project Manager (or their designated representatives) fails to attend the test and/or inspection, or if it is agreed between the parties that such persons shall not do so, then the Contractor may proceed with the test and/or inspection in the absence of such persons, and may provide the Project Manager with a certified report of the results thereof. 23.5 The Project Manager may require the Contractor to carry out any test and/or inspection not required by the Contract, provided that the Contractor’s reasonable costs and expenses incurred in the carrying out of such test and/or inspection shall be added to the Contract Price. Further, if such test and/or inspection impedes the progress of work on the Facilities and/or the Contractor’s performance of its other obligations under the Contract, due allowance will be made in respect of the Time for Completion and the other obligations so affected. 23.6 If any Plant and Equipment or any part of the Facilities fails to pass any test and/or inspection, the Contractor shall either rectify or replace such Plant and Equipment or part of the Facilities and shall repeat the test and/or inspection upon giving a notice under GCC Sub-Clause 23.3. 23.7 If any dispute or difference of opinion shall arise between the parties in connection with or arising out of the test and/or inspection of the Plant and Equipment or part of the Facilities that cannot be settled between the parties within a reasonable period of time, it may be referred to an Arbitrator for determination in accordance with GCC Sub-Clause 6.1. 23.8 The Contractor shall afford the Employer and the Project Manager, at the Employer’s expense, access at any reasonable time to any place where the Plant and Equipment are being manufactured or the Facilities are being installed, in order to inspect the progress and the manner of manufacture or installation, provided that the Project Manager shall give the Contractor a reasonable prior notice. 23.9 The Contractor agrees that neither the execution of a test and/or inspection of Plant and Equipment or any part of the Facilities, nor the attendance by the Employer or the Project Manager, nor the issue of any test certificate pursuant to GCC Sub-Clause 23.4, shall release the Contractor from any other responsibilities under the Contract. 23.10 No part of the Facilities or foundations shall be covered up on the Site without the Contractor carrying out any test and/or inspection required under the Contract. The Contractor shall give a reasonable notice to the Project Manager whenever any such part of the Facilities or foundations are ready or about to be ready for test and/or inspection; such test and/or inspection and notice thereof shall be subject to the requirements of the Contract. 23.11 The Contractor shall uncover any part of the Facilities or foundations, or shall make openings in or through the same as the Project Manager may from time to time require at the Site, and shall reinstate and make good such part or parts. If any parts of the Facilities or foundations have been covered up at the Site after compliance with the requirement of GCC Sub-Clause 23.10 and are found to be executed in accordance with the Contract, the expenses of uncovering, making openings in or through, reinstating, and making good the same shall be borne by the Employer, and the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been delayed or impeded in the performance of any of its obligations under the Contract. |
| 24. Completion of the Facilities | 24.1 As soon as the Facilities or any part thereof has, in the opinion of the Contractor, been completed operationally and structurally and put in a tight and clean condition as specified in the Technical Specifications, excluding minor items not materially affecting the operation or safety of the Facilities, the Contractor shall so notify the Employer in writing. 24.2 Within seven (7) days after receipt of the notice from the Contractor under GCC Sub-Clause 24.1, the Employer shall supply the operating and maintenance personnel specified in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement for Precommissioning of the Facilities or any part thereof. Pursuant to the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement, the Employer shall also provide, within the said seven (7) day period, the raw materials, utilities, lubricants, chemicals, catalysts, facilities, services and other matters required for Precommissioning of the Facilities or any part thereof. 24.3 As soon as reasonably practicable after the operating and maintenance personnel have been supplied by the Employer and the raw materials, utilities, lubricants, chemicals, catalysts, facilities, services and other matters have been provided by the Employer in accordance with GCC Sub-Clause 24.2, the Contractor shall commence Precommissioning of the Facilities or the relevant part thereof in preparation for Commissioning. 24.4 As soon as all works in respect of Precommissioning are completed and, in the opinion of the Contractor, the Facilities or any part thereof is ready for Commissioning, the Contractor shall so notify the Project Manager in writing. 24.5 The Project Manager shall, within fourteen (14) days after receipt of the Contractor’s notice under GCC Sub-Clause 24.4, either issue a Completion Certificate in the form specified in the Sample Forms and Procedures section in the bidding documents, stating that the Facilities or that part thereof have reached Completion as of the date of the Contractor’s notice under GCC Sub-Clause 24.4, or notify the Contractor in writing of any defects and/or deficiencies. If the Project Manager notifies the Contractor of any defects and/or deficiencies, the Contractor shall then correct such defects and/or deficiencies, and shall repeat the procedure described in GCC Sub-Clause 24.4.If the Project Manager is satisfied that the Facilities or that part thereof have reached Completion, the Project Manager shall, within seven (7) days after receipt of the Contractor’s repeated notice, issue a Completion Certificate stating that the Facilities or that part thereof have reached Completion as of the date of the Contractor’s repeated notice.If the Project Manager is not so satisfied, then it shall notify the Contractor in writing of any defects and/or deficiencies within seven (7) days after receipt of the Contractor’s repeated notice, and the above procedure shall be repeated. 24.6 If the Project Manager fails to issue the Completion Certificate and fails to inform the Contractor of any defects and/or deficiencies within fourteen (14) days after receipt of the Contractor’s notice under GCC Sub-Clause 24.4 or within seven (7) days after receipt of the Contractor’s repeated notice under GCC Sub-Clause 24.5, or if the Employer makes use of the Facilities or part thereof, then the Facilities or that part thereof shall be deemed to have reached Completion as of the date of the Contractor’s notice or repeated notice, or as of the Employer’s use of the Facilities, as the case may be. 24.7 As soon as possible after Completion, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract, failing which the Employer will undertake such completion and deduct the costs thereof from any monies owing to the Contractor. 24.8 Upon Completion, the Employer shall be responsible for the care and custody of the Facilities or the relevant part thereof, together with the risk of loss or damage thereto, and shall thereafter take over the Facilities or the relevant part thereof. |
| 25. Commissioning and Operational Acceptance | 25.1 Commissioning 25.1.1 Commissioning of the Facilities or any part thereof shall be commenced by the Contractor immediately after issue of the Completion Certificate by the Project Manager, pursuant to GCC Sub-Clause 24.5, or immediately after issue of the deemed Completion, under GCC Sub-Clause 24.6. 25.1.2 The Employer shall supply the operating and maintenance personnel and all raw materials, utilities, lubricants, chemicals, catalysts, facilities, services and other matters required for Commissioning. 25.2 Guarantee Test 25.2.1 The Guarantee Test (and repeats thereof) shall be conducted by the Contractor during Commissioning of the Facilities or the relevant part thereof to ascertain whether the Facilities or the relevant part can attain the Functional Guarantees specified in the Technical Specifications. The Contractor’s and Project Manager’s advisory personnel shall attend the Guarantee Test, and shall advise and assist the Employer. The Employer shall promptly provide the Contractor with such information as the Contractor may reasonably require in relation to the conduct and results of the Guarantee Test (and any repeats thereof). 25.2.2 If for reasons not attributable to the Contractor, the Guarantee Test of the Facilities or the relevant part thereof cannot be successfully completed within the period from the date of Completion specified in the SCC or any other period agreed upon by the Employer and the Contractor, the Contractor shall be deemed to have fulfilled its obligations with respect to the Functional Guarantees, and GCC Sub-Clauses 28.2 and 28.3 shall not apply. 25.3 Operational Acceptance 25.3.1 Subject to GCC Sub-Clause 25.4 below, Operational Acceptance shall occur in respect of the Facilities or any part thereof when (a) the Guarantee Test has been successfully completed and the Functional Guarantees are met; or (b) the Guarantee Test has not been successfully completed or has not been carried out for reasons not attributable to the Contractor within the period from the date of Completion specified in the SCC or any other agreed upon period as specified in GCC Sub-Clause 25.2.2 above; or (c) the Contractor has paid the liquidated damages specified in GCC Sub-Clause 28.3 hereof; and (d) any minor items mentioned in GCC Sub-Clause 24.7 hereof relevant to the Facilities or that part thereof have been completed. 25.3.2 At any time after any of the events set out in GCC Sub-Clause 25.3.1 have occurred, the Contractor may give a notice to the Project Manager requesting the issue of an Operational Acceptance Certificate in the form provided in the Bidding Documents or in another form acceptable to the Employer in respect of the Facilities or the part thereof specified in such notice as of the date of such notice. 25.3.3 The Project Manager shall, after consultation with the Employer, and within seven (7) days after receipt of the Contractor’s notice, issue an Operational Acceptance Certificate. 25.3.4 If within seven (7) days after receipt of the Contractor’s notice, the Project Manager fails to issue the Operational Acceptance Certificate or fails to inform the Contractor in writing of the justifiable reasons why the Project Manager has not issued the Operational Acceptance Certificate, the Facilities or the relevant part thereof shall be deemed to have been accepted as of the date of the Contractor’s said notice. 25.4 Partial Acceptance 25.4.1 If the Contract specifies that Completion and Commissioning shall be carried out in respect of parts of the Facilities, the provisions relating to Completion and Commissioning including the Guarantee Test shall apply to each such part of the Facilities individually, and the Operational Acceptance Certificate shall be issued accordingly for each such part of the Facilities. 25.4.2 If a part of the Facilities comprises facilities such as buildings, for which no Commissioning or Guarantee Test is required, then the Project Manager shall issue the Operational Acceptance Certificate for such facility when it attains Completion, provided that the Contractor shall thereafter complete any outstanding minor items that are listed in the Operational Acceptance Certificate. |

F. Guarantees and Liabilities

| 26. Completion Time Guarantee | 26.1 The Contractor guarantees that it shall attain Completion of the Facilities (or a part for which a separate time for completion is specified in the SCC) within the Time for Completion specified in the SCC pursuant to GCC Sub-Clause 8.2, or within such extended time to which the Contractor shall be entitled under GCC Clause 40 hereof. 26.2 If the Contractor fails to attain Completion of the Facilities or any part thereof within the Time for Completion or any extension thereof under GCC Clause 40, the Contractor shall pay to the Employer liquidated damages in the amount specified in the SCC as a percentage rate of the Contract Price, or the relevant part thereof. The aggregate amount of such liquidated damages shall in no event exceed the amount specified as “Maximum” in the SCC. Once the “Maximum” is reached, the Employer may consider termination of the Contract, pursuant to GCC Sub-Clause 42.2.2.Such payment shall completely satisfy the Contractor’s obligation to attain Completion of the Facilities or the relevant part thereof within the Time for Completion or any extension thereof under GCC Clause 40. The Contractor shall have no further liability whatsoever to the Employer in respect thereof. However, the payment of liquidated damages shall not in any way relieve the Contractor from any of its obligations to complete the Facilities or from any other obligations and liabilities of the Contractor under the Contract. Save for liquidated damages payable under this GCC Sub-Clause 26.2, the failure by the Contractor to attain any milestone or other act, matter or thing by any date specified in the corresponding Appendix (Time Schedule) to the Contract Agreement and/or other program of work prepared pursuant to GCC Sub-Clause 18.2 shall not render the Contractor liable for any loss or damage thereby suffered by the Employer. 26.3 If the Contractor attains Completion of the Facilities or any part thereof before the Time for Completion or any extension thereof under GCC Clause 40, the Employer shall pay to the Contractor a bonus in the amount specified in the SCC. The aggregate amount of such bonus shall in no event exceed the amount specified as “Maximum” in the SCC. |
| --- | --- |
| 27. Defect Liability | 27.1 The Contractor warrants that the Facilities or any part thereof shall be free from defects in the design, engineering, materials and workmanship of the Plant and Equipment supplied and of the work executed. 27.2 The Defect Liability Period shall be eighteen (18) months from the date of Completion of the Facilities (or any part thereof) or twelve (12) months from the date of Operational Acceptance of the Facilities (or any part thereof), whichever first occurs, unless specified otherwise in the SCC. If during the Defect Liability Period any defect should be found in the design, engineering, materials and workmanship of the Plant and Equipment supplied or of the work executed by the Contractor, the Contractor shall promptly, in consultation and agreement with the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace or otherwise make good (as the Contractor shall, at its discretion, determine) such defect as well as any damage to the Facilities caused by such defect. The Contractor shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Facilities arising out of or resulting from any of the following causes: (a) improper operation or maintenance of the Facilities by the Employer (b) operation of the Facilities outside specifications provided in the Contract (c) normal wear and tear. 27.3 The Contractor’s obligations under this GCC Clause 27 shall not apply to (a) any materials that are supplied by the Employer under GCC Sub-Clause 21.2, are normally consumed in operation, or have a normal life shorter than the Defect Liability Period stated herein (b) any designs, specifications or other data designed, supplied or specified by or on behalf of the Employer or any matters for which the Contractor has disclaimed responsibility herein (c) any other materials supplied or any other work executed by or on behalf of the Employer, except for the work executed by the Employer under GCC Sub-Clause 27.7. 27.4 The Employer shall give the Contractor a notice stating the nature of any such defect together with all available evidence thereof, promptly following the discovery thereof. The Employer shall afford all reasonable opportunity for the Contractor to inspect any such defect. 27.5 The Employer shall afford the Contractor all necessary access to the Facilities and the Site to enable the Contractor to perform its obligations under this GCC Clause 27.The Contractor may, with the consent of the Employer, remove from the Site any Plant and Equipment or any part of the Facilities that are defective if the nature of the defect, and/or any damage to the Facilities caused by the defect, is such that repairs cannot be expeditiously carried out at the Site. 27.6 If the repair, replacement or making good is of such a character that it may affect the efficiency of the Facilities or any part thereof, the Employer may give to the Contractor a notice requiring that tests of the defective part of the Facilities shall be made by the Contractor immediately upon completion of such remedial work, whereupon the Contractor shall carry out such tests. If such part fails the tests, the Contractor shall carry out further repair, replacement or making good (as the case may be) until that part of the Facilities passes such tests. The tests shall be agreed upon by the Employer and the Contractor. 27.7 If the Contractor fails to commence the work necessary to remedy such defect or any damage to the Facilities caused by such defect within a reasonable time (which shall in no event be considered to be less than fifteen (15) days), the Employer may, following notice to the Contractor, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Contractor or may be deducted by the Employer from any monies due the Contractor or claimed under the Performance Security. 27.8 If the Facilities or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Facilities or such part, as the case may be, shall be extended by a period equal to the period during which the Facilities or such part cannot be used by the Employer because of any of the aforesaid reasons. 27.9 Except as provided in GCC Clauses 27 and 33, the Contractor shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, in respect of defects in the Facilities or any part thereof, the Plant and Equipment, design or engineering or work executed that appear after Completion of the Facilities or any part thereof, except where such defects are the result of the gross negligence, fraud, criminal or willful action of the Contractor. 27.10 In addition, the Contractor shall also provide an extended warranty for any such component of the Facilities and during the period of time as may be specified in the SCC. Such obligation shall be in addition to the defect liability specified under GCC Sub-Clause 27.2. |
| 28. Functional Guarantees | 28.1 The Contractor guarantees that during the Guarantee Test, the Facilities and all parts thereof shall attain the Functional Guarantees specified in the corresponding Appendix (Functional Guarantees) to the Contract Agreement, subject to and upon the conditions therein specified. 28.2 If, for reasons attributable to the Contractor, the minimum level of the Functional Guarantees specified in the corresponding Appendix (Functional Guarantees) to the Contract Agreement are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications and/or additions to the Plant or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. The Contractor shall notify the Employer upon completion of the necessary changes, modifications and/or additions, and shall request the Employer to repeat the Guarantee Test until the minimum level of the Guarantees has been met. If the Contractor eventually fails to meet the minimum level of Functional Guarantees, the Employer may consider termination of the Contract, pursuant to GCC Sub-Clause 42.2.2. 28.3 If, for reasons attributable to the Contractor, the Functional Guarantees specified in the corresponding Appendix (Functional Guarantees) to the Contract Agreement are not attained either in whole or in part, but the minimum level of the Functional Guarantees specified in the said Appendix to the Contract Agreement is met, the Contractor shall, at the Contractor’s option, either (a) make such changes, modifications and/or additions to the Facilities or any part thereof that are necessary to attain the Functional Guarantees at its cost and expense, and shall request the Employer to repeat the Guarantee Test or (b) pay liquidated damages to the Employer in respect of the failure to meet the Functional Guarantees in accordance with the provisions in the corresponding Appendix (Functional Guarantees) to the Contract Agreement. 28.4 The payment of liquidated damages under GCC Sub-Clause 28.3, up to the limitation of liability specified in the SCC, shall completely satisfy the Contractor’s guarantees under GCC Sub-Clause 28.3, and the Contractor shall have no further liability whatsoever to the Employer in respect thereof. Upon the payment of such liquidated damages by the Contractor, the Project Manager shall issue the Operational Acceptance Certificate for the Facilities or any part thereof in respect of which the liquidated damages have been so paid. |
| 29. Patent Indemnity | 29.1 The Contractor shall, subject to the Employer’s compliance with GCC Sub-Clause 29.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract by reason of: (a) the installation of the Facilities by the Contractor or the use of the Facilities in the country where the Site is located; and (b) the sale of the products produced by the Facilities in any country. Such indemnity shall not cover any use of the Facilities or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the Facilities or any part thereof, or any products produced thereby in association or combination with any other equipment, plant or materials not supplied by the Contractor, pursuant to the Contract Agreement. 29.2 If any proceedings are brought or any claim is made against the Employer arising out of the matters referred to in GCC Sub-Clause 29.1, the Employer shall promptly give the Contractor a notice thereof, and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. 29.3 The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Contractor may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Employer. |
| 30. Limitation of Liability | 30.1 Except in cases of criminal negligence or willful misconduct, (a) the Contractor shall not be liable to the Employer, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. |

G. Risk Distribution

| 31. Transfer of Ownership | 31.1 Ownership of the Plant and Equipment (including spare parts) to be imported into the country where the Site is located shall be transferred to the Employer upon loading on to the mode of transport to be used to convey the Plant and Equipment from the country of origin to that country. 31.2 Ownership of the Plant and Equipment (including spare parts) procured in the country where the Site is located shall be transferred to the Employer when the Plant and Equipment are brought on to the Site. 31.3 Ownership of the Contractor’s Equipment used by the Contractor and its Subcontractors in connection with the Contract shall remain with the Contractor or its Subcontractors. 31.4 Ownership of any Plant and Equipment in excess of the requirements for the Facilities shall revert to the Contractor upon Completion of the Facilities or at such earlier time when the Employer and the Contractor agree that the Plant and Equipment in question are no longer required for the Facilities. 31.5 Notwithstanding the transfer of ownership of the Plant and Equipment, the responsibility for care and custody thereof together with the risk of loss or damage thereto shall remain with the Contractor pursuant to GCC Clause 32 (Care of Facilities) hereof until Completion of the Facilities or the part thereof in which such Plant and Equipment are incorporated. |
| --- | --- |
| 32. Care of Facilities | 32.1 The Contractor shall be responsible for the care and custody of the Facilities or any part thereof until the date of Completion of the Facilities pursuant to GCC Clause 24 or, where the Contract provides for Completion of the Facilities in parts, until the date of Completion of the relevant part, and shall make good at its own cost any loss or damage that may occur to the Facilities or the relevant part thereof from any cause whatsoever during such period. The Contractor shall also be responsible for any loss or damage to the Facilities caused by the Contractor or its Subcontractors in the course of any work carried out, pursuant to GCC Clause 27. Notwithstanding the foregoing, the Contractor shall not be liable for any loss or damage to the Facilities or that part thereof caused by reason of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GCC Sub-Clauses 32.2 and 38.1. 32.2 If any loss or damage occurs to the Facilities or any part thereof or to the Contractor’s temporary facilities by reason of (a) (insofar as they relate to the country where the Site is located) nuclear reaction, nuclear radiation, radioactive contamination, pressure wave caused by aircraft or other aerial objects, or any other occurrences that an experienced contractor could not reasonably foresee, or if reasonably foreseeable could not reasonably make provision for or insure against, insofar as such risks are not normally insurable on the insurance market and are mentioned in the general exclusions of the policy of insurance, including War Risks and Political Risks, taken out under GCC Clause 34 hereof (b) any use or occupation by the Employer or any third party (other than a Subcontractor) authorized by the Employer of any part of the Facilities (c) any use of or reliance upon any design, data or specification provided or designated by or on behalf of the Employer, or any such matter for which the Contractor has disclaimed responsibility herein, the Employer shall pay to the Contractor all sums payable in respect of the Facilities executed, notwithstanding that the same be lost, destroyed or damaged, and will pay to the Contractor the replacement value of all temporary facilities and all parts thereof lost, destroyed or damaged. If the Employer requests the Contractor in writing to make good any loss or damage to the Facilities thereby occasioned, the Contractor shall make good the same at the cost of the Employer in accordance with GCC Clause 39. If the Employer does not request the Contractor in writing to make good any loss or damage to the Facilities thereby occasioned, the Employer shall either request a change in accordance with GCC Clause 39, excluding the performance of that part of the Facilities thereby lost, destroyed or damaged, or, where the loss or damage affects a substantial part of the Facilities, the Employer shall terminate the Contract pursuant to GCC Sub-Clause 42.1 hereof. 32.3 The Contractor shall be liable for any loss of or damage to any Contractor’s Equipment, or any other property of the Contractor used or intended to be used for purposes of the Facilities, except (i) as mentioned in GCC Sub-Clause 32.2 (with respect to the Contractor’s temporary facilities), and (ii) where such loss or damage arises by reason of any of the matters specified in GCC Sub-Clauses 32.2 (b) and (c) and 38.1. 32.4 With respect to any loss or damage caused to the Facilities or any part thereof or to the Contractor’s Equipment by reason of any of the matters specified in GCC Sub-Clause 38.1, the provisions of GCC Sub-Clause 38.3 shall apply. |
| 33. Loss of or Damage to Property; Accident or Injury to Workers; Indemnification | 33.1 Subject to GCC Sub-Clause 33.3, the Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property (other than the Facilities whether accepted or not), arising in connection with the supply and installation of the Facilities and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents. 33.2 If any proceedings are brought or any claim is made against the Employer that might subject the Contractor to liability under GCC Sub-Clause 33.1, the Employer shall promptly give the Contractor a notice thereof and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. 33.3 The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from any liability for loss of or damage to property of the Employer, other than the Facilities not yet taken over, that is caused by fire, explosion or any other perils, in excess of the amount recoverable from insurances procured under GCC Clause 34, provided that such fire, explosion or other perils were not caused by any act or failure of the Contractor.33.4 The party entitled to the benefit of an indemnity under this GCC Clause 33 shall take all reasonable measures to mitigate any loss or damage which has occurred. If the party fails to take such measures, the other party’s liabilities shall be correspondingly reduced. |
| 34. Insurance | 34.1 To the extent specified in the corresponding Appendix (Insurance Requirements) to the Contract Agreement, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified in the said Appendix. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, who should not unreasonably withhold such approval. (a) Cargo Insurance During Transport Covering loss or damage occurring while in transit from the Contractor’s or Subcontractor’s works or stores until arrival at the Site, to the Plant and Equipment (including spare parts therefor) and to the Contractor’s Equipment. (b) Installation All Risks Insurance Covering physical loss or damage to the Facilities at the Site, occurring prior to Completion of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the Defect Liability Period while the Contractor is on the Site for the purpose of performing its obligations during the Defect Liability Period. (c) Third Party Liability Insurance Covering bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property occurring in connection with the supply and installation of the Facilities. (d) Automobile Liability Insurance Covering use of all vehicles used by the Contractor or its Subcontractors (whether or not owned by them) in connection with the execution of the Contract. (e) Workers’ Compensation In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed. (f) Employer’s Liability In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed. (g) Other Insurances Such other insurances as may be specifically agreed upon by the parties hereto as listed in the said the corresponding Appendix. 34.2 The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1, except for the Third Party Liability, Workers’ Compensation and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Workers’ Compensation and Employer’s Liability Insurances. All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. 34.3 The Contractor shall, in accordance with the provisions of the corresponding Appendix (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days’ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy. 34.4 The Contractor shall ensure that, where applicable, its Subcontractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Subcontractors are covered by the policies taken out by the Contractor. 34.5 The Employer shall at its expense take out and maintain in effect during the performance of the Contract those insurances specified in the corresponding Appendix (Insurance Requirements) to the Contract Agreement, in the sums and with the deductibles and other conditions specified in the said Appendix. The Contractor and the Contractor’s Subcontractors shall be named as co-insureds under all such policies. All insurers’ rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. The Employer shall deliver to the Contractor satisfactory evidence that the required insurances are in full force and effect. The policies shall provide that not less than twenty-one (21) days’ notice shall be given to the Contractor by all insurers prior to any cancellation or material modification of the policies. If so requested by the Contractor, the Employer shall provide copies of the policies taken out by the Employer under this GCC Sub-Clause 34.5. 34.6 If the Contractor fails to take out and/or maintain in effect the insurances referred to in GCC Sub-Clause 34.1, the Employer may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Contractor under the Contract any premium that the Employer shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Contractor. If the Employer fails to take out and/or maintain in effect the insurances referred to in GCC 34.5, the Contractor may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Employer under the Contract any premium that the Contractor shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Employer. If the Contractor fails to or is unable to take out and maintain in effect any such insurances, the Contractor shall nevertheless have no liability or responsibility towards the Employer, and the Contractor shall have full recourse against the Employer for any and all liabilities of the Employer herein. 34.7 Unless otherwise provided in the Contract, the Contractor shall prepare and conduct all and any claims made under the policies effected by it pursuant to this GCC Clause 34, and all monies payable by any insurers shall be paid to the Contractor. The Employer shall give to the Contractor all such reasonable assistance as may be required by the Contractor. With respect to insurance claims in which the Employer’s interest is involved, the Contractor shall not give any release or make any compromise with the insurer without the prior written consent of the Employer. With respect to insurance claims in which the Contractor’s interest is involved, the Employer shall not give any release or make any compromise with the insurer without the prior written consent of the Contractor. |
| 35. Unforeseen Conditions | 35.1 If, during the execution of the Contract, the Contractor shall encounter on the Site any physical conditions (other than climatic conditions) or artificial obstructions that could not have been reasonably foreseen prior to the date of the Contract Agreement by an experienced contractor on the basis of reasonable examination of the data relating to the Facilities (including any data as to boring tests) provided by the Employer, and on the basis of information that it could have obtained from a visual inspection of the Site (if access thereto was available) or other data readily available to it relating to the Facilities, and if the Contractor determines that it will in consequence of such conditions or obstructions incur additional cost and expense or require additional time to perform its obligations under the Contract that would not have been required if such physical conditions or artificial obstructions had not been encountered, the Contractor shall promptly, and before performing additional work or using additional Plant and Equipment or Contractor’s Equipment, notify the Project Manager in writing of (a) the physical conditions or artificial obstructions on the Site that could not have been reasonably foreseen (b) the additional work and/or Plant and Equipment and/or Contractor’s Equipment required, including the steps which the Contractor will or proposes to take to overcome such conditions or obstructions (c) the extent of the anticipated delay (d) the additional cost and expense that the Contractor is likely to incur. On receiving any notice from the Contractor under this GCC Sub-Clause 35.1, the Project Manager shall promptly consult with the Employer and Contractor and decide upon the actions to be taken to overcome the physical conditions or artificial obstructions encountered. Following such consultations, the Project Manager shall instruct the Contractor, with a copy to the Employer, of the actions to be taken. 35.2 Any reasonable additional cost and expense incurred by the Contractor in following the instructions from the Project Manager to overcome such physical conditions or artificial obstructions referred to in GCC Sub-Clause 35.1 shall be paid by the Employer to the Contractor as an addition to the Contract Price. 35.3 If the Contractor is delayed or impeded in the performance of the Contract because of any such physical conditions or artificial obstructions referred to in GCC Sub-Clause 35.1, the Time for Completion shall be extended in accordance with GCC Clause 40. |
| 36. Change in Laws and Regulations | 36.1 If, after the date twenty-eight (28) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the SCC. |
| 37. Force Majeure | 37.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether a state of war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of civil or military government, conspiracy, riot, civil commotion and terrorist acts, (c) confiscation, nationalization, mobilization, commandeering or requisition by or under the order of any government or de jure or de facto authority or ruler or any other act or failure to act of any local state or national government authority, (d) strike, sabotage, lockout, embargo, import restriction, port congestion, lack of usual means of public transportation and communication, industrial dispute, shipwreck, shortage or restriction of power supply, epidemics, quarantine and plague, (e) earthquake, landslide, volcanic activity, fire, flood or inundation, tidal wave, typhoon or cyclone, hurricane, storm, lightning, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, (f) shortage of labor, materials or utilities where caused by circumstances that are themselves Force Majeure. 37.2 If either party is prevented, hindered or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event. 37.3 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GCC Clause 40. 37.4 The party or parties affected by the event of Force Majeure shall use reasonable efforts to mitigate the effect thereof upon its or their performance of the Contract and to fulfill its or their obligations under the Contract, but without prejudice to either party’s right to terminate the Contract under GCC Sub-Clauses 37.6 and 38.5. 37.5 No delay or nonperformance by either party hereto caused by the occurrence of any event of Force Majeure shall (a) constitute a default or breach of the Contract, (b) (subject to GCC Sub-Clauses 32.2, 38.3 and 38.4) give rise to any claim for damages or additional cost or expense occasioned thereby if and to the extent that such delay or nonperformance is caused by the occurrence of an event of Force Majeure. 37.6 If the performance of the Contract is substantially prevented, hindered or delayed for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of one or more events of Force Majeure during the currency of the Contract, the parties will attempt to develop a mutually satisfactory solution, failing which either party may terminate the Contract by giving a notice to the other, but without prejudice to either party’s right to terminate the Contract under GCC Sub-Clause 38.5. 37.7 In the event of termination pursuant to GCC Sub-Clause 37.6, the rights and obligations of the Employer and the Contractor shall be as specified in GCC Sub-Clauses 42.1.2 and 42.1.3. 37.8 Notwithstanding GCC Sub-Clause 37.5, Force Majeure shall not apply to any obligation of the Employer to make payments to the Contractor herein. |
| 38. War Risks | 38.1 “War Risks” shall mean any event specified in paragraphs (a) and (b) of GCC Sub-Clause 37.1 and any explosion or impact of any mine, bomb, shell, grenade or other projectile, missile, munitions or explosive of war, occurring or existing in or near the country (or countries) where the Site is located. 38.2 Notwithstanding anything contained in the Contract, the Contractor shall have no liability whatsoever for or with respect to; (a) destruction of or damage to Facilities, Plant and Equipment, or any part thereof, (b) destruction of or damage to property of the Employer or any third party, (c) injury or loss of life if such destruction, damage, injury or loss of life is caused by any War Risks, and the Employer shall indemnify and hold the Contractor harmless from and against any and all claims, liabilities, actions, lawsuits, damages, costs, charges or expenses arising in consequence of or in connection with the same. 38.3 If the Facilities or any Plant and Equipment or Contractor’s Equipment or any other property of the Contractor used or intended to be used for the purposes of the Facilities shall sustain destruction or damage by reason of any War Risks, the Employer shall pay the Contractor for; (a) any part of the Facilities or the Plant and Equipment so destroyed or damaged (to the extent not already paid for by the Employer), (b) replacing or making good any Contractor’s Equipment or other property of the Contractor so destroyed or damaged, (c) replacing or making good any such destruction or damage to the Facilities or the Plant and Equipment or any part thereof, so far as may be required by the Employer, and as may be necessary for completion of the Facilities. If the Employer does not require the Contractor to replace or make good any such destruction or damage to the Facilities, the Employer shall either request a change in accordance with GCC Clause 39, excluding the performance of that part of the Facilities thereby destroyed or damaged or, where the loss, destruction or damage affects a substantial part of the Facilities, shall terminate the Contract, pursuant to GCC Sub-Clause 42.1. 38.4 Notwithstanding anything contained in the Contract, the Employer shall pay the Contractor for any increased costs or incidentals to the execution of the Contract that are in any way attributable to, consequent on, resulting from, or in any way connected with any War Risks, provided that the Contractor shall as soon as practicable notify the Employer in writing of any such increased cost. 38.5 If during the performance of the Contract any War Risks shall occur that financially or otherwise materially affect the execution of the Contract by the Contractor, the Contractor shall use its reasonable efforts to execute the Contract with due and proper consideration given to the safety of its and its Subcontractors’ personnel engaged in the work on the Facilities, provided, however, that if the execution of the work on the Facilities becomes impossible or is substantially prevented for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of any War Risks, the parties will attempt to develop a mutually satisfactory solution, failing which either party may terminate the Contract by giving a notice to the other. 38.6 In the event of termination pursuant to GCC Sub-Clauses 38.3 or 38.5, the rights and obligations of the Employer and the Contractor shall be specified in GCC Sub-Clauses 42.1.2 and 42.1.3. |

H. Change in Contract Elements

| 39. Change in the Facilities | 39.1 Introducing a Change 39.1.1 Subject to GCC Sub-Clauses 39.2.5 and 39.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Facilities (hereinafter called “Change”), provided that such Change falls within the general scope of the Facilities and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Facilities and the technical compatibility of the Change envisaged with the nature of the Facilities as specified in the Contract. 39.1.2 The Contractor may from time to time during its performance of the Contract propose to the Employer (with a copy to the Project Manager) any Change that the Contractor considers necessary or desirable to improve the quality, efficiency or safety of the Facilities. The Employer may at its discretion approve or reject any Change proposed by the Contractor, provided that the Employer shall approve any Change proposed by the Contractor to ensure the safety of the Facilities. 39.1.3 Notwithstanding GCC Sub-Clauses 39.1.1 and 39.1.2, no change made necessary because of any default of the Contractor in the performance of its obligations under the Contract shall be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Completion. 39.1.4 The procedure on how to proceed with and execute Changes is specified in GCC Sub-Clauses 39.2 and 39.3, and further details and sample forms are provided in the Sample Forms and Procedures section in the bidding documents. 39.2 Changes Originating from Employer 39.2.1 If the Employer proposes a Change pursuant to GCC Sub-Clause 39.1.1, it shall send to the Contractor a “Request for Change Proposal,” requiring the Contractor to prepare and furnish to the Project Manager as soon as reasonably practicable a “Change Proposal,” which shall include the following: (a) brief description of the Change (b) effect on the Time for Completion (c) estimated cost of the Change (d) effect on Functional Guarantees (if any) (e) effect on any other provisions of the Contract. 39.2.2 Prior to preparing and submitting the “Change Proposal,” the Contractor shall submit to the Project Manager an “Estimate for Change Proposal,” which shall be an estimate of the cost of preparing and submitting the Change Proposal. Upon receipt of the Contractor’s Estimate for Change Proposal, the Employer shall do one of the following: (a) accept the Contractor’s estimate with instructions to the Contractor to proceed with the preparation of the Change Proposal (b) advise the Contractor of any part of its Estimate for Change Proposal that is unacceptable and request the Contractor to review its estimate (c) advise the Contractor that the Employer does not intend to proceed with the Change. 39.2.3 Upon receipt of the Employer’s instruction to proceed under GCC Sub-Clause 39.2.2 (a), the Contractor shall, with proper expedition, proceed with the preparation of the Change Proposal, in accordance with GCC Sub-Clause 39.2.1. 39.2.4 The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If such rates and prices are inequitable, the parties thereto shall agree on specific rates for the valuation of the Change. 39.2.5 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Contractor under this GCC Clause 39 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price) of the Contract Agreement by more than fifteen percent (15%), the Contractor may give a written notice of objection thereto prior to furnishing the Change Proposal as aforesaid. If the Employer accepts the Contractor’s objection, the Employer shall withdraw the proposed Change and shall notify the Contractor in writing thereof. The Contractor’s failure to so object shall neither affect its right to object to any subsequent requested Changes or Change Orders herein, nor affect its right to take into account, when making such subsequent objection, the percentage increase or decrease in the Contract Price that any Change not objected to by the Contractor represents. 39.2.6 Upon receipt of the Change Proposal, the Employer and the Contractor shall mutually agree upon all matters therein contained. Within fourteen (14) days after such agreement, the Employer shall, if it intends to proceed with the Change, issue the Contractor with a Change Order. If the Employer is unable to reach a decision within fourteen (14) days, it shall notify the Contractor with details of when the Contractor can expect a decision. If the Employer decides not to proceed with the Change for whatever reason, it shall, within the said period of fourteen (14) days, notify the Contractor accordingly. Under such circumstances, the Contractor shall be entitled to reimbursement of all costs reasonably incurred by it in the preparation of the Change Proposal, provided that these do not exceed the amount given by the Contractor in its Estimate for Change Proposal submitted in accordance with GCC Sub-Clause 39.2.2. 39.2.7 If the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters identified in the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order.” Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the Arbitrator in accordance with the provisions of GCC Sub-Clause 6.1. 39.3 Changes Originating from Contractor 39.3.1 If the Contractor proposes a Change pursuant to GCC Sub-Clause 39.1.2, the Contractor shall submit to the Project Manager a written “Application for Change Proposal,” giving reasons for the proposed Change and including the information specified in GCC Sub-Clause 39.2.1.Upon receipt of the Application for Change Proposal, the parties shall follow the procedures outlined in GCC Sub-Clauses 39.2.6 and 39.2.7. However, should the Employer choose not to proceed, the Contractor shall not be entitled to recover the costs of preparing the Application for Change Proposal. |
| --- | --- |
| 40. Extension of Time for Completion | 40.1 The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) any Change in the Facilities as provided in GCC Clause 39 (b) any occurrence of Force Majeure as provided in GCC Clause 37, unforeseen conditions as provided in GCC Clause 35, or other occurrence of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GCC Sub-Clause 32.2 (c) any suspension order given by the Employer under GCC Clause 41 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 41.2 or (d) any changes in laws and regulations as provided in GCC Clause 36 or (e) any default or breach of the Contract by the Employer, specifically including failure to supply the items listed in the corresponding Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement, or any activity, act or omission of any other contractors employed by the Employer or (f) delays attributable to the Employer or caused by customs or (g) any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. 40.2 Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to an Arbitrator, pursuant to GCC Sub-Clause 6.1. 40.3 The Contractor shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract. |
| 41. Suspension | 41.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager. If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor’s default or breach of the Contract, the Contractor’s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in accordance with GCC Clause 39, excluding the performance of the suspended obligations from the Contract. If the Employer fails to do so within such period, the Contractor may, by a further notice to the Project Manager, elect to treat the suspension, where it affects a part only of the Facilities, as a deletion of such part in accordance with GCC Clause 39 or, where it affects the whole of the Facilities, as termination of the Contract under GCC Sub-Clause 42.1. 41.2 If (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GCC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, or fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice or (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas in accordance with GCC Sub-Clause 10.2, or failure to obtain any governmental permit necessary for the execution and/or completion of the Facilities, then the Contractor may by fourteen (14) days’ notice to the Employer suspend performance of all or any of its obligations under the Contract, or reduce the rate of progress. 41.3 If the Contractor’s performance of its obligations is suspended or the rate of progress is reduced pursuant to this GCC Clause 41, then the Time for Completion shall be extended in accordance with GCC Sub-Clause 40.1, and any and all additional costs or expenses incurred by the Contractor as a result of such suspension or reduction shall be paid by the Employer to the Contractor in addition to the Contract Price, except in the case of suspension order or reduction in the rate of progress by reason of the Contractor’s default or breach of the Contract. 41.4 During the period of suspension, the Contractor shall not remove from the Site any Plant and Equipment, any part of the Facilities or any Contractor’s Equipment, without the prior written consent of the Employer. |
| 42. Termination | 42.1 Termination for Employer’s Convenience 42.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 42.1. 42.1.2 Upon receipt of the notice of termination under GCC Sub-Clause 42.1.1, the Contractor shall either immediately or upon the date specified in the notice of termination (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) below (c) remove all Contractor’s Equipment from the Site, repatriate the Contractor’s and its Subcontractors’ personnel from the Site, remove from the Site any wreckage, rubbish and debris of any kind, and leave the whole of the Site in a clean and safe condition (d) In addition, the Contractor, subject to the payment specified in GCC Sub-Clause 42.1.3, shall (i) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors (iii) deliver to the Employer all non-proprietary drawings, specifications and other documents prepared by the Contractor or its Subcontractors as at the date of termination in connection with the Facilities. 42.1.3 In the event of termination of the Contract under GCC Sub-Clause 42.1.1, the Employer shall pay to the Contractor the following amounts: (a) the Contract Price, properly attributable to the parts of the Facilities executed by the Contractor as of the date of termination (b) the costs reasonably incurred by the Contractor in the removal of the Contractor’s Equipment from the Site and in the repatriation of the Contractor’s and its Subcontractors’ personnel (c) any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges (d) costs incurred by the Contractor in protecting the Facilities and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 42.1.2 (e) the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (d) above. 42.2 Termination for Contractor’s Default 42.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GCC Sub-Clause 42.2: (a) if the Contractor becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Contractor is a corporation, a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Contractor takes or suffers any other analogous action in consequence of debt (b) if the Contractor assigns or transfers the Contract or any right or interest therein in violation of the provision of GCC Clause 43. (c) if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract. For the purpose of this Sub-Clause: “corrupt practice” means the offering, giving, receiving or soliciting of any thing of value to influence the action of a public official in the procurement process or in contract execution. “fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Employer, and includes collusive practice among bidders (prior to or after bid submission) designed to establish bid prices at artificial non-competitive levels and to deprive the Employer of the benefits of free and open competition. “collusive practice” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Borrower, designed to establish bid prices at artificial, non competitive levels; and; “coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in the procurement process or affect the execution of a contract 42.2.2 If the Contractor (a) has abandoned or repudiated the Contract (b) has without valid reason failed to commence work on the Facilities promptly or has suspended (other than pursuant to GCC Sub-Clause 41.2) the progress of Contract performance for more than twenty-eight (28) days after receiving a written instruction from the Employer to proceed (c) persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause (d) refuses or is unable to provide sufficient materials, services or labor to execute and complete the Facilities in the manner specified in the program furnished under GCC Sub-Clause 18.2 at rates of progress that give reasonable assurance to the Employer that the Contractor can attain Completion of the Facilities by the Time for Completion as extended, then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GCC Sub-Clause 42.2. 42.2.3 Upon receipt of the notice of termination under GCC Sub-Clauses 42.2.1 or 42.2.2, the Contractor shall, either immediately or upon such date as is specified in the notice of termination, (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) below (c) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination (d) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors (e) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Facilities. 42.2.4 The Employer may enter upon the Site, expel the Contractor, and complete the Facilities itself or by employing any third party. The Employer may, to the exclusion of any right of the Contractor over the same, take over and use with the payment of a fair rental rate to the Contractor, with all the maintenance costs to the account of the Employer and with an indemnification by the Employer for all liability including damage or injury to persons arising out of the Employer’s use of such equipment, any Contractor’s Equipment owned by the Contractor and on the Site in connection with the Facilities for such reasonable period as the Employer considers expedient for the supply and installation of the Facilities. Upon completion of the Facilities or at such earlier date as the Employer thinks appropriate, the Employer shall give notice to the Contractor that such Contractor’s Equipment will be returned to the Contractor at or near the Site and shall return such Contractor’s Equipment to the Contractor in accordance with such notice. The Contractor shall thereafter without delay and at its cost remove or arrange removal of the same from the Site. 42.2.5 Subject to GCC Sub-Clause 42.2.6, the Contractor shall be entitled to be paid the Contract Price attributable to the Facilities executed as of the date of termination, the value of any unused or partially used Plant and Equipment on the Site, and the costs, if any, incurred in protecting the Facilities and in leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 42.2.3. Any sums due the Employer from the Contractor accruing prior to the date of termination shall be deducted from the amount to be paid to the Contractor under this Contract. 42.2.6 If the Employer completes the Facilities, the cost of completing the Facilities by the Employer shall be determined. If the sum that the Contractor is entitled to be paid, pursuant to GCC Sub-Clause 42.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GCC Sub-Clause 42.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GCC Sub-Clause 42.2.5, the Employer shall pay the balance to the Contractor. The Employer and the Contractor shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. 42.3 Termination by Contractor 42.3.1 If (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the corresponding Appendix (Terms and Procedures of Payment) of the Contract Agreement, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GCC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice, or (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas or failure to obtain any governmental permit necessary for the execution and/or completion of the Facilities, then the Contractor may give a notice to the Employer thereof, and if the Employer has failed to pay the outstanding sum, to approve the invoice or supporting documents, to give its reasons for withholding such approval, or to remedy the breach within twenty-eight (28) days of such notice, or if the Contractor is still unable to carry out any of its obligations under the Contract for any reason attributable to the Employer within twenty-eight (28) days of the said notice, the Contractor may by a further notice to the Employer referring to this GCC Sub-Clause 42.3.1, forthwith terminate the Contract. 42.3.2 The Contractor may terminate the Contract forthwith by giving a notice to the Employer to that effect, referring to this GCC Sub-Clause 42.3.2, if the Employer becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, being a corporation, if a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Employer takes or suffers any other analogous action in consequence of debt. 42.3.3 If the Contract is terminated under GCC Sub-Clauses 42.3.1 or 42.3.2, then the Contractor shall immediately (a) cease all further work, except for such work as may be necessary for the purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) (c) remove all Contractor’s Equipment from the Site and repatriate the Contractor’s and its Subcontractors’ personnel from the Site. (d) In addition, the Contractor, subject to the payment specified in GCC Sub-Clause 42.3.4, shall (i) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors (iii) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Facilities. 42.3.4 If the Contract is terminated under GCC Sub-Clauses 42.3.1 or 42.3.2, the Employer shall pay to the Contractor all payments specified in GCC Sub-Clause 42.1.3, and reasonable compensation for all loss, except for loss of profit, or damage sustained by the Contractor arising out of, in connection with or in consequence of such termination. 42.3.5 Termination by the Contractor pursuant to this GCC Sub-Clause 42.3 is without prejudice to any other rights or remedies of the Contractor that may be exercised in lieu of or in addition to rights conferred by GCC Sub-Clause 42.3. 42.4 In this GCC Clause 42, the expression “Facilities executed” shall include all work executed, Installation Services provided, and all Plant and Equipment acquired (or subject to a legally binding obligation to purchase) by the Contractor and used or intended to be used for the purpose of the Facilities, up to and including the date of termination. 42.5 In this GCC Clause 42, in calculating any monies due from the Employer to the Contractor, account shall be taken of any sum previously paid by the Employer to the Contractor under the Contract, including any advance payment paid pursuant to the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement. |
| 43. Assignment | 43.1 Neither the Employer nor the Contractor shall, without the express prior written consent of the other party (which consent shall not be unreasonably withheld), assign to any third party the Contract or any part thereof, or any right, benefit, obligation or interest therein or thereunder, except that the Contractor shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract. |
| 44. Export Restriction | 44.1 Notwithstanding any obligation under the Contract to complete all export formalities, any export restrictions attributable to the Purchaser, to the country of the Purchaser, or to the use of the products/goods, systems or services to be supplied, which arise from trade regulations from a country supplying those products/goods, systems or services, and which substantially impede the Supplier from meeting its obligations under the Contract, shall release the Supplier from the obligation to provide deliveries or services, always provided, however, that the Supplier can demonstrate to the satisfaction of the Purchaser and of the Bank that it has completed all formalities in a timely manner, including applying for permits, authorizations and licenses necessary for the export of the products/goods, systems or services under the terms of the Contract. Termination of the Contract under this basis shall be for the Employer’s convenience pursuant to Sub-Clause 42.1. |

# Section V. Special Conditions of Contract

## Notes on the Special Conditions of Contract The provisions of Section V complement the General Conditions of Contract included in Section IV, specifying contractual requirements linked to the special circumstances of the Employer, the Employer’s country, the sector, and the facilities installed.

Special Conditions of Contract

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC). Whenever there is a conflict, the provisions herein shall prevail over those in the GCC. The corresponding clause number of the GCC is indicated in parentheses.

| GCC 1.1 (a) | The Arbitrator is: [Name, address, and telephone, cable and facsimile numbers] |
| --- | --- |
| GCC 1.1 (g) | The Contractor is: [Name, address, and telephone, cable and facsimile numbers] |
| GCC 1.1 (i) | The Contractor’s Representative is: [Name, address, and telephone, cable and facsimile numbers] |
| GCC 1.1 (j) | Country of Origin: all countries and territories as indicated in the section of the bidding documents, Eligibility for the Provision of Goods, Works and Services. |
| GCC 1.1 (n) | The Employer is: ZESCO Limited |
| GCC 1.1 (w) | The Project Manager is: Name: Senior Manager Transmission Projects, Address: ZESCO Limited, P.O. Box 33304, Telephone: +260 211 362369, Facsimile: +260 211 223971, |
| GCC 1.1 (aa) | Time for Completion for all Facilities: Thirty (30) calendar months. |
| GCC 3.1.1 | Ruling language shall be: English |
| GCC 3.1.2 | Language for communications shall be: English |
| GCC 4.1 | For notices, the Employer’s address shall be: Attention: [ insert full name of person, if applicable] Street Address: [insert street address and number] Floor/ Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal ZIP code, if applicable] Country: [insert name of country] Telephone: [include telephone number, including country and city codes] Facsimile number: [insert facsimile number, including country and city codes] Electronic mail address: [insert e-mail address, if applicable] Contractor’s address for notice purposes: Attention: [ insert full name of person, if applicable] Street Address: [insert street address and number] Floor/ Room number: [insert floor and room number, if applicable] City: [insert name of city or town] ZIP Code: [insert postal ZIP code, if applicable] Country: [insert name of country] Telephone: [include telephone number, including country and city codes] Facsimile number: [insert facsimile number, including country and city codes] Electronic mail address: [insert e-mail address, if applicable] |
| GCC 5.1 | The law that applies to the Contract is the law of Government of the Republic of Zambia. |
| GCC 6.1.3 | Arbitrator’s hourly fee: [The fee shall be specified in a convertible currency.] |
| GCC 6.1.4 | Appointing Authority for Arbitrator: [The Appointing Authority should be an impartial organization recognized in the sector.] |
| GCC 6.2.3 | The Parties shall use their best efforts to amicably settle all disputes, differences and questions whatsoever which may at any time hereafter arise between the parties hereto out of the construction of or concerning anything contained in or arising out of this Contract through good faith, discussion, consultation and negotiation. If after twenty eight (28) days, the parties have failed to resolve their dispute or difference by such mutual consultation, then either party may give notice to the other party of its intention to commence arbitration, as hereinafter provided, as to the matter in dispute, and no arbitration in respect of this matter may be commenced unless such notice is given. Any dispute or difference in respect of which notice of intention to commence arbitration has been given in accordance with this clause shall finally be settled by arbitration in accordance with the Arbitration Act No. 19 of 2000 and as may be amended from time to time). The seat of the Arbitration shall be Lusaka, Zambia and the language of Arbitration shall be English. The Arbitrator shall be selected by the parties to the contract in conjunction with the Chartered Institute of Arbitrators (Zambian Branch), Zambia Association of Arbitrators or Zambia Centre for Dispute Resolution. Notwithstanding any reference to arbitration herein, the parties shall continue to perform their respective obligations under the Contract unless they otherwise agree. |
| GCC 7.3 | The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. Other spare parts and components shall be supplied as promptly as possible, but at the most within six (6) months of placing the order and opening the letter of credit. In addition, in the event of termination of the production of spare parts, advance notification will be made to the Employer of the pending termination, with sufficient time to permit the Employer to procure the needed requirement. Following such termination, the Contractor will furnish to the extent possible and at no cost to the Employer the blueprints, drawings and specifications of the spare parts, if requested. |
| GCC 8.1 | The Contractor shall commence work on the Facilities from the Effective Date for determining Time for Completion as specified in the Contract Agreement. |
| GCC 8.2 | The Completion of the Facilities shall be attained within Thirty (30) calendar months |
| GCC 11.2 | The Contract is not subject to price adjustment. |
| GCC 13.3.1 | A Performance Security shall be required within 14 days of signing the contract. The amount of performance security, as a percentage of the Contract Price, shall be 10 (ten) percent of the contract price. |
| GCC 13.3.2 | The performance security shall be in the form of the attached hereto in the section on Sample Forms and Procedures. |
| GCC 13.3.3 | The performance security shall be reduced to ten percent (10%) of the value of the component covered by the extended warranty to cover the Contractor’s extended warranty in accordance with the provision in the SCC, pursuant to GCC Sub-Clause 27.10. |
| GCC 18.2 | The form of the program of performance of the Contract shall be in the form of the critical path method (CPM), the PERT network, or other internationally used programs. The period between Program updates is fourteen (14) days. The amount to be withheld for late submission of an updated Program is to be agreed. |
| GCC 25.2.2 | The Guarantee Test of the Facilities shall be successfully completed within ______ [days or weeks, written in words and figures] from the date of Completion. [Parts and separate times for the respective Guarantee Tests shall be specified where applicable.] |
| GCC 26.2 | Applicable rate for liquidated damages: The liquidated damages for the whole of the Works are 0.05 percent per day. The maximum amount of liquidated damages for the whole of the Works is ten (10) percent of the final Contract Price. The above rate and maximum apply to the price of the part of the Facilities, as quoted in the Price Schedule, for that part for which the Contractor fails to achieve Completion within the particular Time for Completion. |
| GCC 26.3 | No bonus will be given for earlier Completion of the Facilities or part thereof. |
| GCC 27.10 | The Defects Liability Period is: 24 Months on the Substation, Line and Equipment. |
| GCC Clauses 24.3 and 25.2 | 1. In the event that the Contractor is unable to proceed with the Precommissioning of the Facilities pursuant to Sub-Clause 24.3, or with the Guarantee Test pursuant to Sub-Clause 25.2, for reasons attributable to the Employer either on account of nonavailability of other facilities under the responsibilities of other contractor(s), or for reasons beyond the Employer’s control, the provisions leading to “deemed” completion of activities such as Completion, pursuant to GCC Sub-Clause 24.6, and Operational Acceptance, pursuant to GCC Sub-Clause 25.3.4, and Contractor’s obligations regarding Defect Liability Period, pursuant to GCC Sub-Clause 27.2, Functional Guarantee, pursuant to GCC Clause 28, and Care of Facilities, pursuant to GCC Clause 32, and GCC Clause 41.1, Suspension, shall not apply. In this case, the following provisions shall apply. 2. When the Contractor is notified by the Project Manager that he will be unable to proceed with the activities and obligations pursuant to above para. 1, the Contractor shall be entitled to the following: (a) the Time of Completion shall be extended for the period of suspension without imposition of liquidated damages pursuant to GCC Sub-Clause 26.2; (b) payments due to the Contractor in accordance with the provision specified in the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement, which would not have been payable in normal circumstances due to non-completion of the subject activities, shall be released to the Contractor against submission of a security in the form of a bank guarantee of equivalent amount acceptable to the Employer, and which shall become null and void when the Contractor will have complied with its obligations regarding those payments, subject to the provision of para.3 below; (c) the expenses towards the above security and extension of other securities under the contract, of which validity needs to be extended, shall be reimbursed to the Contractor by the Employer; (d) the additional charges towards the care of the Facilities pursuant to GCC Sub-Clause 32.1 shall be reimbursed to the Contractor by the Employer for the period between the notification mentioned above and the notification mentioned in para.4 below. The provision of GCC Sub-Clause 33.2 shall apply to the Facilities during the same period. 3. In the event that the period of suspension under above para.1 actually exceeds one hundred eighty (180) days, the Employer and Contractor shall mutually agree to any additional compensation payable to the Contractor. 4. When the Contractor is notified by the Project Manager that the plant is ready for Precommissioning, the Contractor shall proceed without delay in performing all the specified activities and obligations under the contract. |

# Section VI. Technical Specifications and Drawings

## Notes on Preparing the Technical Specifications and Drawings The technical Specifications and Drawings are provided in separate Parts of the Bidding Documents

# Section VII. Sample Forms and Procedures

## Notes on the Sample Forms and Procedures The Bidder shall complete and submit with its bid the Bid Form and Price Schedules, in accordance with the requirements included in the bidding documents. There are two different Bid Forms included herein, depending on whether Option A—Single Stage Bidding, or Option B—Two Stage Bidding, is to be used. The latter consists of a Bid Form for the First Stage Bid and a Bid Form for the Second Stage Bid. These forms shall be included unamended for the Bidder to complete, sign and submit with the Bid. The price breakdown given in the sample Price Schedules is the breakdown required for application of the domestic preference. Employers are free to choose whether they fill in the Item/Description details prior to issuing the bidding documents (desirable when the Facilities and Installation Services to be executed can be easily identified and defined), or whether bidders are required to fill in Item/Description details (may be more suitable when details are not easily identifiable). The Bidder shall provide the Bid Security, either in the form included hereafter or in another form acceptable to the Employer, pursuant to the provisions in the Instructions to Bidders. The Form of Contract Agreement shall be used unamended, except for the need to complete Article 1.1 (Contract Documents) and Article 3 (Effective Date), as appropriate. The form shall also include the Appendixes listed, as required, which should be completed according to the instructions for their completion provided at the beginning of each Appendix. If required, the Price Schedule deemed to form part of the Contract should be modified according to any corrections or modifications to the accepted bid resulting from price corrections, pursuant to the provisions of the Instructions to Bidders. The Performance Security and Bank Guarantee for Advance Payment forms should not be completed by the bidders at the time of their bid preparation. The Employer shall include in the bidding documents the type of performance security form (unconditional or conditional) that it has selected, pursuant to GCC Sub-Clause 13.2.2. Only the successful Bidder will be required to provide performance security and a bank guarantee for advance payment, according to one of the forms indicated herein or in another form acceptable to the Employer and pursuant to the provisions of the General and Special Conditions of Contract, respectively. Recommended Sample Forms for Completion and Operational Acceptance are included herein, together with Change Order Procedures and Forms that complement the provisions in Part H of the General Conditions of Contract. Unless the Employer has good reason to require different procedures for those recommended, or to require different wording in the certificates, the procedures and forms shall be included unamended. If the Employer wishes to amend the recommended procedures and/or certificates, it may propose alternatives for the approval of the Bank before incorporation in the bidding documents.

Table of Sample Forms and Procedures

1. Bid Forms and Price Schedules	175

2. Form of Bid Security (Bank Guarantee)	178

4. Manufacturer’s Authorisation	179

6.  Form of Contract Agreement	180

6. Performance Security Forms1F1F1F	198

7. Bank Guarantee Form for Advance Payment	200

8. Form of Completion Certificate	202

9. Form of Operational Acceptance Certificate	203

10. Change Order Procedures	204

### 1. Bid Forms and Price Schedules

Date:

IFB No:

[Name of Contract]

To: [Name and address of Employer]

Ladies and/or Gentlemen,

Having examined the bidding documents, including Addendum Nos. [insert numbers], the receipt of which is hereby acknowledged, we, the undersigned, offer to design, manufacture, test, deliver, install, precommission and commission the Facilities under the above-named Contract in full conformity with the said bidding documents for the sum of: [amount of foreign currency in words], [amount in figures], and [amount of local currency in words], [amount in figures] or such other sums as may be determined in accordance with the terms and conditions of the Contract. The above amounts are in accordance with the Price Schedules attached herewith and are made part of this bid.

We undertake, if our bid is accepted, to commence the Facilities and to achieve Completion within the respective times stated in the bidding documents.

If our bid is accepted, we undertake to provide an advance payment security and a performance security in the form, in the amounts, and within the times specified in the bidding documents.

We accept the appointment of [name proposed in Bid Data Sheet] as the Arbitrator.

or

We do not accept the appointment of [name proposed in Bid Data Sheet] as the Arbitrator, and we propose instead that [name] be appointed as Arbitrator, whose résumé and hourly fees are attached.

We agree to abide by this bid, which consists of this letter and Attachments 1 through [number] hereto, for a period of [number] days from the date fixed for submission of bids as stipulated in the bidding documents, and it shall remain binding upon us and may be accepted by you at any time before the expiration of that period.

Commissions or gratuities, if any, paid or to be paid by us to agents relating to this Bid, and to contract execution if we are awarded the contract, are listed below

| Name and address of agent |  | Amount and Currency |  | Purpose of Commission or gratuity |
| --- | --- | --- | --- | --- |
| (if none, state “none”). |  |  |  |  |

Until a formal contract is prepared and executed between us, this bid, together with your written acceptance thereof and your notification of award, shall constitute a binding contract between us.

We understand that you are not bound to accept the lowest or any bid you may receive.

Dated this 	 day of 	, 19

[signature]

In the capacity of

[position]

Duly authorized to sign this bid for and on behalf of

[name of Bidder]

Attachments: [In accordance with ITB Sub-Clause 9.3, plus any additional attachment either specified by the Employer in the Bid Data Sheet or included by the Bidder. In this regard, the Employer may include in the bidding document, as an Attachment to the Bid Form, a list of “Bidding Data,” including the most important data to be provided by the Bidder (e.g., Time for Completion, Functional Guarantees, etc.).]

1.4 Price Schedules

The Price Schedules are contained in Part 4 of the Bidding Documents.

### 2. Form of Bid Security (Bank Guarantee)

________________________________
[Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	___________________ [Name and Address of Employer]

Date:	________________

BID GUARANTEE No.:	_________________

We have been informed that [name of the Bidder] (hereinafter called "the Bidder") has submitted to you its bid dated (hereinafter called “the Bid”) for the execution of [name of contract] under Invitation for Bids No. [IFB number] (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] ([amount in words]) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a) 	has withdrawn its Bid during the period of bid validity specified by the Bidder in the Form of Bid; or

(b) 	having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Form, if required, or (ii) fails or refuses to furnish the performance security, in accordance with the Instructions  to Bidders.

This guarantee will expire: (a) if the Bidder is the successful bidder, upon our receipt of copies of the contract signed by the Bidder and the performance security issued to you upon the instruction of the Bidder; or (b) if the Bidder is not the successful bidder, upon the earlier of (i) our receipt of a copy of your notification to the Bidder of the name of the successful bidder; or (ii) twenty-eight days after the expiration of the Bidder’s Bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

_____________________________

[signature(s)]

### 3. Manufacturer’s Authorisation

Date: __________________

ICB No.: _________________

To:  ________________________

WHEREAS

We ___________________, who are official manufacturers of ____________________, having factories at _____________________, do hereby authorize ______________________ to submit a bid the purpose of which is to provide the following goods, manufactured by us _______________________, and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27 of the General Conditions, with respect to the goods offered by the above firm.

Signed: _______________________________________

Name: ______________________________________

Title:______________________________________

Duly authorized to sign this Authorization on behalf of: ______________________________________

Dated on ____________ day of __________________, _______

### 4.  Form of Contract Agreement

THIS CONTRACT AGREEMENT is made the 	 day of 	, 19	.

BETWEEN

(1) [Name of Employer], a corporation incorporated under the laws of [country of Employer] and having its principal place of business at [address of Employer] (hereinafter called “the Employer”), and (2) [name of Contractor], a corporation incorporated under the laws of [country of Contractor] and having its principal place of business at [address of Contractor] (hereinafter called “the Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver, install, complete and commission certain Facilities, viz. [list of facilities] (“the Facilities”) and the Contractor have agreed to such engagement upon and subject to the terms and conditions hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

| Article 1. Contract Documents | 1.1 Contract Documents (Reference GCC Clause 2) The following documents shall constitute the Contract between the Employer and the Contractor, and each shall be read and construed as an integral part of the Contract: (a) This Contract Agreement and the Appendixes hereto (b) Bid and Price Schedules submitted by the Contractor (c) Special Conditions of Contract (d) General Conditions of Contract (e) Technical Specifications and Drawings (f) Procedures (as listed) (g) Any other documents shall be added here 1.2 Order of Precedence (Reference GCC Clause 2) In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above. 1.3 Definitions (Reference GCC Clause 1) Capitalized words and phrases used herein shall have the same meanings as are ascribed to them in the General Conditions of Contract. |
| --- | --- |
| Article 2. Contract Price and Terms of Payment | 2.1 Contract Price (Reference GCC Clause 11) The Employer hereby agrees to pay to the Contractor the Contract Price in consideration of the performance by the Contractor of its obligations hereunder. The Contract Price shall be the aggregate of: [amount of foreign currency in words], [amount in figures] as specified in Price Schedule No. 5 (Grand Summary), and [amount of local currency in words], [amount in figures], or such other sums as may be determined in accordance with the terms and conditions of the Contract. 2.2 Terms of Payment (Reference GCC Clause 12) The terms and procedures of payment according to which the Employer will reimburse the Contractor are given in the corresponding Appendix (Terms and Procedures of Payment) hereto. The Employer shall instruct its bank to issue an irrevocable confirmed documentary credit made available to the Contractor in a bank in the country of the Contractor. The credit shall be for an amount of [insert an amount equal to the total named in Schedule 1 less the advance payment to be made for Plant and Equipment supplied from abroad]; and shall be subject to the Uniform Customs and Practice for Documentary Credits 1993 Revision, ICC Publication No. 500. In the event that the amount payable under Schedule No. 1 is adjusted in accordance with GCC 11.2 or with any of the other terms of the Contract, the Employer shall arrange for the documentary credit to be amended accordingly. [The Employer may want to insert a similar provision for the payment of the items listed in Schedule 2.] |
| Article 3. Effective Date for Determining Time for Completion | 3.1 Effective Date (Reference GCC Clause 1) The Time of Completion of the Facilities shall be determined from the date when all of the following conditions have been fulfilled: (a) This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor; (b) The Contractor has submitted to the Employer the performance security and the advance payment guarantee; (c) The Employer has paid the Contractor the advance payment (d) The Contractor has been advised that the documentary credit referred to in Article 2.2 above has been issued in its favor. (d) The finance agreement for the project has been duly signed and is effective Each party shall use its best efforts to fulfill the above conditions for which it is responsible as soon as practicable. 3.2 If the conditions listed under 3.1 are not fulfilled within six (06) months from the date of this Contract notification, then the contract shall automatically lapse unless both Parties have agreed in writing to extend the period. |
| Article 4. Appendixes | 4.1 The Appendixes listed in the attached List of Appendixes shall be deemed to form an integral part of this Contract Agreement. 4.2 Reference in the Contract to any Appendix shall mean the Appendixes attached hereto, and the Contract shall be read and construed accordingly. |

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

Signed for and on behalf of THE PURCHASER:…………………………………

NAME:

CAPACITY: MANAGING DIRECTOR

In the presence of:

NAME:……………………………………………………………………………………

DESIGNATION:………………………………………………………………………

ADDRESS:………………………………………………………………………………

OCCUPATION:…………………………………………………………………………

Signed for and on behalf of THE SUPPLIER:………………………………

NAME:

CAPACITY:

In the presence of:

NAME:……………………………………………………………………………………

DESIGNATION:………………………………………………………………………

ADDRESS:………………………………………………………………………………

OCCUPATION:…………………………………………………………………………

APPENDIXES

Appendix 1	Terms and Procedures of Payment

Appendix 2	Price Adjustment

Appendix 3	Insurance Requirements

Appendix 4	Time Schedule

Appendix 5	List of Approved Subcontractors

Appendix 6	Scope of Works and Supply by the Employer

Appendix 7	List of Documents for Approval or Review

Appendix 8	Functional Guarantees

Appendix 1. Terms and Procedures of Payment

In accordance with the provisions of GCC Clause 12 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on Price Schedules. Payments will be made in the currencies quoted by the Bidder. Applications for payment in respect of part deliveries may be made by the Contractor as work proceeds.

TERMS OF PAYMENT

Schedule No. 1. Plant and Equipment Supplied from Abroad for Substations and Transmission Lines

In respect of plant and equipment supplied from abroad, the following payments shall be made:

- Fifteen percent (15%) of the total DDP amount as an advance payment shall be paid via Telegraphic Transfer (TT) against receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and equipment delivered to the site, as evidenced by shipping and delivery documents;

- Fifty percent (50%) of the total or pro rata DDP amount shall be paid via Telegraphic Transfer (TT) upon Shipment of the consignment within forty-five (45) days after receipt of Letter of Claim, invoice and Shipping documents, [such as a negotiable bill of lading, a non-neegotiable sea way bill, an airway bill, a railway consignment note, a road consignment note, insurance certificate, Certificate of Origin, Packaging List etc.];

- Twenty Five percent (25%) of the total or pro rata DDP amount shall be paid via Telegraphic Transfer (TT) upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice; and

- 10% of contract value for Schedule No. 1 shall be retained as retention of which 5% of the retention shall be paid via Telegraphic Transfer (TT) after 6 months within the defect liability period, while the remaining 5% shall be paid after the defects Liability period.

Schedule No. 2. Plant and Equipment Supplied from within the Employer’s Country for Substations and Transmission Lines

In respect of plant and equipment supplied from within the Employer’s country, the following payments shall be made:

Fifteen percent (15%) of the total DDP amount as an advance payment shall be paid via Telegraphic Transfer (TT) against receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and equipment delivered to the site, as evidenced by shipping and delivery documents.

Fifty percent (50%) of the total or pro rata DDP amount shall be paid via Telegraphic Transfer (TT) upon shipment of the consignment within forty-five (45) days after receipt of Letter of Claim, invoice and shipment documents, such as railway consignment note, a road consignment note, insurance certificate, Certificate of Origin and Packaging List etc.].

- Twenty Five percent (25%) of the total or pro rata DDP amount shall be paid via Telegraphic Transfer (TT) upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice; and

- 10% of contract value for Schedule No. 2 shall be retained as retention of which 5% of the retention shall be paid via Telegraphic Transfer (TT) after 6 months within the defect liability period, while the remaining 5% shall be paid after the defects Liability period.

Schedule No. 3. Local Transportation for Substations and Transmission Lines

In respect of local transportation for both the foreign currency (where applicable) and the local currency portions, the following payments shall be made:

Fifteen percent (15%) of the total DDP amount as an advance payment shall be paid via Telegraphic Transfer (TT) against receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the Plant and Equipment delivered to the site, as evidenced by shipping and delivery documents.

Eighty - Five percent (85%) of the total or pro rata local transportation amount shall be paid via Telegraphic Transfer (TT) upon delivery to the site within forty-five (45) days after receipt of invoice.

Schedule No. 4. Installation Services for Substations and Transmission Lines

In respect of installation services for both the foreign and local currency portions, the following payments shall be made:

Fifteen percent (15%) of the total DDP amount as an advance payment shall be paid via Telegraphic Transfer (TT) against receipt of invoice, and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of work performed by the Contractor as evidenced by the invoices for installation services.

Seventy Five percent (75%) percent of the measured value of work performed by the Contractor, as identified in the said Program of Performance, during the preceding month, as evidenced by the Employer’s authorization of the Contractor’s application, shall be paid via Telegraphic Transfer (TT) monthly within forty-five (45) days after receipt of invoice.

- 10% of contract value for Schedule No. 2 shall be retained as retention of which 5% of the retention shall be paid via Telegraphic Transfer (TT) after 6 months within the defect liability period, while the remaining 5% shall be paid after the defects Liability period.

In the event that the Employer fails to make any payment on its respective due date, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate of Libor plus one  percent (1%) per month for period of delay until payment has been made in full.

PAYMENT PROCEDURES

The procedures to be followed in applying for certification and making payments shall be as follows:

  - Contractor Submits Invoices;

  - Employers reviews, certifies and approves;

  - Utilization request raised to the Financier with all the necessary supporting documents;

  - Financier pays the contractor directly; and

  - Notice sent to the employer.

Appendix 2. Price Adjustment

The prices are to remain firm and fixed for the duration of the Contract.

Appendix 3. Insurance Requirements

Details to be completed by the Employer prior to issuing the bidding documents. In the event that the Employer provides any insurances under the Contract, appropriate details must also be given.

Insurances To Be Taken Out By The Contractor

In accordance with the provisions of GCC Clause 34, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, such approval not to be unreasonably withheld.

(a)	Cargo Insurance

Covering loss or damage occurring, while in transit from the supplier’s or manufacturer’s works or stores until arrival at the Site, to the Facilities (including spare parts therefor) and to the construction equipment to be provided by the Contractor or its Subcontractors.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| 110% CIP | US$5,000 | Contractor | Works/Stores | Site |

(b)	Installation All Risks Insurance

Covering physical loss or damage to the Facilities at the Site, occurring prior to completion of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the defect liability period while the Contractor is on the Site for the purpose of performing its obligations during the defect liability period.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| Contract Amount | US$5,000 | ZESCO and Contractor | Start of the installation | completion of the Facilities |

(c)	Third Party Liability Insurance

Covering bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities that have been accepted by the Employer) occurring in connection with the supply and installation of the Facilities.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| US$5 million | US$5,000 | Contractor | Start of the installation | completion of the Facilities |

(d)	Automobile Liability Insurance

Covering use of all vehicles used by the Contractor or its Subcontractors (whether or not owned by them) in connection with the supply and installation of the Facilities. Comprehensive insurance in accordance with statutory requirements.

Required per the laws and regulations of Zambia.

(e)	Workers’ Compensation

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

(f)	Employer’s Liability

At US$ 100 000=00 any one accident.

(g)	Other Insurances

The Contractor is also required to take out and maintain at its own cost the following insurances:

Details:

Amount	Deductible limits	Parties insured	From	To

[in currency(ies)]	[names]	[place]	[place]

The Employer shall be named as co-insured under all insurance policies taken out by the Contractor, except for the Third Party Liability, Workers’ Compensation and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor, except for the Cargo, Workers’ Compensation and Employer’s Liability Insurances. All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies

Insurances To Be Taken Out By The Employer

Not Applicable

Appendix 4. Time Schedule

The Employer should normally provide a Time Schedule to be followed by the Contractor during the performance of the Contract. This schedule should be provided with the bidding documents under this Appendix. All completion times indicated must be in accordance with the information regarding Time(s) for Completion given in the Bid Data Sheet. Except under exceptional circumstances, the Time Schedule should indicate periods of time (e.g., weeks or months) and not specify calendar dates. All periods should be shown from the Effective Date of the Contract. Should it become necessary to amend the Time Schedule to reflect any agreements made with the selected Bidder prior to award of Contract, the amended Time Schedule shall replace the original Time Schedule prior to signature of the Contract Agreement. If the bidding documents contain no Time Schedule, the Bidder shall be required to submit with its bid a detailed program, normally in the form of a bar chart, showing how and the order in which it intends to perform the Contract and showing the key events requiring action or decision by the Employer. In preparing this Program, the Bidder shall adhere to the Time(s) for Completion given in the Bid Data Sheet or give its reasons for not adhering thereto. The Time Schedule submitted by the selected Bidder and amended as necessary prior to award of Contract shall be included as Appendix to the Contract Agreement before the Contract is signed. If bidders, pursuant to the provisions of the Instructions to Bidders, are to be permitted to offer an Alternative Bid based on a different Time Schedule, details of this and any resulting reduction in Price from their conforming bid based on the Time Schedule included in the bidding documents shall be submitted as an Attachment to their bid.

Appendix 5. List of Approved Subcontractors

Prior to award of Contract, the following details shall be completed, indicating those Subcontractors proposed by the Bidder in the corresponding Attachment to its bid that are approved by the Employer for engagement by the Contractor during the performance of the Contract.

The following Subcontractors are approved for carrying out the item of the facilities indicated. Where more than one Subcontractor is listed, the Contractor is free to choose between them, but it must notify the Employer of its choice in good time prior to appointing any selected Subcontractor. In accordance with GCC Sub-Clause 19.1, the Contractor is free to submit proposals for Subcontractors for additional items from time to time. No Subcontracts shall be placed with any such Subcontractors for additional items until the Subcontractors have been approved in writing by the Employer and their names have been added to this list of Approved Subcontractors.

Item of Facilities	Approved Subcontractors	Nationality

Appendix 6. Scope of Works and Supply by the Employer

Prior to issuing the bidding documents, the Employer shall indicate in this Appendix details of all personnel and Facilities it will provide for use by the Contractor and indicate, where applicable, the charges that it will make in respect of their use. The Employer shall also identify any part(s) of the facilities it intends to carry out itself (or by other contractors), and any plant, equipment, or materials that it proposes to purchase itself and supply to the Contractor for incorporation in the facilities, indicating, where applicable, the charges that it will make in respect thereof.

The following personnel, facilities, works and supplies will be provided/supplied by the Employer, and the provisions of GCC Clauses 10, 21 and 24 shall apply as appropriate.

All personnel, facilities, works and supplies will be provided by the Employer in good time so as not to delay the performance of the Contractor, in accordance with the approved Time Schedule and Program of Performance pursuant to GCC Sub-Clause 18.2.

Unless otherwise indicated, all personnel, facilities, works and supplies will be provided free of charge to the Contractor.

Personnel	Charge to Contractor (if any)

Facilities	Charge to Contractor (if any)

Works	Charge to Contractor (if any)

Supplies	Charge to Contractor (if any)

Appendix 7. List of Documents for Approval or Review

Pursuant to GCC Sub-Clause 20.3.1, the Contractor shall prepare, or cause its Subcontractor to prepare, and present to the Project Manager in accordance with the requirements of GCC Sub-Clause 18.2 (Program of Performance), the following documents for

A.	Approval

1.

2.

3.

B.	Review

1.

2.

3.

Appendix 8. Functional Guarantees

1.	General

This Appendix sets out

(a)	the functional guarantees referred to in GCC Clause 28 (Functional Guarantees)

(b)	the preconditions to the validity of the functional guarantees, either in production and/or consumption, set forth below

(c)	the minimum level of the functional guarantees

(d)	the formula for calculation of liquidated damages for failure to attain the functional guarantees.

2.	Preconditions

The Contractor gives the functional guarantees (specified herein) for the facilities, subject to the following preconditions being fully satisfied:

[List any conditions for the carrying out of the Guarantee Test referred to in GCC Sub-Clause 25.2.]

3.	Functional Guarantees

Subject to compliance with the foregoing preconditions, the Contractor guarantees as follows:

3.1	Production Capacity

[List here the production capacity that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its bid.]

and/or

3.2	Raw Materials and Utilities Consumption

[List here the guaranteed items of consumption per unit of production (e.g., kg, tons, kcal, kWh, etc.) that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its bid.]

4.	Failure in Guarantees and Liquidated Damages

4.1	Failure to Attain Guaranteed Production Capacity

If the production capacity of the facilities attained in the guarantee test, pursuant to GCC Sub-Clause 25.2, is less than the guaranteed figure specified in para. 3.1 above, but the actual production capacity attained in the guarantee test is not less than the minimum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities, pursuant to GCC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [amount in the contract currency] for every complete one percent (1%) of the deficiency in the production capacity of the Facilities, or at a proportionately reduced rate for any deficiency, or part thereof, of less than a complete one percent (1%).

4.2	Raw Materials and Utilities Consumption in Excess of Guaranteed Level

[To be specified in the appropriate wording for the type of facilities if there are consumption guarantees.]

If the actual measured figure of specified raw materials and utilities consumed per unit (or their average total cost of consumption) exceeds the guaranteed figure specified in para. 3.2 above (or their specified average total cost of consumption), but the actual consumption attained in the guarantee test, pursuant to GCC Sub-Clause 25.2, is not more than the maximum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities pursuant to GCC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [amount in the contract currency] for every complete one percent (1%) of the excess consumption of the Facilities, or part thereof, of less than a complete one percent (1%).

[The rate of liquidated damages specified in paras. 4.1 and 4.2 above shall be at least equivalent to the rate specified in the Bid Data Sheet under ITB Sub-Clause 25.3 (d), in Single Stage bidding, or ITB Sub-Clause 35.3 (c), in Two Stage bidding, for the comparison of functional guarantees provided by the bidders.]

4.3	Minimum Levels

Notwithstanding the provisions of this paragraph, if as a result of the guarantee test(s), the following minimum levels of performance guarantees (and consumption guarantees) are not attained by the Contractor, the Contractor shall at its own cost make good any deficiencies until the Facilities reach any of such minimum performance levels, pursuant to GCC Sub-Clause 28.2:

(a)	production capacity of the Facilities attained in the guarantee test: ninety-five percent (95%) of the guaranteed production capacity (the figures offered by the Contractor in its bid for functional guarantees represents 100%).

and/or

(b)	average total cost of consumption of all the raw materials and utilities of the Facilities: one hundred and five percent (105%) of the guaranteed figures (the figures offered by the Contractor in its bid for functional guarantees represents 100%).

4.4	Limitation of Liability

Subject to para. 4.3 above, the Contractor’s aggregate liability to pay liquidated damages for failure to attain the functional guarantees shall not exceed ______ percent ( ___ %) of the Contract price [the percentage specified shall not exceed ten percent (10%)].

### 6. Performance Security Forms1F1F1F

Bank Guarantee

________________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	[Name and Address of Employer]

Date:	________________

PERFORMANCE GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. [reference number of the contract] dated ____________ with you, for the execution of [name of contract and brief description of Facilities] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] (___) [amount in words]2F2F2F, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall be reduced by half upon our receipt of:

(a) 	a copy of the Operational Acceptance Certificate; or

(b) 	a registered letter from the Contractor (i) attaching a copy of its notice requesting issuance of the Operational Acceptance Certificate and (ii) stating that the project manager has failed to issue such Certificate within the time required or provide in writing justifiable reasons why such Certificate has not been issued, so that Operational Acceptance is deemed to have occurred.

This guarantee shall expire no later than the earlier of:3F3F3F

(a) 	twelve months after our receipt of either (a) or (b) above; or

(b) 	eighteen months after our receipt of:

(i) 	a copy of the Completion Certificate; or

(ii) 	a registered letter from the Contractor, attaching a copy of the notice to the project manager that the Facilities are ready for commissioning, and stating that fourteen days have elapsed from receipt of such notice (or seven days have elapsed if the notice was a repeated notice) and the project manager has failed to issue a Completion Certificate or inform the Contractor in writing of any defects or deficiencies; or

(iii) 	a registered letter from the Contractor stating that no Completion Certificate has been issued but the Employer is making use of the Facilities; or

(c) 	the ____ day of _____, 2___.4F4F4F

Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

_____________________ 
[signature(s)]

### 7. Bank Guarantee Form for Advance Payment

[Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	[Name and Address of Employer]

Date:	________________

ADVANCE PAYMENT GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. [reference number of the contract] dated [date] with you, for the execution of [name of contract and brief description of Facilities] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum [amount in figures] (____) [amount in words] is to be made against an advance payment guarantee.

At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] (____) [amount in words] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than toward the execution of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on his account number ___________ at [name and address of Bank].

The maximum amount of this guarantee shall be progressively reduced in proportion to the value of each part-shipment or part-delivery of plant and equipment to the site, as indicated in copies of the relevant shipping and delivery documents that shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of documentation indicating full repayment by the Contractor of the amount of the advance payment, or on the ___ day of _______, 2___, whichever is earlier.5F5F5F Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 458.

_____________________ 
[signature(s)]

### 8. Form of Completion Certificate

Date:

Loan/Credit No:

IFB No:

[Name of Contract]

To: [Name and address of Contractor]

Dear Ladies and/or Gentlemen,

Pursuant to GCC Clause 24 (Completion of the Facilities) of the General Conditions of the Contract entered into between yourselves and the Employer dated [date], relating to the [brief description of the Facilities], we hereby notify you that the following part(s) of the Facilities was (were) complete on the date specified below, and that, in accordance with the terms of the Contract, the Employer hereby takes over the said part(s) of the Facilities, together with the responsibility for care and custody and the risk of loss thereof on the date mentioned below.

1.	Description of the Facilities or part thereof: [description]

2.	Date of Completion: [date]

However, you are required to complete the outstanding items listed in the attachment hereto as soon as practicable.

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

### 9. Form of Operational Acceptance Certificate

Date:

Loan/Credit No:

IFB No:

[Name of Contract]

To: [Name and address of Contractor]

Dear Ladies and/or Gentlemen,

Pursuant to GCC Sub-Clause 25.3 (Operational Acceptance) of the General Conditions of the Contract entered into between yourselves and the Employer dated [date], relating to the [brief description of the Facilities], we hereby notify you that the Functional Guarantees of the following part(s) of the Facilities were satisfactorily attained on the date specified below.

1.	Description of the Facilities or part thereof: [description]

2.	Date of Operational Acceptance: [date]

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

### 10. Change Order Procedures

Date:

Loan/Credit No:

IFB No:

CONTENTS

1.	General

2.	Change Order Log

3.	References for Changes

ANNEXES

Annex 1	Request for Change Proposal

Annex 2	Estimate for Change Proposal

Annex 3	Acceptance of Estimate

Annex 4	Change Proposal

Annex 5	Change Order

Annex 6	Pending Agreement Change Order

Annex 7	Application for Change Proposal

Change Order Procedure

1.	General

This section provides samples of procedures and forms for implementing changes in the Facilities during the performance of the Contract in accordance with GCC Clause 39 (Change in the Facilities) of the General Conditions of Contract.

2.	Change Order Log

The Contractor shall keep an up-to-date Change Order Log to show the current status of Requests for Change and Changes authorized or pending, as Annex 8. Entries of the Changes in the Change Order Log shall be made to ensure that the log is up-to-date. The Contractor shall attach a copy of the current Change Order Log in the monthly progress report to be submitted to the Employer.

3.	References for Changes

(1)	Request for Change as referred to in GCC Clause 39 shall be serially numbered CR-X-nnn.

(2)	Estimate for Change Proposal as referred to in GCC Clause 39 shall be serially numbered CN-X-nnn.

(3)	Acceptance of Estimate as referred to in GCC Clause 39 shall be serially numbered CA-X-nnn.

(4)	Change Proposal as referred to in GCC Clause 39 shall be serially numbered CP-X-nnn.

(5)	Change Order as referred to in GCC Clause 39 shall be serially numbered CO-X-nnn.

Note:	(a)	Requests for Change issued from the Employer’s Home Office and the Site representatives of the Employer shall have the following respective references:

Home Office	CR-H-nnn

Site	CR-S-nnn

(b)	The above number “nnn” is the same for Request for Change, Estimate for Change Proposal, Acceptance of Estimate, Change Proposal and Change Order.

Annex 1. Request for Change Proposal

(Employer’s Letterhead)

To: [Contractor’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

With reference to the captioned Contract, you are requested to prepare and submit a Change Proposal for the Change noted below in accordance with the following instructions within [number] days of the date of this letter [or on or before (date)].

1.	Title of Change: [Title]

2.	Change Request No./Rev.: [Number]

3.	Originator of Change:	Employer: [Name]

Contractor (by Application for Change Proposal No. [Number]6F6F6F:

4.	Brief Description of Change: [Description]

5.	Facilities and/or Item No. of equipment related to the requested Change: [Description]

6.	Reference drawings and/or technical documents for the request of Change:

Drawing No./Document No.	Description

7.	Detailed conditions or special requirements on the requested Change: [Description]

8.	General Terms and Conditions:

(a)	Please submit your estimate to us showing what effect the requested Change will have on the Contract Price.

(b)	Your estimate shall include your claim for the additional time, if any, for completion of the requested Change.

(c)	If you have any opinion negative to the adoption of the requested Change in connection with the conformability to the other provisions of the Contract or the safety of the Plant or Facilities, please inform us of your opinion in your proposal of revised provisions.

(d)	Any increase or decrease in the work of the Contractor relating to the services of its personnel shall be calculated.

(e)	You shall not proceed with the execution of the work for the requested Change until we have accepted and confirmed the amount and nature in writing.

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 2. Estimate for Change Proposal

(Contractor’s Letterhead)

To: [Employer’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

With reference to your Request for Change Proposal, we are pleased to notify you of the approximate cost of preparing the below-referenced Change Proposal in accordance with GCC Sub-Clause 39.2.1 of the General Conditions of Contract. We acknowledge that your agreement to the cost of preparing the Change Proposal, in accordance with GCC Sub-Clause 39.2.2, is required before estimating the cost for change work.

1.	Title of Change: [Title]

2.	Change Request No./Rev.: [Number]

3.	Brief Description of Change: [Description]

4.	Scheduled Impact of Change: [Description]

5.	Cost for Preparation of Change Proposal: [Cost]7F7F7F

(a)	Engineering	(Amount)

(i)	Engineer		 hrs x 	 rate/hr =

(ii)	Draftsperson		 hrs x 	 rate/hr =

Sub-total		 hrs

Total Engineering Cost

(b)	Other Cost

Total Cost (a) + (b)

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 3. Acceptance of Estimate

(Employer’s Letterhead)

To: [Contractor’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

We hereby accept your Estimate for Change Proposal and agree that you should proceed with the preparation of the Change Proposal.

1.	Title of Change: [Title]

2.	Change Request No./Rev.: [Request number/revision]

3.	Estimate for Change Proposal No./Rev.: [Proposal number/revision]

4.	Acceptance of Estimate No./Rev.: [Estimate number/revision]

5.	Brief Description of Change: [Description]

6.	Other Terms and Conditions: In the event that we decide not to order the Change accepted, you shall be entitled to compensation for the cost of preparation of Change Proposal described in your Estimate for Change Proposal mentioned in para. 3 above in accordance with GCC Clause 39 of the General Conditions of Contract.

(Employer’s Name)

(Signature)

(Name and Title of signatory)

Annex 4. Change Proposal

(Contractor’s Letterhead)

To: [Employer’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

In response to your Request for Change Proposal No. [Number], we hereby submit our proposal as follows:

1.	Title of Change: [Name]

2.	Change Proposal No./Rev.: [Proposal number/revision]

3.	Originator of Change:	Employer: [Name]

Contractor: [Name]

4.	Brief Description of Change: [Description]

5.	Reasons for Change: [Reason]

6.	Facilities and/or Item No. of Equipment related to the requested Change: [Facilities]

7.	Reference drawings and/or technical documents for the requested Change:

Drawing/Document No.	Description

8.	Estimate of increase/decrease to the Contract Price resulting from Change Proposal:8F8F8F

(Amount)

(a)	Direct material

(b)	Major construction equipment

(c)	Direct field labor (Total 	 hrs)

(d)	Subcontracts

(e)	Indirect material and labor

(f)	Site supervision

(g)	Head office technical staff salaries

Process engineer		 hrs @ 	 rate/hr

Project engineer		 hrs @ 	 rate/hr

Equipment engineer		 hrs @ 	 rate/hr

Procurement		 hrs @ 	 rate/hr

Draftsperson		 hrs @ 	 rate/hr

Total		 hrs

(h)	Extraordinary costs (computer, travel, etc.)

(i)	Fee for general administration, 	 % of Items

(j)	Taxes and customs duties

Total lump sum cost of Change Proposal

[Sum of items (a) to (j)]

Cost to prepare Estimate for Change Proposal

[Amount payable if Change is not accepted]

9.	Additional time for Completion required due to Change Proposal

10.	Effect on the Functional Guarantees

11.	Effect on the other terms and conditions of the Contract

12.	Validity of this Proposal: within [Number] days after receipt of this Proposal by the Employer

13.	Other terms and conditions of this Change Proposal:

(a)	You are requested to notify us of your acceptance, comments or rejection of this detailed Change Proposal within [Number] days from your receipt of this Proposal.

(b)	The amount of any increase and/or decrease shall be taken into account in the adjustment of the Contract Price.

(c)	Contractor’s cost for preparation of this Change Proposal:9F9F9F2

(Note) This cost shall be reimbursed by the Employer in case of Employer’s withdrawal or rejection of this Change Proposal without default of the Contractor in accordance with GCC Clause 39 of the General Conditions of Contract.

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 5. Change Order

(Employer’s Letterhead)

To: [Contractor’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

We approve the Change Order for the work specified in the Change Proposal (No. [Number]), and agree to adjust the Contract Price, Time for Completion and/or other conditions of the Contract in accordance with GCC Clause 39 of the General Conditions of Contract.

1.	Title of Change: [Name]

2.	Change Request No./Rev.: [Request number/revision]

3.	Change Order No./Rev.: [Order number/revision]

4.	Originator of Change:	Employer: [Name]

Contractor: [Name]

5.	Authorized Price:

Ref. No.: [Number]	Date: [Date]

Foreign currency portion [Amount] plus Local currency portion [Amount]

6.	Adjustment of Time for Completion

None	Increase [Number] days	Decrease [Number] days

7.	Other effects, if any

Authorized by: 		Date:

(Employer)

Accepted by: 		Date:

(Contractor)

Annex 6. Pending Agreement Change Order

(Employer’s Letterhead)

To: [Contractor’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

We instruct you to carry out the work in the Change Order detailed below in accordance with GCC Clause 39 of the General Conditions of Contract.

1.	Title of Change: [Name]

2.	Employer’s Request for Change Proposal No./Rev.: [Number/revision]	dated: [Date]

3.	Contractor’s Change Proposal No./Rev.: [Number/revision]	dated: [Date]

4.	Brief Description of Change: [Description]

5.	Facilities and/or Item No. of equipment related to the requested Change: [Facilities]

6.	Reference Drawings and/or technical documents for the requested Change:

Drawing/Document No.	Description

7.	Adjustment of Time for Completion:

8.	Other change in the Contract terms:

9.	Other terms and conditions:

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

Annex 7. Application for Change Proposal

(Contractor’s Letterhead)

To: [Employer’s name and address]	Date:

Attention: [Name and title]

Contract Name: [Contract name]

Contract Number: [Contract number]

Dear Ladies and/or Gentlemen:

We hereby propose that the below-mentioned work be treated as a Change in the Facilities.

1.	Title of Change: [Name]

2.	Application for Change Proposal No./Rev.: [Number/revision]	dated: [Date]

3.	Brief Description of Change: [Description]

4.	Reasons for Change:

5.	Order of Magnitude Estimation (in the currencies of the Contract):

6.	Scheduled Impact of Change:

7.	Effect on Functional Guarantees, if any:

8.	Appendix:

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

# Section VIII. Eligible Countries

1.	Eligibility for the Provision of Goods, Works and Services in Zambia

1.	In accordance with Section 61 of the Public Procurement Act No. 12 of 2008 and Clause 155 of the Public Procurement Regulations of 2011, the Government permits firms and individuals from all countries to offer goods, works and services for Government-financed projects. As an exception, firms of a Country or goods manufactured in a Country may be excluded if:

(i): as a matter of law or official regulation, the Government prohibits commercial relations with that Country, provided that the Cooperating Partners involved are satisfied that such exclusion does not preclude effective competition for the supply of the Goods required, or

(ii): by an Act of Compliance with a Decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government prohibits any import of goods from that Country or any payments to persons or entities in that Country.

2.	For the information of bidders, at the present time firms, goods and services from the following countries are excluded from this bidding:

(a) 	With reference to paragraph (i) above:

_________________________

_________________________

(b) 	With reference to paragraph (ii) above:

_________________________

_________________________

In this context, any action taken by a bidder, supplier, contractor, or any of its personnel, agents, sub-consultants, sub-contractors, service providers, suppliers and/or their employees to influence the procurement process or contract execution for undue advantage is improper.

“Another party” refers to a public official acting in relation to the procurement process or contract execution. In this context, “public official” includes Government staff and employees of other organizations taking or reviewing procurement decisions.

“Party” refers to a public official; the terms  “benefit” and “obligation” relate to the procurement process or contract execution; and the “act or omission” is intended to influence the procurement process or contract execution.

“Parties” refers to participants in the procurement process (including public officials) attempting to establish bid prices at artificial, non competitive levels.

“Party” refers to a participant in the procurement process or contract execution.

b 	A nominated sub-contractor, consultant, manufacturer or supplier, or service provider (different names are used depending on the particular bidding document) is one which either has been: (i) included by the bidder in its pre-qualification application or bid because it brings specific and critical experience and know-how that are accounted for in the evaluation of the bidder’s pre-qualification application or the bid; or (ii) appointed by the Procuring Entity.

The Employer should insert either the Bank Guarantee (4.1) or the Conditional Guarantee (4.2).

The Guarantor shall insert an amount representing the percentage of the Contract Price specified in the Contract and denominated either in the currency(ies) of the Contract or a freely convertible currency acceptable to the Employer.

This text shall be revised as and where necessary to take into account (i) partial acceptance of the Facilities in accordance with Sub-Clause 25.4 of the GCC; and (ii) extension of the performance security when the Contractor is liable for an extended warranty obligation pursuant to Sub-Clause 27.10 of the GCC (although in this latter case the Employer might want to consider an extended warranty security in lieu of the extension of the performance security).

Insert the date twenty-eight days after the expected expiration date of the Defect Liability Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

Insert the expected expiration date of the Time for Completion. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

Refer to Annex 7.

Costs shall be in the currencies of the Contract.

Costs shall be in the currencies of the Contract.

2 Specify where necessary.